## Project Plan
Project Name |  | WIOA
Start Date |  | 21.05.2025
End Date |  | 29.07.2025
Teams |  | UI, API, DB and QA teams
S.No | SDLC Phase | Task Description | Start Date | End Date | End Date | Type | Dependency | Owner/Team | Status
1 | Requirements | Requirements & Analysis | 21.05.2025 | 02.06.2025 |  | Parallel | None | Requirements and Testing | Completed
2 | Design & Development | UI Development – New & Change Requirements + UI Fixes (All Portals) - 400 Issues | 26.05.2025 | 20.06.2025 | 25.06.2025 | Parallel | None | UI Team | In Progress
3 | Development | Caseworker Portal API Binding(191 APIs) | 16.04.2025 | 20.06.2025 | 11.07.2025 | Parallel | None | UI Team | In Progress
4 | Development | Database Development – All Portals (CW, Employer, Client) | 28.04.2025 | 20.06.2025 | 27.07.2025 | Parallel | None | DB Team | In Progress
5 | Testing Preparation | Test Case Creation – All Modules | 03.06.2025 | 16.06.2025 |  | Parallel | None | Requirements and Testing | In Progress
6 | Development | API Development – All Portals (Caseworker, Employer, Client) | 29.04.2025 | 30.06.2025 | 04.07.2025 | Sequential | Starts after DB & partial UI work | API Team | In Progress
7 | Development | API Binding – Employer (73 APIs) + Client Portal (101 APIs) | 01.07.2025 | 11.07.2025 | 11.07.2025 | Sequential | After all APIs are developed | UI Team | In Progress
8 | Contingency | Buffer/Contingency Period | 12.07.2025 | 18.07.2025 |  | Sequential | Follows API Binding | Entire Project Team | Yet to Start
9 | Testing | Testing Phase – Functional + Integration (4 QA Resources, 6 Days) | 22.07.2025 | 29.07.2025 |  | Sequential | After buffer and all integration tasks | Requirements and Testing | Yet to Start

## Case Worker
Portal | Module | Screen name | Priority | Requirement Date | DB Team | [5 empty] | API Team
[5 empty] | Procedure | DB Status | DB Resource | ETA | Completed On | DB Comments | API EndPoint | API Resource | API Status | ETA | Completed On | API Comment | Task Description | UI Resource | ETA for API | ETA for UI | Status | Completed On | Comments | Dependencies | Due date
Case Worker Portal | Login | Login User Info |  |  | Users$Sp_Get_UserInfo.sql6:56 AM | completed | Nithyasri | 2025-06-09 |  |  | GET ~/api/login/get/info |  | Completed | 2025-06-10 |  | Working | Service consumption & Data Binding | Kamalanathan | 13/06/2025 |  | completed | 26/6/2025 |  |  | Assigned To | Total ETA(hrs) | Total ETA(days)
Case Worker Portal | Login | Sign-In |  |  | Users$Sp_Login_AuthenticateByEmail.sql | completed | Nithyasri |  |  |  | GET ~/api/login/authenticate-email |  | Completed |  |  | Working | Service consumption & Data Binding | Kamalanathan | 13/06/2025 |  | completed | 26/6/2025 |  |  |  |  | With buffer
Case Worker Portal | Login | LogOut |  |  | Users$Sp_Logout_User.sql | completed | Nithyasri |  |  |  | PUT ~/api/login/logout |  | Completed |  |  | Working | Service consumption & Data Binding | Kamalanathan | 13/06/2025 |  | db issue
Case Worker Portal | Login | Confirm Forget Password Request |  |  | Users$Sp_PasswordReset_Confirm.sql | completed | Nithyasri |  |  |  | PUT ~/api/login/password/reset/confirm |  | Completed |  |  |  | Service consumption & Data Binding | Kamalanathan | 13/06/2025 |  | need screen |  |  |  | Ezhavendhan | 71.66 hrs | 10days
Case Worker Portal | Login | Forget Password Request |  |  | Users$Sp_PasswordReset_Request.sql | completed | Nithyasri |  |  |  | POST ~/api/login/password/reset/request |  | Completed |  |  | Working | Service consumption & Data Binding | Kamalanathan | 13/06/2025 |  | completed | 26/6/2025 |  |  | Gokul | 78.00 hrs | 11days
Case Worker Portal | Login | Forget Password Request |  |  | Users$Sp_MailToken_Validate | completed | Nithyasri |  | 2025-07-08 | New Procedure | POST ~ /api/login/user/validate-mail-token |  |  |  |  | Working
Case Worker Portal | Login | Two Factor Login |  |  | usp_sp_tw | Pending | Nithyasri | 2025-06-09 | [5 empty] | 2025-06-10 |  | Not Valid
Case Worker Portal | Login | Two Factor Login |  |  | Users$Sp_MailToken_Validate | completed | Nithyasri |  |  |  | POST ~/api/login/user/validate-mail-token |  |  |  |  | Working
Case Worker Portal | Dashboard | Quick Statistics | High |  | dbo.Dashboard_GetSummaryCounts_Fields_S2 | completed |  | 2025-06-09 |  |  | GET~api/dashboard/dashboard/summary |  |  | 2025-06-10 |  | Working | Service consumption & Data Binding | Manoj | 13/06/2025 |  | DB Re-work |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework by DB. Not received | Kamalanathan | 0.00 hrs | 0.00 days
Case Worker Portal | Dashboard | Overdue Tasks |  |  | dbo.usp_WIOA_Dashboard_OverdueTasksByCaseworker | completed |  | 2025-06-09 |  |  | POST~/api/dashboard/overdue-tasks |  |  | 2025-06-10 |  | Working | API verification, Data Binding | Manoj | 13/06/2025 |  | DB Re-work |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework by DB. Not received | Manoj | 51.25 hrs | 8 days
Case Worker Portal | Dashboard | Upcoming Appointments |  |  | Appointment$Sp_GetUpcomingAppointmentsByCaseMember | completed |  | 2025-06-09 |  |  | POST~/api/dashboard/appointments/upcoming |  | Completed |  | 2025-06-25 | Working | API verification, Data Binding | Manoj | 13/06/2025 |  | DB Re-work |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework by DB. Not received | Sri Karthik | 23.50 hrs | 5 days
Case Worker Portal | Dashboard | new applications |  |  | dbo.Applicant$Sp_GetLatestNewApplication | completed |  | 2025-06-09 |  |  | Get~/api/dashboard/applicant/latest |  | Completed |  | 2025-06-25 | Working | API verification, Data Binding | Manoj | 13/06/2025 |  | DB Re-work |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework by DB. Not received | Vinoth | 52.92 hrs | 8 days
Case Worker Portal | Dashboard | Dashboard_GetAllData_S1 |  |  | Dashboard_GetAllData_S1 | completed |  | 2025-06-09 |  |  | GET~api/dashboard/dashboard/snapshot |  | Completed |  |  | Working | API verification, Data Binding | Manoj | 13/06/2025 |  | DB Re-work |  | Data binding - 2hr Api verification - 15mins + 30mins | Rework by DB. Not received | Vivek | 103.00 hrs | 14 days
Case Worker Portal | Dashboard | [11 empty] | Completed
Completed
Case Worker Portal | Dashboard | Announcement |  |  | Announcement_RetrieveAll | completed | Balaji | 2025-06-09 |  |  | er/list |  |  | 2025-06-10 |  | working | API verification, Data Binding | Manoj | 13/06/2025 |  | DB Re-work
Case Worker Portal | Application | Create Caseworker |  |  | usp_User_Add_S1 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | POST~/api/application/user/add |  | Completed |  |  | not used | [7 empty] | Nithya sri
Case Worker Portal | Applicants | Create new Applicant |  |  | usp_Applicant_InsertBase_S1 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | POST~ /api/application/applicant/insertbase |  | Completed |  |  | not used | Service consumption & Data Binding | Manoj | 13/06/2025 |  | not required |  |  | Nithya sri | Except New requirement - Known issues will completed on 11/6/2025
Case Worker Portal | Applicants | Add new Applicants--> Add Barriers |  |  | usp_ApplicantBarrier_Add_S7 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | POST~/api/application/applicant/barriers |  | Completed |  |  | not used | Service consumption & Data Binding | Manoj | 13/06/2025 |  | not required |  |  | Nithya sri
Case Worker Portal | Applicants | Add new Applicants--> Add Public Assistance |  |  | usp_ApplicantPublicAssistance_Add_S6 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | POST ~/api/application/applicant/{applicantId}/public-assistance |  | Completed |  |  | not used | Service consumption & Data Binding | Manoj | 13/06/2025 |  | not required |  |  | Nithya sri
Case Worker Portal | Applicants | Evaluate Eligibility |  |  | usp_Applicant_EvaluateEligibility_S1 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | GET~/api/application/applicant/evaluate-eligibility |  | Completed |  |  | not used | API verification, Data Binding | Manoj | 13/06/2025 |  | not required |  |  | Nithya sri
Case Worker Portal | Applicants | Add new Applicants--> Add eligible program |  |  | usp_ApplicantEligibleProgram_Add_S8 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | POST~/api/application/applicant/eligibleprograms |  | Completed |  |  | not used | Service consumption & Data Binding | Manoj | 13/06/2025 |  | not required |  |  | Nithya sri
Case Worker Portal | Applicants | Add new Applicants-->AddAddress |  |  | usp_ApplicantAddress_Add_S5 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | POST~ /api/application/applicant/addresses |  | Completed |  |  | not used | API verification, Data Binding | Manoj | 13/06/2025 |  | not required |  |  | Nithya sri
Case Worker Portal | Applicants | Add new Applicants--> Upload Documents |  |  | usp_Document_Insert_S3 | Completed | Nithyasri |  |  | Not used In API - Using Inside the DB | POST~ /api/application/documents/add |  | Completed |  |  | not used | Service consumption & Data Binding | Manoj | 13/06/2025 |  | not required |  |  | Nithya sri
Case Worker Portal | Applicants | Add new Applicants-->submit Consent form |  |  | usp_FinalSubmit_S4 | Completed | Nithyasri | 2025-06-09 |  | Not used In API - Using Inside the DB | POST~ /api/application/final-submit |  |  | 2025-06-10 |  | not used | Service consumption & Data Binding | Manoj | 13/06/2025 |  | not required
Case Worker Portal | Applicants | Create new Applicant |  |  | usp_Applicant_Insert_S1 | Completed | Nithyasri | 2025-06-09 | 2025-06-12 | New Procedure | POST~ /api/application/applicant/insert |  | Completed | 2025-06-10 | 2025-06-12 | working |  | Manoj |  |  | Pending
Case Worker Portal | Review Application | ReviewApplication |  |  | usp_ReviewApplication_GetList_S1 | Completed | Nithyasri |  | 2025-06-12 | Modified | GET~/api/application/review/application-list |  | Completed |  | 2025-06-12 | working | Service Consumption, Data Binding | Vivek | 13/06/2025 |  | completed
Case Worker Portal | Review Application | ReviewApplication >> View |  |  | usp_Applicant_GetDetails_S1 | Completed | Nithyasri |  | 2025-06-12 | Modified | GET~/api/application/applicant/details |  | Completed |  | 2025-06-12 | working | Service Consumption, Data Binding | Vivek | 13/06/2025 |  | completed
Case Worker Portal | Review Application | ReviewApplication >> View >> eligibility Results |  |  | usp_ApplicantEligibleProgram_GetAll_S8 | Completed | Nithyasri |  | 2025-06-12 | Modified | GET~/api/application/applicant/eligibleprograms |  | Completed |  | 2025-06-13 | working | Service Consumption, Data Binding | Vivek | 13/06/2025 |  | completed |  | Db rework | partially completed reasoning fields misssing(Nithyasri
Case Worker Portal | Review Application | ReviewApplication >> View >> Documents |  |  | usp_Document_GetAll_S3 | Completed | Nithyasri |  | 2025-06-12 |  | GET ~/api/application/documents/getAllData |  | Completed |  | 2025-06-13 | working | Service Consumption, Data Binding | Vivek | 13/06/2025 |  | completed |  | Db rework | partially completed api issue Status field data is mis matching for differrent applicant id (Nithyasri)
Case Worker Portal | Review Application | Update Document Status |  |  | usp_Document_UpdateStatus_S1 | Completed | Nithyasri |  | 2025-06-12 |  | PUT~/api/application/document/status |  | Completed |  | 2025-06-13 | working | Service Consumption, Data Binding | Vivek | 13/06/2025 |  | completed |  |  | partially completed api issue
Case Worker Portal | Review Application | MESSAGES |  |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri |  | 2025-06-12 | Modified | GET~/api/application/user/message-history |  | Completed |  | 2025-06-13 | working |  | Vivek |  |  |  |  | Db rework | Nithyasri
Case Worker Portal | Review Application | MESSAGES |  |  | usp_Conversation_CreateAndInsertMessage_S1 | Completed | Nithyasri |  | 2025-06-12 | Modified | post~/api/application/conversation/create-insert-message |  | Completed |  | 2025-06-13 | working |  | Vivek |  |  |  |  | Db rework
Case Worker Portal | Review Application | MESSAGES |  |  | usp_Message_ReadStatus_Update_S1 | Completed | Nithyasri |  | 2025-06-12 | New Procedure | PUT~/api/application/message/read-status/update |  | Completed |  | 2025-06-13 | working |  | Vivek |  |  |  |  | Db rework
Case Worker Portal | Review Application | Template |  |  | usp_Template_GetAll_S1 | Completed | Nithyasri |  | 2025-06-12 |  | GET~/api/application/template/getall |  | Completed |  | 2025-06-13 | working | Service consumption & Data Binding | Vivek | 13/06/2025 |  | completed
Case Worker Portal | Review Application | Update applicant details |  |  | usp_Applicant_UpdateBase_S1 | Completed | Nithyasri | 2025-06-09 | 2025-06-12 | Modified | PUT~/api/application/applicant/updatebase |  |  | 2025-06-10 | 2025-06-13 | working | Service consumption & Data Binding | Vivek | 13/06/2025 |  |  |  | DB rework | Nithyasri
Case Worker Portal | Review Application | After Updating the details here again we need to call the evaluate eligibility and Update eligible program |  |  |  | Completed | Nithyasri |  | 2025-06-12 | [7 empty] | API verification, Data Binding | Vivek | 13/06/2025 |  |  |  | Not required
Case Worker Portal | Review Application | Update eligible programs |  |  | usp_ApplicantEligibleProgram_Update_S8 | Completed | Nithyasri |  | 2025-06-12 |  | PUT~/api/application/applicant/eligibleprograms/update |  | Completed |  | 2025-06-13 | not consumed | Service consumption & Data Binding | Vivek | 13/06/2025 |  |  |  | Not required
Case Worker Portal | Review Application | update Public Assitance |  |  | usp_ApplicantPublicAssistance_Update_S6 | Completed | Nithyasri |  | 2025-06-12 |  | PUT~/api/application/applicant/{applicantId}/public-assistance |  | Completed |  | 2025-06-13 | not consumed | Service consumption & Data Binding | Vivek | 13/06/2025 |  |  |  | Not required
Case Worker Portal | Review Application | Update Barriers |  |  | usp_ApplicantBarrier_Update_S7 | Completed | Nithyasri |  | 2025-06-12 |  | PUT~/api/application/applicant-barrier/update |  | Completed |  | 2025-06-13 | not consumed | Service consumption & Data Binding | Vivek | 13/06/2025 |  |  |  | Not required
Case Worker Portal | Review Application | Add preliminary Notes |  |  | usp_PreliminaryNote_AddUpdate_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | POST~/api/application/preliminary-note/add-update |  | Completed |  | 2025-06-13 | working | API verification, Data Binding | Vivek | 13/06/2025 |  | completed
Case Worker Portal | Review Application | Get notes |  |  | usp_PreliminaryNote_Get_S1 | Completed | Nithyasri |  | 2025-06-12 |  | GET~ /api/application/preliminary-note/get |  | Completed |  | 2025-06-13 | working | Service consumption & Data Binding | Vivek | 13/06/2025 |  | completed
Case Worker Portal | Review Application | Update the Application status |  |  | usp_Applicant_UpdateStatus_S1 | Pending | Nithyasri | 2025-06-09 | 2025-06-12 |  | PUT~/api/application/applicant/updatestatus |  | Completed | 2025-06-10 | 2025-06-13 | working | Service consumption & Data Binding | Vivek | 13/06/2025 |  |  |  | Db rework | Nithyasri
Case Worker Portal | Review Application | While giving info requested it will send as message and we need to call the procedure used for messages |  |  |  | Need to map | Nithyasri | 2025-06-05 | [8 empty] | API verification, Data Binding | Vivek | 13/06/2025
Case Worker Portal | Review Application | After approved for the Application user,case will be created for the Application |  |  |  |  | Nithyasri | [9 empty] | API verification, Data Binding | Vivek | 13/06/2025
Case Worker Portal | Review Application | Create User |  |  | usp_User_Add_S1 | Completed | Nithyasri |  |  |  | POST~/api/application/user/add |  | Completed |  |  | not consumed | API verification, Data Binding | Vivek | 13/06/2025 |  |  |  | Not required
Case Worker Portal | Review Application | Create Case |  |  | usp_Case_CreateNew_S1 | Completed | Nithyasri |  |  |  | POST ~ /api/application/case/create |  | Completed |  |  | working | Service consumption & Data Binding | Vivek | 13/06/2025 |  |  |  | Not required
Case Worker Portal | My caseLoad | my case load screen |  |  | usp_MyCaseload_List_S1 | Completed | Nithyasri |  | 21/06/2025 | New Procedure | GET~/api/caseload/my-caseload/list |  | Completed |  | 2025-06-23 |  | Service consumption & Data Binding | Sri karthik | 13/06/2025 |  | SP Re-work |  | Data binding - 1hr
Case Worker Portal | My caseLoad | my case load screen >> actions >> view |  |  | usp_Get_Case_S1 | Pending | Nithyasri |  |  |  | GET ~/api/caseload/get/case |  | Completed |  |  |  | Service consumption & Data Binding | Sri karthik | 13/06/2025 |  | SP Re-work |  | Data binding - 1hr | SP Re-work
Case Worker Portal | My caseLoad | Program Timeline |  |  | usp_Get_ProgramTimeline_ByCase_S1 | Completed | Nithyasri |  | 2025-06-25 | Modified | GET~/api/caseload/programtimeline/bycase |  | Completed |  |  |  | Service consumption & Data Binding | Sri karthik | 13/06/2025 |  | SP Re-work (Descrption Data Missing) |  | Data binding - 1hr | SP Re-work (Descrption Data Missing)
Case Worker Portal | My caseLoad | Assessment |  |  | usp_AssessmentSubmission_Add_S1 | Pending | Nithyasri |  |  |  | POST~ /api/caseload/add-submission |  | Completed |  |  | working | Service consumption & Data Binding | Sri karthik | 13/06/2025 |  | Partially completed |  | Data binding - 1hr | Data Missing
Case Worker Portal | My caseLoad |  |  |  | usp_AssessmentSubmission_RetrieveByID_S1 | Pending | Nithyasri |  |  |  | POST~/api/caseload/retrieve-submission |  | Completed |  |  | working | API verification, Data Binding | Sri karthik | 13/06/2025 |  | SP Re-work |  | Data binding - 1hr Api verification - 15mins + 30mins | SP Re-work
Case Worker Portal | My caseLoad |  |  |  | usp_AssessmentSubmission_Update_S1 | Pending | Nithyasri |  |  |  | PUT~/api/caseload/update-submission |  | Completed |  |  | working | Service consumption | Sri karthik | 13/06/2025 |  | Pending |  |  | API Not Working SQLServerException: Error converting data type nvarchar to int.\r\ncom.arkansas.beans.base.AppsException: org.springframework.jdbc.UncategorizedSQLException:
Case Worker Portal | My caseLoad | create case program and service |  |  | usp_Case_ProgramService_Add_S1 | Completed | Nithyasri |  | 2025-06-23 | Modified | POST~/api/caseload/caseprogramservice/add |  | Completed |  | 2025-06-19 | working | Service consumption | Sri karthik | 13/06/2025 |  | Pending
Case Worker Portal | My caseLoad |  |  |  | usp_Case_ProgramService_Status_Update_S1 | Pending | Nithyasri |  |  |  | PUT~/api/caseload/caseprogramservice/status |  | Completed |  | 2025-06-19 | working | Service consumption | Sri karthik | 13/06/2025 |  | Pending
Case Worker Portal | My caseLoad |  |  |  | usp_Case_ProgramService_Update_S1 | Pending | Nithyasri |  |  |  | PUT~/api/caseload/caseprogramservice/update |  | Completed |  |  | working |  | Sri karthik | 13/06/2025 |  | Pending |  |  | Need REFM SP's for programs and services dropdown. for update program and services
Case Worker Portal | My caseLoad |  |  |  | usp_Case_ProgramService_Get_S1 | Pending | Nithyasri |  |  |  | GET~/api/managecase/case/program-services |  | Completed |  | 2025-06-19 | working | Service consumption & Data Binding | Sri karthik | 13/06/2025 |  | Completed |  | Data binding - 1hr
Case Worker Portal | My caseLoad | Iss |  |  | IssPlan_AddFull_S1 | Completed | Nithyasri |  | 2025-06-27 | Modified | Post ~/api/arkansas/iss-plan/full |  | Completed |  |  | working | Service consumption & Data Binding | Sri karthik | 13/06/2025 |  | Pending |  | Data binding - 1hr
Case Worker Portal | My caseLoad |  |  |  | usp_IssPlan_RetrieveByID_S1 | Completed | Nithyasri |  |  |  | Get ~/api/caseload/issplan/retrieve-by-id |  | Completed |  |  | working | API verification, model and Service - pending | Sri karthik | 13/06/2025 |  | Pending |  | Data binding - 1hr Api verification - 15mins + 30mins DM & Services - 30min
Case Worker Portal | My caseLoad |  |  |  | usp_IssPlan_Update_S1 | Completed | Nithyasri |  |  |  | Put ~ /api/caseload/issplan/update |  | Completed |  |  | working | API verification, model and Service - pending, Service consumption | Sri karthik | 13/06/2025 |  | Pending |  | Data binding - 1hr Api verification - 15mins + 30mins DM & Services - 30min | API Not Working / Fileds Missing AppsException: Not found or concurrency conflict.\r\ncom.arkansas.beans.base.AppsException: Not found or concurrency conflict.\r\n\tat
Case Worker Portal | My caseLoad | case managment |  |  | same sp for get case,update case | Completed | Nithyasri | [5 empty] | Completed |  |  |  | API verification, model and Service - pending, Service consumption | Sri karthik | 13/06/2025 |  | Pending |  | Data binding - 1hr Api verification - 15mins + 30mins DM & Services - 30min
Case Worker Portal | My caseLoad | casenote |  |  | usp_Update_CaseNote_s2 | Completed | Nithyasri |  |  |  | PUT~/api/caseload/case-note/update |  | Completed |  |  | working | API verification, model and Service - pending, Service consumption | Sri karthik | 13/06/2025 |  | Pending |  | Data binding - 1hr Api verification - 15mins + 30mins DM & Services - 30min
Case Worker Portal | My caseLoad | casenote |  |  | usp_Get_CaseNote_s3 | Completed | Nithyasri |  | 2025-06-27 | Modified | GET~/api/caseload/case/note |  | Completed |  |  | working | API verification, model and Service - pending | Sri karthik | 13/06/2025 |  | Pending |  | Data binding - 1hr Api verification - 15mins + 30mins DM & Services - 30min
Case Worker Portal | My caseLoad | casenote |  |  | usp_Add_CaseNote_s1 | Completed | Nithyasri |  |  |  | GET~/api/caseload/case-note/add |  | Completed |  |  | working |  |  | 13/06/2025 |  | Pending
Case Worker Portal | My caseLoad | Training Enrollment |  |  | usp_FormSubmission_RetrieveAll_S1 | Completed | Nithyasri |  | 2025-07-07 |  | GET /api/forms/form-submission/list |  |  |  |  | working
Case Worker Portal | My caseLoad | Carrer Planning |  |  | Job$SpSearchJobs | Completed | Nithyasri |  | 2025-07-07 |  | GET~ /api/job/search |  |  |  |  | working
Case Worker Portal | My caseLoad | Applied Jobs |  |  | Job$SpGetJobApplications | Completed | Nithyasri |  | 2025-07-07 |  | GET/api/job/application/list |  |  |  |  | working
Case Worker Portal | My caseLoad | Resume |  |  | Resume$Sp_GetAll_ResumesByUser | Completed | Nithyasri |  | 2025-07-07 |  | GET~/api/resume/get/all/by-user |  |  |  |  | working
Case Worker Portal | My caseLoad | Carrer development Activities |  |  | usp_CaseMinorActivity_Get_S1 | Completed | Nithyasri |  | 2025-07-07 | Modified | GET~/api/managecase/case/minor-activities |  |  |  |  | working
Case Worker Portal | My caseLoad | Record Activity |  |  | usp_CaseMinorActivity_Insert_S1 | Completed | Nithyasri |  | 2025-07-07 | Modified | POST ~ /api/managecase/insert/case-minor-activity |  |  |  |  | working
Case Worker Portal | My caseLoad |  |  |  | usp_CaseMinorActivity_Update_S1 | Completed | Nithyasri |  | 2025-07-07 | New Procedure | PUT ~/api/managecase/case/minor-activity/update |  |  |  |  | working
Case Worker Portal | My caseLoad | Employment Status |  |  | Employment$Sp_Get_UserEmployment | Completed | Nithyasri |  | 2025-07-07 | New Procedure | GET ~ /api/employer/user/employment |  |  |  |  | working
Case Worker Portal | My caseLoad | Update Employment status |  |  | Employment$Sp_Update_UserEmployment | Completed | Nithyasri |  | 2025-07-07 | New Procedure | POST ~ /api/employer/employment/update-user-employment |  |  |  |  | working
Case Worker Portal | My caseLoad | Mark As Employed |  |  | Employment$Sp_Add_UserEmployment | Completed | Nithyasri |  | 2025-07-07 | New Procedure | POST ~ /api/caseload/add/user-employment |  |  |  |  | working
Case Worker Portal | Case Management | Create new case |  |  | usp_Duplication_Check_S1 | Completed | Nithyasri |  | 2025-06-12 | Modified | GET ~/api/managecase/duplication/check |  | Completed |  | 2025-06-19 | working | API verification, Data Binding | Lakshmi Narayanan | 13/06/2025 | Completed |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | CaseExists |  |  | usp_Get_Case_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | GET~/api/caseload/get/case |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_Case_Update_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | PUT~/api/managecase/case/update |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_UserAddress_Update_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | PUT~/api/managecase/user/address/update |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_Case_ProgramService_Get_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | GET~/api/managecase/case/program-services |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_Case_ProgramService_Update_S1 | Completed | Nithyasri |  | 2025-06-18 |  | PUT~/api/caseload/caseprogramservice/update |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_OrganizationProgram_List_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | GET~/api/managecase/organization/program/list |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_OrganizationProgramService_List_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | GET~/api/managecase/organization/program/services/list |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_Case_ProgramService_Add_S1 | Completed | Nithyasri |  | 2025-06-18 |  | POST~/api/caseload/caseprogramservice/add |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_Case_ProgramService_Status_Update_S1 | Completed | Nithyasri |  | 2025-06-18 |  | PUT~/api/caseload/caseprogramservice/status |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | CaseExists |  |  | usp_CaseProgramService_Delete_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | DELETE~/api/managecase/case/program/service/delete |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | Create Applicant same process |  |  |  | Completed | Nithyasri | [5 empty] | Completed |  |  |  | API verification, Data Binding | Lakshmi Narayanan | 13/06/2025 | Completed |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | caseoverview |  |  | usp_MyCaseload_Fetch_S1 | Completed | Nithyasri |  |  |  | GET~/api/caseload/list |  | Completed |  | 2025-06-19 | working | Service consumption & Data Binding | Sri karthik | 13/06/2025 | Completed | Completed |  | Data binding - 1hr DM & Services- 30mins
Case Worker Portal | Case Management | caseoverview >> View |  |  | usp_Get_Case_S1 | Completed | Nithyasri |  |  |  | GET~/api/caseload/get/case |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | caseoverview >> View |  |  | usp_CasePrimaryNeeds_Get_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/case/primaryneeds |  | Completed |  | 2025-06-19
Case Worker Portal | Case Management | caseoverview |  |  | usp_Case_Update_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | PUT~/api/managecase/case/update |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | caseoverview |  |  | usp_UserAddress_Update_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | PUT~/api/managecase/user/address/update |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | caseoverview >> Service Needed |  |  | usp_Case_ProgramService_Get_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | GET~/api/managecase/case/program-services |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | caseoverview >> Service Needed |  |  | usp_CaseService_Insert_S2 | Completed | Nithyasri |  | 2025-06-18 | Modified | POST~/api/managecase/insert/case-service |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | caseoverview >> Service Needed |  |  | usp_CaseService_Update_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | PUT~/api/managecase/caseservice |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | caseoverview >> Service Needed |  |  | usp_Case_Service_Bycase_Get_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | GET~/api/managecase/case/services |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | caseoverview >> Service Needed |  |  | usp_CaseService_Delete_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | DELETE~/api/managecase/case/service |  | Completed |  | 2025-06-19 | working
Case Worker Portal | Case Management | Service Needed Left Menu |  |  | usp_Get_service_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | GET~/api/managecase/service/list |  | Completed |  | 2025-06-20 | working | Service consumption & Data Binding | Lakshmi Narayanan | 13/06/2025 | Completed |  |  | Data binding - 1hr DM & Services- 30mins | Need Status and categoty description field for grid
Case Worker Portal | Case Management | Service Needed Left Menu |  |  | usp_ServiceNotes_Update_S1 | Completed | Nithyasri |  | 2025-06-18 | Modified | PUT~/api/managecase/service/notes |  | Completed |  | 2025-06-20 | working | API verification, Data Binding | Lakshmi Narayanan | 13/06/2025 | Completed |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Need to update this SP collect the serviceId as array or JSON formet
Case Worker Portal | Case Management | Service Needed Left Menu |  |  | usp_Service_Insert_S1 | Completed | Nithyasri |  | 2025-06-18 |  | POST~/api/managecase/insert/service |  | Completed |  | 2025-06-20 | working | API verification, Data Binding | Lakshmi Narayanan | 13/06/2025 | Completed |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | Service Needed Left Menu |  |  | usp_Service_Update_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | PUT~/api/managecase/update/service |  | Completed |  | 2025-06-20 | working
Case Worker Portal | Case Management | Service Needed Left Menu |  |  | usp_Service_Delete_S1 | Completed | Nithyasri |  | 2025-06-18 | New Procedure | DLEETE~/api/managecase/delete/service |  | Completed |  | 2025-06-20 | working
Case Worker Portal | Case Management | Referrals >> Case Over view |  |  | usp_Referral_Add_S1 | Completed | Nithyasri |  | 2025-06-25 | Modified | POST~/api/managecase/referral/add |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | USP_SENT_REFERRAL_GET_S1 | Completed | Nithyasri |  | 2025-06-25 | New Procedure | GET~ /api/arkansas/referral/sent |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_Referral_Update_S1 | Completed | Nithyasri |  | 2025-06-25 | Modified | PUT~/api/managecase/referral/update |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_Referral_Update_Status_S1 | Completed | Nithyasri |  | 2025-06-25 | New Procedure | PUT~/api/arkansas/referral/status |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_ReferralNote_Add_S1 | Completed | Nithyasri |  | 2025-06-25 | Modified | POST~/api/managecase/referral-note |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_ReferralNote_Update_S1 | Completed | Nithyasri |  | 2025-06-25 | Modified | PUT~/api/managecase/referral-note |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_Referral_FollowUp_History_S1 | Completed | Nithyasri |  | 2025-06-25 | New Procedure | GET ~ /api/arkansas/referral/followup-history |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_ReferralNote_Delete_S1 | Completed | Nithyasri |  | 2025-06-25 | Modified | DELETE~/api/managecase/referral-note |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management | referrals >> Left Menu |  |  | usp_Referral_Add_S1 | Completed | Nithyasri |  |  |  | POST~/api/managecase/referral/add |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_Sent_Referral_Get_S1 | Completed | Nithyasri |  |  |  | GET~/api/arkansas/referral/sent |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_Received_Referral_Get_S1 | Completed | Nithyasri |  | 2025-06-25 | New Procedure | GET~/api/job/referral/received/list |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management |  |  |  | usp_ReferralResponse_Update_S1 | Completed | Nithyasri |  | 2025-06-25 | New Procedure | PUT~/api/managecase/update/referral/response |  | Completed |  | 2025-06-26 | working
Case Worker Portal | Case Management |  |  |  | usp_ReferralOutcome_Update_S1 | Completed | Nithyasri |  | 2025-06-25 | New Procedure | PUT~/api/arkansas/referral/outcome/update |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management | Detailed plan >> Left Menu |  |  | usp_DetailedPlan_User_Get_S1 | Completed | Nithyasri |  | 2025-06-26 | New Procedure | GET ~ /api/managecase/detailed-plan/user |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_IssPlan_RetrieveByID_S1 | Completed | Nithyasri |  | 2025-06-26 |  | GET ~ /api/caseload/issplan/retrieve-by-id |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_IssPlan_Goals_Get_S1 | Completed | Nithyasri |  | 2025-06-26 | New Procedure | POST ~/api/managecase/issplan/goals |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_Goal_Add_S1 | Completed | Nithyasri |  | 2025-06-26 | New Procedure | POST ~ /api/managecase/goal |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | IssGoal_Update_S1 | Completed | Nithyasri |  | 2025-06-26 | New Procedure | PUT ~ /api/arkansas/iss-goal |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | IssGoal_Delete_S1 | Completed | Nithyasri |  | 2025-06-26 | New Procedure | DELETE ~ /api/arkansas/iss-goal |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_GoalActionItem_Update_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | PUT ~ /api/managecase/update/goal/action-item |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_GoalActionItem_Delete_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | DELETE ~ api/managecase/delete/goal/action-item |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_GoalActionItem_Add_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | POST ~ api/managecase/goal-action-item/add |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_GoalActionItem_GetDetail_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | GET~/api/managecase/fetch/goal/action-item |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | usp_GoalActionItem_UpdateStatus_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | Put ~/api/managecase/goal-action-item/update-status |  |  |  |  | working
Case Worker Portal | Case Management | Detailed plan |  |  | IssGoal_UpdateStatus_S1 | Completed | Nithyasri |  | 2025-06-26 | New Procedure | Put ~/api/managecase/issgoal/status |  |  |  |  | not implemented
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_UserProgress_GetParticipants_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | GET ~ api/managecase/user-progress/participants |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_UserProgress_Milestones_Get_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | GET ~ api/managecase/user-progress/milestones |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_ProgressOutcome_Get_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | GET ~ api/managecase/progress-outcome/get |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_UserProgress_Milestones_Add_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | POST ~ api/managecase/user-progress/add-with-milestones |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_UserProgress_DeleteByCase_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | DELETE ~ api/managecase/user-progress/delete-by-case |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_ProgressMilestones_Notes_List_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | GET ~ api/managecase/milestone-notes/list |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_ProgressMilestones_UpdateStatus_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | PUT ~ api/managecase/milestones/update-status |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_ProgressOutcome_Add_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | POST ~ api/managecase/progress-outcome/add |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_ProgressOutcome_Update_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | PUT ~ api/managecase/progress-outcome/update |  |  |  |  | Working
Case Worker Portal | Case Management | Progress Tracking |  |  | usp_ProgressOutcome_Get_S1 | Completed | Nithyasri |  | 2025-06-27 | New Procedure | GET ~ api/managecase/progress-outcome/get |  |  |  |  | Working
Case Worker Portal | Case Management |  |  |  | usp_CaseService_Insert_S2 | Completed | Nithyasri |  |  |  | POST~/api/managecase/insert/case-service |  | Completed |  | 2025-06-19 | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_CaseService_Update_S1 | Completed | Nithyasri |  |  |  | PUT~/api/managecase/caseservice |  | Completed |  | 2025-06-19 | Working | API verification, Data Binding | Vivek | 13/06/2025 |  |  |  | Partially completed
Case Worker Portal | Case Management |  |  |  | usp_Case_Service_Bycase_Get_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/case/services |  | Completed |  | 2025-06-19 | Working | API verification, Data Binding | Vivek | 13/06/2025 |  |  |  | Db rework
Case Worker Portal | Case Management | My caseLoad >> after completing |  |  | usp_CaseMinorActivity_Insert_S1 | Completed | Nithyasri |  |  |  | POST ~ /api/managecase/insert/case-minor-activity |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_CaseMinorActivity_Status_Update_S1 | Completed | Nithyasri |  |  |  | PUT ~/api/managecase/caseminoractivity/updatestatus |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_CaseMinorActivity_Get_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/case/minor-activities |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_CaseMajorActivity_Status_Update_S1 | Completed | Nithyasri |  |  |  | PUT ~ /api/managecase/update/case-major-activity-status |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins DM & Services - 30min
Case Worker Portal | Case Management |  |  |  | usp_CaseMajorActivity_Get_S1 | Pending | Nithyasri | 2025-06-09 |  |  | GET ~ /api/managecase/case/major-activities |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_CaseMajorActivity_Add_S1 | Pending | Nithyasri | 2025-06-09 |  |  | POST~/api/managecase/case/majoractivity |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins DM & Services - 30min
Case Worker Portal | Case Management | primary needs |  |  | usp_CaseprimaryNeeds_Insert_S1 | Completed | Nithyasri |  |  |  | POST~/api/managecase/case/primaryneeds |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_CasePrimaryNeeds_Get_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/case/primaryneeds |  | Completed |  | 2025-06-19 | Working | API verification, Data Binding |  | 13/06/2025 |  | Completed |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_CasePrimaryNeeds_Update_S1 | Completed | Nithyasri |  |  |  | PUT~/api/managecase/case/primaryneeds |  | Completed |  |  | Working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | Progress tracking update |  |  |  | Pending | Nithyasri | 2025-06-09 | [5 empty] | 2025-06-10 |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | progress chart |  |  |  | Pending | Nithyasri | 2025-06-09 | [5 empty] | 2025-06-10 |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management |  |  |  | usp_Referral_Add_S1 | Completed | Nithyasri |  |  |  | POST~ /api/managecase/referral/add |  | Completed |  |  | working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | API Pending for Dropdowns | Bhuvan
Case Worker Portal | Case Management | Get Referrals |  |  | usp_Sent_Referral_Get_S1 |  | Nithyasri |  |  |  | GET~ /api/arkansas/referral/sent |  | Completed |  | 2025-06-25 | working
Case Worker Portal | Case Management | [5 empty] | Nithyasri
Case Worker Portal | Case Management | [5 empty] | Nithyasri
Case Worker Portal | Case Management | get referrral |  |  | usp_Referral_GetAllDetails_S1 | Completed | Nithyasri |  |  |  | GET~ /api/managecase/allReferral/details |  | Completed |  |  | NO Data | API verification, Data Binding |  | 13/06/2025 |  | Completed |  | Data binding - 1hr Api verification - 15mins + 30mins | Need Addition Field in Output | Bhuvan
Case Worker Portal | Case Management | get partner agencies |  |  | usp_PartnerAgency_GetAll_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/partner-agency/list |  | Completed |  |  | working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Service issue - Input Field Missing | Bhuvan
Case Worker Portal | Case Management | delete referral |  |  | usp_Referral_Delete_S1 | Completed | Nithyasri |  |  |  | DELETE~ /api/managecase/referral/delete |  | Completed |  |  | working | API verification, Data Binding |  | 13/06/2025 |  | Completed |  | Data binding - 1hr Api verification - 15mins + 30mins | Completed | Bhuvan
Case Worker Portal | Case Management | update referral |  |  | usp_Referral_Update_S1 | Completed | Nithyasri |  |  |  | PUT~/api/managecase/referral/update |  | Completed |  |  | working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | API Pending for Dropdowns | Bhuvan
Case Worker Portal | Case Management | view referral |  |  | usp_Referral_GetDetails_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/referral/details |  | Completed |  |  | No Data | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Not Required
Case Worker Portal | Case Management | detailed plan -> get participants |  |  | dbo.CASE$SP_GET_CASE_LIST | Completed | Nithyasri |  |  |  | GET~/api/managecase/case/list |  | Completed |  |  | working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | DB Issue
Case Worker Portal | Case Management | add goal |  |  | usp_Goal_Add_S1 | Completed | Nithyasri |  |  |  | PUT~/api/managecase/goal |  | Completed |  |  | working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework from DB
Case Worker Portal | Case Management | getiss |  |  | usp_Case_GetGoalsWithActionItemsReport_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/case/goals-report |  | Completed |  |  | No Data | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework from DB
Case Worker Portal | Case Management | edit goal |  |  | usp_Goal_Update_S1 | Completed | Nithyasri |  |  |  | PUT/api/managecase/goal/update |  | Completed |  |  | working | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework from DB
Case Worker Portal | Case Management | delete goal |  |  | usp_Goal_Delete_S1 | Completed | Nithyasri |  |  |  | DELETE/api/managecase/goal/delete |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework from DB
Case Worker Portal | Case Management | add action item |  |  | usp_GoalActionItem_Add_S1 | Completed | Nithyasri |  |  |  | POST/api/managecase/goal-action-item/add |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework from DB
Case Worker Portal | Case Management | update action item |  |  | usp_GoalActionItem_Update_S1 | Completed | Nithyasri |  |  |  | Update~/api/managecase/update/goal/action-item |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework from DB
Case Worker Portal | Case Management | delete action item |  |  | usp_GoalActionItem_Delete_S1 | Completed | Nithyasri |  |  |  | DELETE ~/api/managecase/delete/goal/action-item |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework from DB
Case Worker Portal | Case Management | add referrral note |  |  | usp_ReferralNote_Add_S1 | Completed | Nithyasri |  |  |  | POST~/api/managecase/referral-note |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | delete referral note |  |  | usp_ReferralNote_Delete_S1 | Completed | Nithyasri |  |  |  | DELETE~/api/managecase/referral-note |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | update referral note |  |  | usp_ReferralNote_Update_S1 | Completed | Nithyasri |  |  |  | PUT~/api/managecase/referral-note |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | get active referral |  |  | usp_Referral_GetActive_S1 | Completed | Nithyasri |  |  |  | GET~ /api/managecase/referral/active |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | progress tracking -> get list |  |  | dbo.CASE$SP_GET_CASE_PERCENT | Pending | Nithyasri | 2025-06-09 |  |  | GET /api/managecase/case/get-case-percent |  |  | 2025-06-10 |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | DB Issue
Case Worker Portal | Case Management | oucome |  |  | WIOA_SP_GET_PROGRAM_OUTCOME | Completed | Nithyasri |  |  |  | GET /api/managecase/program/get-outcomes |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | get goal |  |  | usp_Goal_GetDetail_S1 | Completed | Nithyasri |  |  |  | GET/api/managecase/goal/detail |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | get action item |  |  | usp_GoalActionItem_GetDetail_S1 | Completed | Nithyasri |  |  |  | GET~/api/managecase/fetch/goal/action-item |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | update action item status |  |  | usp_GoalActionItem_UpdateStatus_S1 | Completed | Nithyasri |  |  |  | Put ~/api/managecase/goal-action-item/update-status |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins
Case Worker Portal | Case Management | get milestones |  |  | usp_Case_GetCaseActivites | Completed | Nithyasri |  |  |  | GET~ /api/managecase/activities |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | DB issue
Case Worker Portal | Case Management | get active referrals |  |  | usp_Referral_GetActive_S1 | Completed | Nithyasri |  |  |  | GET~ /api/managecase/referral/active |  | Completed |  |  |  | API verification, Data Binding |  | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 15mins + 30mins | Rework
Case Worker Portal | Case Management | add service |  |  | CustomCaseService_Add_S1 | Completed | Nithyasri |  |  | Not in Use | POST~/api/customcase/custom-case-service/add |  | Completed |  | 2025-06-25 | not in use |  |  | 13/06/2025
Case Worker Portal | Case Management | update service |  |  | CustomCaseService_Update_S1 | Completed | Nithyasri |  |  | Not in Use | PUT~/api/customcase/custom-case-service/update |  | Completed |  |  | not in use |  |  | 13/06/2025
Case Worker Portal | Case Management | delete service |  |  | CustomCaseService_Delete_S1 | Completed | Nithyasri |  |  | Not in Use | DELETE~/api/customcase/custom-case-service/delete |  | Completed |  |  | not in use |  |  | 13/06/2025
Case Worker Portal | Case Management | get service by id |  |  | CustomCaseService_GetByID_S1 | Completed | Nithyasri |  |  | Not in Use | GET~/api/customcase/custom-case-service/get-by-id |  | Completed |  |  | not in use |  |  | 13/06/2025
Case Worker Portal | Case Management | get all service |  |  | CustomCaseService_Search_S1 | Completed | Nithyasri |  |  | Not in Use | GET~/api/customcase/custom-case-service/get-by-id |  | Completed |  |  | not in use |  |  | 13/06/2025
Case Worker Portal | Appointments | get all appointment |  |  | Calendar$SpGetAppointmentsByUser | Completed | Pavan kalyan |  | 2025-07-02 |  | GET~/api/arkansas/calendar/appointments |  | Completed |  | 2025-06-25 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | Data binding - 1hr Api verification - 30mins
Case Worker Portal | Appointments | get calendars |  |  | CALENDAR_RetrieveAll_S1 | Completed | Pavan kalyan |  | 2025-06-27 |  | Get~/api/appointments/calendar/list |  | Completed |  | 2025-06-23 | working | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | field missing - color code.
Case Worker Portal | Appointments | add calendar |  |  | CALENDAR_Add_S1 | Completed | Pavan kalyan |  | 2025-06-20 |  | POST~ /api/appointments/calendar/add |  | Completed |  | 2025-06-23 | working | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | field missing :workspaceNameText,location
Case Worker Portal | Appointments | update calendar |  |  | Calendar$Sp_Update_Calendar | Completed | Pavan kalyan |  | 2025-06-20 |  | Put~/api/appointments/update |  | Completed |  | 2025-06-23 | working | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | field missing : workspaceNameText, calendarUrlText
Case Worker Portal | Appointments | while update get the existing data |  |  | CALENDAR_RetrieveByID_S1 | Completed | Pavan kalyan |  | 2025-06-20 |  | Get~/api/appointments/calendar |  | Completed |  | 2025-06-23 | working | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | field missing : workspaceNameText, calendarUrlText
Case Worker Portal | Appointments | Calendar --> Delete calendar |  |  | Calendar$Sp_Delete_Calendar | Completed | Pavan kalyan |  |  |  | DELETE ~/api/appointments/delete |  | Completed |  |  | working | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | Calendar --> update status deactivate or activate calendar |  |  | Calendar$Sp_Update_Calendar_Status | Completed | Pavan kalyan |  |  |  | PUT ~/api/appointments/update-status |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | calendar - > availability update |  |  | Calendar$SpUpdateCalendarAvailability | Completed | Pavan kalyan |  |  |  | PUT~/api/appointments/calendar/update-availability |  | Completed |  |  | working | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | Calendar - > Calendar availabilityget |  |  | Calendar$SpGetCalendarAvailability | Completed | Pavan kalyan |  | 2025-06-20 |  | GET~/api/appointments/calendar/availability |  | Completed |  | 2025-06-23 | working | API verification pending, Data Binding pending | Vinoth | 13/06/2025
| Appointments | get one time booking link |  |  | Calendar$SpGetTempCalendarShareLink | Completed | Pavan kalyan |  | 2025-06-25 | new procedure | GET~/api/appointments/calendar/share-link/temp |  | Completed |  | 2025-06-25 | working
| Appointments | Add one time url link |  |  | Calendar$SpAddShareLink | Completed | Pavan kalyan |  | 2025-06-25 | new procedure | POST~/api/appointments/calendar/share-link/add |  | Completed |  | 2025-06-25 | working
| Appointments | update url link status after booking |  |  | Calendar$SpUpdateExpireShareLink | Completed | Pavan kalyan |  | 2025-06-25 | new procedure | PUT~/api/appointments/calendar/share-link/expire |  | Completed |  | 2025-06-25 | working
| Appointments | get share link workspace |  |  | Calendar$SpGetShareLinkWorkspace | Completed | Pavan kalyan |  | 2025-06-25 | new procedure | GET ~ /api/appointments/calendar/share-link/workspace |  | Completed |  | 2025-06-25 | working
| Appointments | get unavailbility slots |  |  | Calendar$SpGetCalendarUnAvailabilitySlots | Completed | Pavan kalyan |  | 2025-07-01 |  | GET ~ /api/appointments/calendar/unavailable-slots |  | Completed |  | 2025-06-25
Case Worker Portal | Appointments | working hours default user availability timings |  |  | USER_CreateDefaultWorkingHours_S1 | Completed | Pavan kalyan |  |  |  | POST~/api/appointments/user/default-working-hours |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | Working Hours ->user update availability timings |  |  | WORKINGHOURS_Save_S1 | Completed | Pavan kalyan |  |  |  | PUT~/api/appointments/working-hours/save |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | Working Hours -->get working hours |  |  | Calendar$SpGetUserWorkingHours | Completed | Pavan kalyan |  |  |  | GET~ /api/appointments/user/working-hours |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | Field name : overrideDate is mistmatched
Case Worker Portal | Appointments | add unit |  |  | UNIT_InsertWithMembers_S1 | Completed | Pavan kalyan |  |  |  | POST ~/api/appointments/insert-with-members |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | update unit |  |  | UNIT_UpdateWithMembers_S1 | Completed | Pavan kalyan |  | 2025-06-20 |  | PUT ~ /api/appointments/unit/update-with-members |  | Completed |  | 2025-06-23 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | get all units |  |  | UNIT_RetrieveAll_S1 | Completed | Pavan kalyan |  | 2025-06-20 |  | GET ~ /api/appointments/unit/list |  | Completed |  | 2025-06-23 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | get single unit |  |  | UNIT_RetrieveByID_S1 | Completed | Pavan kalyan |  |  |  | GET ~ /api/appointments/unit/detail |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | Error: SQLServerException: The column name CreatedBy_Name is not valid
Case Worker Portal | Appointments | update unit status |  |  | UNIT_UpdateStatus_S1 | Completed | Pavan kalyan |  | 2025-06-20 |  | PUT ~ /api/appointments/unit/status |  | Completed |  | 2025-06-23 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | add meeting room |  |  | MeetingRooms$Sp_Add_MeetingRoom | Completed | Pavan kalyan |  | 2025-06-20 |  | POST ~ /api/appointments/add/meeting-room |  | Completed |  | 2025-06-23 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | Missing Fields - passcode, email, avartarImageUrl; Field name: usersJson - data not added
Case Worker Portal | Appointments | update meeting room |  |  | MeetingRooms$Sp_Update_MeetingRoom | Completed | Pavan kalyan |  | 2025-06-20 |  | POST ~ /api/appointments/update/meeting-room |  | Completed |  | 2025-06-23 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | Missing Fields - passcode, email, avartarImageUrl; Field name:usersJson - data not added
Case Worker Portal | Appointments | delete meeting room |  |  | MeetingRooms$Sp_Delete_MeetingRoom | Completed | Pavan kalyan |  | 2025-06-20 |  | DELETE ~ /api/appointments/delete/meeting-room |  | Completed |  | 2025-06-23 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | field missing - TransactionSeqEvent_NUMB
Case Worker Portal | Appointments | get all meeting rooms |  |  | MeetingRooms$Sp_Get_MeetingRooms | Completed | Pavan kalyan |  |  |  | GET ~ /api/appointments/get/meeting-rooms |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  |  |  | "SQLServerException: The column name RowCount_NUMB is not valid
Case Worker Portal | Appointments | get single meeting room |  |  | MeetingRooms$Sp_Get_MeetingRoomInfo | Completed | Pavan kalyan |  |  |  | GET ~ /api/appointments/get/meeting-room-info |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | add appointment |  |  | Calendar$SpAddAppointment | Completed | Pavan kalyan |  | 2025-06-25 |  | POST ~ /api/appointments/add/appointment |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | update appointment |  |  | Calendar$SpUpdateAppointment | Completed | Pavan kalyan |  | 2025-06-25 |  | PUT~ /api/appointments/calendar/appointment |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | delete appointment |  |  | Calendar$SpDeleteAppointment | Completed | Pavan kalyan |  |  |  | DELETE ~ /api/appointments/delete/appointment |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | get appointment |  |  | Calendar$SpGetAppointment | Completed | Pavan kalyan |  | 2025-06-25 |  | GET~ /api/appointments/calendar/appointment |  | Completed |  | 2025-06-24 |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | get availbility slots |  |  | Calendar$SpGetCalendarAvailabilitySlots | Completed | Pavan kalyan |  | 2025-07-01 |  | GET~/api/appointments/calendar/availability-slots |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025
Case Worker Portal | Appointments | shareAppointment |  |  | Calendar$SpShareAppointmentViaEmail | Completed | Pavan kalyan |  | 2025-07-01 | new procedure | POST ~ /api/appointments/calendar/share-appointment
Case Worker Portal | Appointments | update-rsvp-status |  |  | Calendar$SpUpdateAppointmentRsvpStatus | Completed | Pavan kalyan |  | 2025-07-01 | new procedure | PUT ~ /api/appointments/calendar/update-rsvp-status
Case Worker Portal | Appointments | switch profile |  |  | Common$SpGetWorkspaceList | Completed | Pavan kalyan |  | 2025-07-09 | new procedure | GET ~ /api/arkansas/workspace/list
Case Worker Portal | Appointments |  |  |  | Calendar$SpGetCalendarUnitMembers | Completed | Pavan kalyan |  | 2025-07-24 | new procedure | GET~/api/appointments/calendar/unit-members
Case Worker Portal | Documents | get applicants list |  |  | Applicant_Get_With_Documents_S1 | Completed | Nivetha |  | 2025-06-26 |  | GET ~ /api/documents/applicants/with-documents |  |  |  |  | Working
Case Worker Portal | Documents | upload new document |  |  | usp_ApplicantDocument_AddBatch_S1 | Completed | Nivetha |  |  |  | POST /api/documents/applicant-document/add-batch |  | Completed |  |  | Working | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | view all documents |  |  | Applicant$Sp_GetAllApplicants | Completed | Nivetha |  |  |  | GET ~/api/documents/applicants/all |  | Completed |  |  | Working | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 20mins Data binding - 1hr
Case Worker Portal | Documents | 1.view all documents -> click on applicant |  |  | usp_ApplicantDocument_GetAll_S1 | Completed | Nivetha |  |  |  | GET/api/documents/list |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 20mins Data binding - 1hr
Case Worker Portal | Documents | 2.view all documetns -> click applicant -> click view on document |  |  | usp_ApplicantDocument_GetDetails_S1 | Completed | Nivetha |  |  |  | GET~/api/documents/applicant/document/details |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 20mins Data binding - 1hr 40mins
Case Worker Portal | Documents | 3.view all documetns -> click applicant ->edit document |  |  | usp_ApplicantDocument_UpdateMetadata_S1 | Completed | Nivetha |  |  |  | PUT/api/documents/document/update-metadata |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 4.view all documetns -> click applicant ->delete document |  |  | usp_ApplicantDocument_Delete_S1 | Completed | Nivetha |  |  |  | POST/api/documents/applicant/document/delete |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 5.view all documetns -> click applicant->Update verification status |  |  | usp_ApplicantDocument_UpdateVerificationStatus_S1 | Completed | Nivetha |  |  |  | PUT/api/documents/applicantdocument/updateverificationstatus |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 6.view all documetns -> click applicant->manage->Upload new version |  |  | usp_ApplicantDocument_AddNewVersion_S1 | Completed | Nivetha |  |  |  | POST /api/documents/applicant-document/add-new-version |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 7.view all documetns -> click applicant->manage ->VERSION HISTORY |  |  | usp_ApplicantDocument_GetVersionHistoryByDocument_S1 | Completed | Nivetha |  |  |  | GET/api/documents/version-history |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed
Case Worker Portal | Documents | 8.view all documetns -> click applicant->manage ->verification |  |  | usp_ApplicantDocument_GetVersionHistoryByDocument_S1 | Completed | Nivetha |  |  |  | GET/api/documents/version-history |  | Completed |  |  |  |  | Kamalanathan | 13/06/2025 |  | completed
Case Worker Portal | Documents | 8.view all documetns -> click applicant->manage ->verification |  |  | ApplicantDocuments$Sp_Get_VerifiedVersion | Completed | Nivetha |  |  |  | GET~/api/documents/applicant-document/verified-version |  | Completed |  |  |  |  | Kamalanathan | 13/06/2025 |  |  |  | API is not available
Case Worker Portal | Documents | 9.view all documetns -> click applicant->manage ->delete version |  |  | usp_ApplicantDocument_DeleteVersion_S1 | Completed | Nivetha |  |  |  | DELETE/api/documents/document/delete/version |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 10.view all documetns -> click applicant->manage ->move to folder |  |  | usp_ApplicantDocument_MoveFolder_S1 | Completed | Nivetha |  |  |  | PUT/api/documents/move-document-folder |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | manage documents |  |  | Applicant$Sp_GetAllApplicants | Completed | Nivetha |  |  |  | GET ~/api/documents/applicants/all |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed
Case Worker Portal | Documents | 1.manage documents -> click on applicant |  |  | usp_ApplicantDocument_GetAll_S1 | Completed | Nivetha |  |  |  | GET/api/documents/list |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 2.manage documetns -> click applicant -> click view on document |  |  | usp_ApplicantDocument_GetDetails_S1 | Completed | Nivetha |  |  |  | GET~/api/documents/applicant/document/details |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed
Case Worker Portal | Documents | 3.manage documetns -> click applicant ->edit document |  |  | usp_ApplicantDocument_UpdateMetadata_S1 | Completed | Nivetha |  |  |  | PUT/api/documents/document/update-metadata |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 4.manage documetns -> click applicant ->delete document |  |  | usp_ApplicantDocument_Delete_S1 | Completed | Nivetha |  |  |  | POST/api/documents/applicant/document/delete |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 5.manage documetns -> click applicant->Update verification status |  |  | usp_ApplicantDocument_UpdateVerificationStatus_S1 | Completed | Nivetha |  |  |  | PUT/api/documents/applicantdocument/updateverificationstatus |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Documents | 6.manage documents -> folders |  |  | usp_ApplicantFolder_GetManage_S1 | Completed | Nivetha |  |  |  | GET /api/documents/applicant/{applicantId}/folders/manage |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | Completed
Case Worker Portal | Documents | 6.manage documents -> folders |  |  | usp_ApplicantFolder_GetTree_S1 | Completed | Nivetha |  |  |  | GET /api/documents/applicant/{applicantId}/folders/tree |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | Not Needed
Case Worker Portal | Documents | 6.manage documents -> folders |  |  | usp_ApplicantFolder_GetAll_S1 | Completed | Nivetha |  |  |  | GET /api/documents/applicant/{applicantId}/folders |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | Not Needed
Case Worker Portal | Documents | 7.manage documents -> versions |  |  | usp_ApplicantDocument_GetVersionHistory_S1 | Completed | Nivetha |  |  |  | GET /api/documents/applicant/{applicantId}/document/version-history |  | Completed |  |  |  | Service consumption, Data binding | Kamalanathan | 13/06/2025 |  | completed
Case Worker Portal | Documents | create subfolder |  |  | usp_ApplicantFolder_Add_S1 | Completed | Nivetha |  |  |  | POST /api/documents/applicant/folder/add |  | Completed |  |  |  | Service consumption | Kamalanathan | 13/06/2025 |  | completed |  | Service consumption - 10mins + 30mins Data Packing 20mins
Case Worker Portal | Forms | form>>create new form |  |  | usp_Form_Add_S1 | Completed | Balagi |  | 2025-06-27 |  | POST~/api/forms/add |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | Partially completed
Case Worker Portal | Forms | get customize forms |  |  | usp_Form_Getall_S1 | Completed | Balagi |  | 2025-06-27 |  | GET~ /api/forms/details |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | forms >>filters |  |  | usp_Form_RetrieveAll_S1 | Completed | Balagi |  | 2025-06-27 |  | GET~ /api/forms/allform/list |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | form update |  |  | usp_Form_Update_S1 | Completed | Balagi |  | 2025-06-27 |  | PUT /api/forms/update |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | update form customize settings |  |  | Form_UpdateInfoSettings_S1 | Completed | Balagi |  | 2025-06-27 |  | PUT /api/forms/update-info-settings |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | forms submitted |  |  | FormSubmission_Add_S1 | Completed | Balagi |  | 2025-06-27 |  | POST /api/forms/form-submission/add |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | retrieve forms >> dashboard |  |  | usp_FormSubmission_RetrieveAll_S1 | Completed | Balagi |  |  |  | GET /api/forms/form-submission/list |  | Completed |  |  | working | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | forms>>formtype>> + |  |  | usp_FormSubmission_RetrieveByID_S1 | Completed | Balagi |  | 2025-06-27 |  | GET /api/forms/form-submission/retrieve |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | forms>>formtype>>+>>submit |  |  | usp_FormSubmission_Update_S1 | Completed | Balagi |  |  |  | PUT /api/forms/form-submission/update |  | Completed |  |  |  | API verification, Data Binding | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | updating form status |  |  | usp_Form_UpdateStatus_S1 | Completed | Balagi |  | 2025-06-27 | not needed | PUT /api/forms/update-status |  | Completed |  |  |  |  | Sri karthik | 13/06/2025 |  | ON HOLD
Case Worker Portal | Forms | Delete form |  |  | Form$SpDeleteForm | completed | Balagi | 2025-06-09 | 2025-06-27 |  |  |  |  | 2025-06-10 |  |  |  | Sri karthik | 13/06/2025 |  |  |  |  | API is not available
Case Worker Portal | forms |  |  |  | usp_FormDashboard_ByFormType_S1 | completed | Balagi |  | 2025-06-27 | not needed | GET ~ api/forms/dashboard/forms/by-form-type
Case Worker Portal | Forms | History Form |  |  | usp_Form_GetHistory_S1 | completed | Balagi | 2025-06-09 | 2025-06-27 |  | GET ~ /api/forms/form/history |  |  | 2025-06-11 |  |  |  | Sri karthik | 13/06/2025 |  |  |  |  | API is not available
Case Worker Portal | Forms | Share Form |  |  |  | Pending |  | 2025-06-09 | [5 empty] | 2025-06-11 |  |  |  | Sri karthik | 13/06/2025 |  |  |  |  | API is not available
Case Worker Portal | forms | clone form |  |  | usp_Form_Clone_FromExisting_S1 | completed | Balagi |  | 2025-06-27
Case Worker Portal | Forms | Download form |  |  | usp_Form_Getall_S1 | Completed |  | 2025-06-09 | 2025-06-27 | not needed | GET ~ api/forms/form/download GET ~ api/forms/plan/form/download |  |  | 2025-06-11 |  |  |  | Sri karthik | 13/06/2025 |  |  |  |  | API is not available
csaeworker Portal | forms | client list |  |  | Common$SpGetUserList | Completed |  |  | 2025-06-27 | not needed | GET ~ /api/forms/client/form-selection
Case Worker Portal | Forms | Default |  |  | usp_Form_SetDefault_S1 | completed |  | 2025-06-09 | 2025-06-27 |  | POST ~ /api/forms/add/formNote |  |  | 2025-06-11 |  |  |  | Sri karthik | 13/06/2025 |  |  |  |  | API is not available
Case Worker Portal | Forms | Notes |  |  | usp_Delete_formNote_s1 | completed |  |  | 2025-07-05 |  | DELETE ~ /api/forms/form-note/delete
Case Worker Portal | Forms | Notes |  |  | usp_Get_formNotes_ByFormID_s1 | completed |  |  | 2025-07-05 |  | GET ~ /api/forms/form-notes
Case Worker Portal | Forms | Notes |  |  | usp_Update_formNote_s1 | completed |  |  | 2025-07-05 |  | PUT ~ /api/forms/form-note/update
Case Worker Portal | Forms | document |  |  | usp_CaseDocument_AddBatch_S1 | completed |  |  | 2025-07-05 |  | POST ~ /api/forms/case-documents/batch
Case Worker Portal | Forms | document |  |  | usp_CaseDocument_DeleteByID_S1 | completed |  |  | 2025-07-05 |  | DELETE ~ /api/forms/case-documents/delete
Case Worker Portal | Forms | document |  |  | usp_CaseDocument_GetByCase_S1 | completed |  |  | 2025-07-05 |  | GET ~ /api/forms/case-documents
Case Worker Portal | Jobs | add a new job details |  |  | dbo.Job$SpSaveJob | Completed |  |  | 2025-06-12 |  | POST ~ /api/job/save |  | Completed |  | 2025-06-23 |  | Service consumption | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | update job status( active or not) |  |  | Job$SpUpdateJobStatus | Completed | Pavan Kalyan |  |  |  | PUT ~ /api/job/update/job-status |  | Completed |  |  |  | Service consumption | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | career plannig >> find job >> get list of jobs |  |  | Job$SpSearchJobs | Completed | Pavan Kalyan |  | 2025-06-27 |  | GET~ /api/job/search |  | Completed |  | 2025-06-23 |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | DB Issue |  |  | Error(Incorrect syntax near 'CHAR'.)
Case Worker Portal | Jobs | career plannig >> find job >> save >> add user saved job |  |  | Job$SpSaveUserJob | Completed | Pavan Kalyan |  |  |  | POST~ /api/job/user/save |  | Completed |  | 2025-06-24 |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | Pending
Case Worker Portal | Jobs | career plannig >> find job >> view details >> get job details |  |  | Job$SpGetJobDetails | Completed | Pavan Kalyan |  | 2025-06-12 |  | GET~/api/job/details |  | Completed |  | 2025-06-23 |  | Service consumption | Ezhavendhan | 13/06/2025 |  | Completed |  |  | "SQLServerException: Procedure or function Job$SpGetJobDetails has too many arguments specified
Case Worker Portal | Jobs | career plannig >> find job >> view details >> apply job >> add user job apply |  |  | Job$SpApplyJob | Completed | Pavan Kalyan |  |  |  | POST~/api/job/apply |  | Completed |  | 2025-06-24 |  | Service consumption | Ezhavendhan | 13/06/2025 |  | Pending
Case Worker Portal | Jobs | career plannig >> find job >> view details >> similar jobs >> get a list of similar jobs |  |  | Job$SpGetSimilarJobs | Completed | Pavan Kalyan |  |  |  | GET~/api/job/similar-jobs |  | Completed |  | 2025-06-24 |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | Completed | 2025-06-06
Case Worker Portal | Jobs | career plannig >> find job >> view details >> similar jobs >> Get Organization Details |  |  | Organization$SpGetOrganizationDetails | Completed | Pavan Kalyan |  |  |  | GET ~ /api/job/organization/details |  | Completed |  |  |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | DB Issue |  |  | "SQLServerException: Implicit conversion from data type datetime to decimal is not allowed.
Case Worker Portal | Jobs | Add Invitation |  |  | Job$SpAddJobInvitation | Completed | Pavan Kalyan |  |  |  | POST~/api/job/add/invitation |  | Completed |  | 2025-06-25 |  | Service consumption | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | Update Invitation Status |  |  | Job$SpUpdateJobInvitationStatus | Completed | Pavan Kalyan |  |  |  | PUT~ /api/job/invitation/status |  | Completed |  | 2025-06-13 |  | Service consumption | Ezhavendhan | 13/06/2025 |  | Completed | 2025-06-10
Case Worker Portal | Jobs | career plannig >> Job Invitations >> get a list of job invitations |  |  | Job$SpGetJobInvitations | Completed | Pavan Kalyan |  | 2025-06-18 |  | GET~/api/job/invitations |  | Completed |  | 2025-06-23 |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | Completed | 2025-06-09
Case Worker Portal | Jobs | career plannig >> Job Invitations >> view details >> get the invitation job details |  |  | Job$SpGetJobInvitationDetails | Completed | Pavan Kalyan |  |  |  | GET/api/job/invitation-details |  | Completed |  | 2025-06-24 |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | Completed | 2025-06-10
Case Worker Portal | Jobs | career plannig >> sent applications>> get the job applications |  |  | Job$SpGetJobApplications | Completed | Pavan Kalyan |  | 2025-07-01 |  | GET/api/job/application/list |  | Completed |  | 2025-06-23 |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | Completed |  |  | "SQLServerException: The column name userdesc is not valid.\r\ncom.arkansas.beans.base.AppsException
Case Worker Portal | Jobs | career plannig >> sent applications >> view application >> get the details of a job application |  |  | Job$SpGetJobApplicationDetails | Completed | Pavan Kalyan |  |  |  | GET/api/job/application/details |  | Completed |  |  |  |  | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | career plannig >> sent applications>> received offers >>view offer >> get the lists of offer |  |  | Job$SpGetJobOfferDetails | Completed | Pavan Kalyan |  |  |  | GET/api/job/offer |  | Completed |  | 2025-06-24 |  | Service consumption, Data binding | Ezhavendhan | 13/06/2025 |  | Completed | 2025-06-09
Case Worker Portal | Jobs | add offer |  |  | Job$SpAddJobOffer.sql | Completed | Pavan Kalyan |  |  |  | POST/api/job/offer/add |  | Completed |  |  |  |  | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | update offer |  |  | Job$SpUpdateJobOffer.sql | Completed | Pavan Kalyan |  |  |  | PUT/api/job/offer/update |  | Completed |  |  |  |  | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | update status |  |  | Job$SpUpdateJobOfferStatus.sql | Completed | Pavan Kalyan |  |  |  | Get/api/job/offer/status |  | Completed |  | 2025-06-24 |  |  | Ezhavendhan | 13/06/2025 |  | Not required |  |  | No need for CaseWorker
Case Worker Portal | Jobs | Get all offers |  |  | Job$SpGetJobOffers.sql | Completed | Pavan Kalyan |  | 2025-06-18 |  | Get/api/job/joboffers |  | Completed |  | 2025-06-23 |  |  | Ezhavendhan | 13/06/2025 |  | Completed | 2025-06-09
Case Worker Portal | Jobs | update job application stauts |  |  | Job$SpUpdateJobApplicationStatus | Completed | Pavan Kalyan |  |  |  | Put/api/job/update-job-application-status |  | Completed |  | 2025-06-24 |  |  | Ezhavendhan | 13/06/2025 |  | DB Issue |  |  | "SQLServerException: Implicit conversion from data type datetime to decimal is not allowed.
Case Worker Portal | Jobs | get company profile details |  |  | Organization$SpGetOrganizationDetails | Completed | Pavan Kalyan |  |  |  | GetMapping/api/job/organization/details |  | Completed |  |  |  |  | Ezhavendhan | 13/06/2025 |  | DB Issue |  |  | description": "SQLServerException: Procedure or function 'Job$SpUpdateJobApplicationStatus'
Case Worker Portal | Jobs | Add contract |  |  | Job$SpAddJobContract.sql | Completed | Pavan Kalyan |  |  |  | POST ~/api/job/job-contract/add |  | Completed |  |  |  |  | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | get contract |  |  | Job$SpGetJobContractDetails.sql | Completed | Pavan Kalyan |  |  |  | GET~/api/job/contract/detail |  | Completed |  | 2025-06-24 |  |  | Ezhavendhan | 13/06/2025 |  | Completed |  |  | description": "SQLServerException: Procedure or function Job$SpGetJobContractDetails has too many arguments specified
Case Worker Portal | Jobs | Contract get all |  |  | Job$SpGetJobContracts.sql | Completed | Pavan Kalyan |  |  |  | GET~/api/job/contracts |  | Completed |  | 2025-06-24 |  |  | Ezhavendhan | 13/06/2025 |  | Completed | 2025-06-18
Case Worker Portal | Jobs | update contract |  |  | Job$SpUpdateJobContract.sql | Completed | Pavan Kalyan |  |  |  | PUT~/api/job/contract/update |  | Completed |  |  |  |  | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | Contract status |  |  | Job$SpUpdateJobContractStatus.sql | Completed | Pavan Kalyan |  |  |  | PUT~/api/job/job-contract/update-status |  | Completed |  | 2025-06-24 |  |  | Ezhavendhan | 13/06/2025 |  | Not required |  |  | Screen not Available
Case Worker Portal | Jobs | Contract recent activities |  |  | Job$SpGetContractActivities | Completed | Pavan Kalyan |  | 2025-06-25 |  | GET~/api/job/contract/activity/list |  | Completed |  | 2025-06-26
Case Worker Portal | jobs | get employer list |  |  | usp_Employer_GetList_S1 | Completed | Pavan Kalyan |  | 2025-06-27 |  | GET~/api/job/employer/list |  | Completed
| jobs | get employer details |  |  | Organization$SpGetOrganizationDetails | Completed | Pavan Kalyan |  | 2025-06-27 |  | GET~/api/arkansas/organization/details
Case Worker Portal | Resume | resume add full |  |  | Resume$Sp_Add_ResumeFull | Completed | Balagi |  |  |  | POST~ /api/resume/add-full |  | Completed |  | 2025-06-20 |  | Service consumption, Data binding | Gokul | 13/06/2025 |  | Not required |  | There is no need of this API, when we add Each section separately | Balagi
Case Worker Portal | Resume | resume update full |  |  | Resume$Sp_Update_ResumeFull | Completed | Balagi |  |  |  | PUT /api/resume/update-full |  | Completed |  |  |  | Service consumption, Data binding | Gokul | 13/06/2025 |  | Not required |  | There is no need of this API, when we add Each section separately | Balagi
Case Worker Portal | Resume | resume get full information |  |  | Resume$Sp_Get_ResumeFullByID | Completed | Balagi |  |  |  | Get~/api/resume/full-by-id |  | Completed |  |  |  | Service consumption, Data binding | Gokul | 13/06/2025 |  | DB Issue |  | Two Fields Requested To Add ( Resume Completion Percentage, is Primary Resume ) | Balagi
Case Worker Portal | Resume | resume>>add |  |  | dbo.Resume$Sp_Add_Resume | Completed | Balagi |  |  |  | POST~/api/resume/add/resume |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | DB Issue |  | notable project,profile update and two check box field missing | Balagi
Case Worker Portal | Resume | update resume |  |  | Resume$Sp_Update_Resume | Completed | Balagi |  |  |  | PUT~/api/resume/update/resume |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | DB Issue |  | notable project,profile update and two check box field missing | Balagi
Case Worker Portal | Resume | resume >>get |  |  | dbo.Resume$Sp_Get_Resume | Completed | Balagi |  |  |  | GET~/api/resume/get/by-resume-id |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | DB Issue |  | notable project,profile update and two check box field missing | Balagi
Case Worker Portal | Resume | resume>>user |  |  | Resume$Sp_GetAll_ResumesByUser | Completed | Balagi |  |  |  | GET~/api/resume/get/all/by-user |  | Completed |  | 2025-06-25 |  |  | Gokul | 13/06/2025 |  | DB Issue |  | Partially completed - Two Fields Requested To Add ( Resume Completion Percentage, is Primary Resume ) | Balagi
Case Worker Portal | Resume | resume>>workexperience |  |  | dbo.Resume$Sp_Add_ResumeWorkExperience | Completed | Balagi |  |  |  | POST~/api/resume/add/work-experience |  | Completed |  | 2025-06-20 |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume | resume >>workexperience |  |  | Resume$Sp_Get_ResumeWorkExperience | Completed | Balagi |  |  |  | GET~/api/resume/get/work-experience/by-id |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume | resume >>workexperienceby resume |  |  | Resume$Sp_GetAll_ResumeWorkExperienceByResume | Completed | Balagi |  |  |  | GET~/api/resume/get/work-experience/by-resume |  | Completed |  | 2025-06-20 |  |  | Gokul | 13/06/2025 |  | Completed |  | Completed | Balagi
Case Worker Portal | Resume | resume>>updateresumeeducation |  |  | .Resume$Sp_Update_ResumeEducation | Completed | Balagi |  |  |  | PUT~/api/resume/update/resume/education |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | Pending |  | UI Change | Balagi
Case Worker Portal | Resume | resume>>getresumeeducation |  |  | dbo.Resume$Sp_Get_ResumeEducation | Completed | Balagi |  |  |  | GET~/api/resume/get/education/by-id |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | NOT NEEDED |  | There is no need of this API, when we GET Each EDUCATION section | Balagi
Case Worker Portal | Resume | resume>>getalleducationbyresume |  |  | dbo.Resume$Sp_GetAll_ResumeEducationByResume | Completed | Balagi |  |  |  | GET /api/resume/education/list |  | Completed |  | 2025-06-20 |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume |  |  |  | dbo.Resume$Sp_Add_ResumeCertification | Completed | Balagi |  |  |  | POST~ /api/resume/resume/certification/add |  | Completed |  | 2025-06-20 |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume | resume certification-get |  |  | Resume$Sp_Get_ResumeCertification | Completed | usp_Form_SetDefault_S1 |  |  |  | GET /api/resume/certification |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | NOT NEEDED |  | There is no need of this API, when we GET Each Certification section | Balagi
Case Worker Portal | Resume |  |  |  | dbo.Resume$Sp_GetAll_ResumeCertificationByResume | Completed | usp_Form_SetDefault_S1 |  |  |  | GET /api/resume/certification/list |  | Completed |  | 2025-06-24 |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume |  |  |  | dbo.Resume$Sp_Update_ResumeSkill | Completed | usp_Form_SetDefault_S1 |  |  |  | PUT /api/resume/skill/update |  | Completed |  | 2025-06-20 |  |  | Gokul | 13/06/2025 |  | NOT NEEDED |  | waiting for new sp | Balagi
Case Worker Portal | Resume | resume skill>>get |  |  | Resume$Sp_Get_ResumeSkill | Completed | usp_Form_SetDefault_S1 |  |  |  | GET~/api/resume/fetch/skill |  | Completed |  | 2025-06-24 |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume | resume skill by resume |  |  | dbo.Resume$Sp_GetAll_ResumeSkillByResume | Completed | usp_Form_SetDefault_S1 |  |  |  | GET~/api/resume/skill/list |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume | resume updatelanguage |  |  | dbo.Resume$Sp_Update_ResumeLanguage | Completed | Balagi |  |  |  | PUT~/api/resume/language/update |  | Completed |  | 2025-06-24 |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume | update resume language |  |  | dbo.Resume$Sp_Update_ResumeLanguage | Completed | Balagi |  |  |  | PUT~/api/resume/language/update |  | Completed |  | 2025-06-24 |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume | get resume language |  |  | dbo.Resume$Sp_Get_ResumeLanguage | Completed | Balagi |  |  |  | GET~/api/resume/get/language |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume |  |  |  | dbo.Resume$Sp_GetAll_ResumeLanguageByResume | Completed | Balagi |  |  |  | GET~/api/resume/language/list |  | Completed |  | 2025-06-24 |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume | Add_ResumeAward |  |  | dbo.Resume$Sp_Add_ResumeAward | Completed | Balagi |  |  |  | POST~/api/resume/award/add |  | Completed |  | 2025-06-20 |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume | update resume award |  |  | dbo.Resume$Sp_Update_ResumeAward | Completed | Balagi |  |  |  | PUT~/api/resume/award/update |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume | get resume award |  |  | dbo.Resume$Sp_Get_ResumeAward | Completed | Balagi |  |  |  | GET~/api/resume/gte/award |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume |  |  |  | dbo.Resume$Sp_GetAll_ResumeAwardByResume | Completed | Balagi |  |  |  | GET~/api/resume/award/list |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | DB Issue |  | SQL Exception | Balagi
Case Worker Portal | Resume | Add_ResumeReference |  |  | dbo.Resume$Sp_Add_ResumeReference | Completed | Balagi |  |  |  | POST~/api/resume/reference/add |  | Completed |  | 2025-06-20 |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume | Update_ResumeReference |  |  | dbo.Resume$Sp_Update_ResumeReference | Completed | Balagi |  |  |  | PUT~/api/resume/reference/update |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume | Get_ResumeReference |  |  | dbo.Resume$Sp_Get_ResumeReference | Completed | Balagi |  |  |  | GET~/api/resume/get/reference |  | Completed |  |  |  |  | Gokul | 13/06/2025 |  | Completed |  | Partially completed - Resume id needed | Balagi
Case Worker Portal | Resume | GetAll_ResumeReferenceByResume |  |  | dbo.Resume$Sp_GetAll_ResumeReferenceByResume | Completed | Balagi |  |  |  | GET~/api/resume/get/references |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | UI Change |  |  | Balagi
Case Worker Portal | Resume | Add_ResumeFreelanceProfile |  |  | dbo.Resume$Sp_Add_ResumeFreelanceProfile | Completed | Balagi |  |  |  | POST~api/resume/add/freelance |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | DB Issue |  |  | Balagi
Case Worker Portal | Resume | Update_ResumeFreelanceProfile |  |  | dbo.Resume$Sp_Update_ResumeFreelanceProfile | Completed | Balagi |  |  |  | PUT~api/resume/update/freelance |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | DB Issue |  |  | Balagi
Case Worker Portal | Resume | Get_ResumeFreelanceProfile |  |  | dbo.Resume$Sp_Get_ResumeFreelanceProfile | Completed | Balagi |  |  |  | GET~api/resume/get/freelance |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | Completed |  |  | Balagi
Case Worker Portal | Resume | GetAll_ResumeFreelanceProfileByResume |  |  | dbo.Resume$Sp_GetAll_ResumeFreelanceProfileByResume | Completed | Balagi |  |  |  | GET~api/resume/get/freelance/list |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | Pending |  |  | Balagi
Case Worker Portal | Resume | Add_ResumeJobPreference |  |  | dbo.Resume$Sp_Add_ResumeJobPreference | Completed | Balagi |  |  |  | POST~api/resume/add/job-preference |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | Pending |  |  | Balagi
Case Worker Portal | Resume | Update_ResumeJobPreference |  |  | dbo.Resume$Sp_Update_ResumeJobPreference | Completed | Balagi |  |  |  | PUT~api/resume/update/job-preference |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | Pending |  |  | Balagi
Case Worker Portal | Resume | Get_ResumeJobPreference |  |  | dbo.Resume$Sp_Get_ResumeJobPreference | Completed | Balagi |  |  |  | GET~api/resume/get/job-preference |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | DB Issue |  |  | Balagi
Case Worker Portal | Resume | resume get job preference |  |  | Resume$Sp_GetAll_ResumeJobPreferenceByResume | Completed | Balagi |  |  |  | GET~api/resume/get/job-preference/list |  | Completed | 2025-06-11 | 2025-06-13 |  |  | Gokul | 13/06/2025 |  | DB Issue |  |  | Balagi
Case Worker Portal | Reports | Reports->>My Performance |  |  | WIOA_SP_GET_REPORTS_MYPERFORMANCE | Completed |  |  |  |  | GET /api/arkansas/program/get-performance |  | Completed |  |  |  | API verification done, Data Binding pending | Vinoth | 13/06/2025 |  | DB Issue |  | working flag missing (api bind completed) | Jayavarthini
Case Worker Portal | Reports | Reports->>Performance Trends |  |  | WIOA_SP_GET_REPORTS_MONTHLYTRENDS | Completed |  |  |  |  | POST~ /api/arkansas/wioa/monthly-trends |  | Completed |  |  |  | API verification done, Data Binding pending | Vinoth | 13/06/2025 |  | DB Issue |  | SQLServerException | Jayavarthini
Case Worker Portal | Reports | Reports->>CaseLoad Summary->>Chart view |  |  | WIOA_SP_GET_REPORTS_CASELOADSUMMARY_CHART | Completed |  |  |  |  | POST~ /api/arkansas/wioa/caseload-summary-chart |  | Completed |  |  |  | API verification done, Data Binding pending | Vinoth | 13/06/2025 |  | DB Issue |  | No Data | Jayavarthini
Case Worker Portal | Reports | Reports->>CaseLoad Summary->>Table View |  |  | WIOA_SP_GET_REPORTS_CASELOADSUMMARY_TABLE | Completed |  |  |  |  | POST~ /api/arkansas/wioa/caseload-summary-table |  | Completed |  |  |  | API verification done, Data Binding pending | Vinoth | 13/06/2025 |  | DB Issue |  | Caseload Summary data not available (api bind completed) | Jayavarthini
Case Worker Portal | Reports | Reports->>Program Outcomes |  |  | WIOA_SP_GET_PROGRAM_OUTCOMES | Completed |  |  |  |  | GET /api/arkansas/program/get-outcomes |  | Completed |  |  |  | API verification done, Data Binding pending | Vinoth | 13/06/2025 |  | DB Issue |  | sp changed need new api | Jayavarthini
Case Worker Portal | Reports | Reports->>Program Outcomes->>Comparison by program |  |  | WIOA_SP_GET_PROGRAM_COMPARISON | Completed |  |  |  |  | GET /api/arkansas/program/get-comparison |  | Completed |  |  |  | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  | Completed | 2025-10-06
Case Worker Portal | Reports | Reports->>Supportive service utilization-->>service summary |  |  | WIOA_SP_GET_REPORTS_SERVICE_CATEGORY_SUMMARY | Need to map |  | 2025-05-22 |  |  | GET ~ /api/arkansas/wioa/report/service-category-summary | [5 empty] | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  | DB Issue |  | need changes form db | Jayavarthini
Case Worker Portal | Reports | Reports->>Supportive service utilization-->>service details |  |  | WIOA_SP_GET_REPORTS_SERVICE_DETAILS 1 | Need to map |  | 2025-05-22 |  |  | GET ~ /api/arkansas/wioa/report/service-details | [5 empty] | API verification pending, Data Binding pending | Vinoth | 13/06/2025 |  | DB Issue |  | SQLServerException need changes form db | Jayavarthini
Case Worker Portal | Reports | Reports->>Custom Reports->>create custom reports. |  |  |  | Pending |  | 2025-06-10 | [5 empty] | 2025-06-11 |  |  |  | Vinoth | 13/06/2025 |  |  |  | API not Available
Case Worker Portal | Reports | Reports->>Custom Reports->> Get custom reports |  |  |  | Pending |  | 2025-06-10 | [5 empty] | 2025-06-11 |  |  |  | Vinoth | 13/06/2025 |  |  |  | API not Available
Case Worker Portal | System Admin | office management >> add |  |  | Office$Sp_Insert_Office_S1 | completed |  | 2025-06-25 |  |  | POST - /api/arkansas/office/insert |  |  | 2025-06-12 |  |  |  | Sri Karthik | 13/06/2025
Case Worker Portal | Profile | office management >> add > organization dropdown |  |  | Organization_Sp_Retrieve_All_S1 | completed |  | 2025-06-25 |  |  | GET -/api/arkansas/organization/list |  |  | 2025-06-12 |  |  |  | Kamalanathan | 13/06/2025
Case Worker Portal | Settings |  |  |  |  | Pending |  | 2025-06-10 | [5 empty] | 2025-06-12 |  |  |  | Kamalanathan | 13/06/2025
Case Worker Portal | Notification |  |  |  |  | Pending | Nithyasri | 2025-06-10 | [5 empty] | 2025-06-12 |  |  |  | Kamalanathan | 13/06/2025
Case Worker Portal | Announcement & Notifications | add announcement |  |  | Announcement_Add | completed | Nivetha | 2025-06-25 |  |  | POST~/api/arkansas/announcement |  | Completed | 2025-06-26 | Working
Case Worker Portal | Announcement & Notifications | Update announcement |  |  | Announcement_Update | completed | Nivetha | 2025-06-25 |  |  | PUT - /api/arkansas/announcement/update |  | Completed | 2025-06-26 | Working
Case Worker Portal | Announcement & Notifications | delete announcement |  |  | Announcement_Delete | completed | Nivetha | 2025-06-25 | 2025-06-25 | new procedure | Office$Sp_Get_OfficeList |  | Completed | 2025-06-26 | Working
Case Worker Portal | Announcement & Notifications | get all announcement |  |  | Announcement_RetrieveAll | completed | Nivetha | 2025-06-25 |  |  | GET~/api/arkansas/announcement/list |  | Completed | 2025-06-26 | Working
|  | common sp to get dropdown values |  |  | Common$SpGetReferenceData | completed |  |  | 2025-06-25 |  | GET ~ /api/arkansas/reference-data |  | Completed |  | 2025-06-25
|  | get user list |  |  | Common$SpGetUserList | completed |  |  | 2025-07-02 |  | POST ~ /api/arkansas/get/user-list
|  | db audit sp |  |  | AuditLog_Insert_S1 | completed |  |  | 2025-06-26
|  | db audit sp |  |  | AuditAccess_Insert_S1 | completed |  |  | 2025-06-26
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorDevice_Add_S1 | completed | Nithyasri |  | 2025-06-27 |  | POST~ /api/login/add/two-factor-device
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorDevice_UpdateStatus_S1 | completed | Nithyasri |  | 2025-06-27 |  | PUT~/api/login/update/two-factor-device-status
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorDevice_Get_S1 | completed | Nithyasri |  | 2025-06-27 |  | GET~/api/login/get/two-factor-device
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorDevice_Update_S1 | completed | Nithyasri |  | 2025-06-27 |  | PUT~/api/login/update/two-factor-device
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorRecoveryCode_Add_S1 | completed | Nithyasri |  | 2025-06-27 |  | POST~/api/login/add/two-factor-recovery-code
Case Worker Portal | Two factor aunthentication |  |  |  | update_password | completed | Nithyasri |  | 2025-06-27 |  | POST~/api/login/add/two-factor-verification-log
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorRecoveryCode_Get_S1 | completed | Nithyasri |  | 2025-06-27 |  | GET~/api/login/get/two-factor-recovery-code
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorRecoveryCode_Update_S1 | completed | Nithyasri |  | 2025-06-27 |  | PUT~/api/login/update/two-factor-recovery-code
Case Worker Portal | Two factor aunthentication |  |  |  | Users$Sp_Regenerate_RecoveryCodes | completed | Nithyasri |  |  |  | PUT ~ /api/loginuser/recovery-codes/regenerate
Case Worker Portal | Two factor aunthentication |  |  |  | usp_TwoFactorDevice_GetAll_S1 | completed | Nithyasri |  | 2025-06-27 |  | GET~/api/login/get/two-factor-devices
Case Worker Portal | Profile |  |  |  | Users$Sp_Update_PersonalInfo | completed |  |  | 2025-06-27 |  | PUT ~ /api/arkansas/user/update/personal-info
Case Worker Portal | Profile |  |  |  | Users$Sp_Update_Password | completed |  |  | 2025-06-27 |  | PUT ~ /api/arkansas/user/update/password
Case Worker Portal | Profile |  |  |  | Users$Sp_Update_TwoFactorDevice | completed |  |  | 2025-06-27 |  | PUT ~ /api/arkansas/user/update/twofactor-device
Case Worker Portal | Profile |  |  |  | TwoFactorDevice$Sp_Get_RecoveryCodes | completed |  |  | 2025-06-27 |  | GET ~ /api/login/twofactor/recovery-codes
Case Worker Portal | Profile |  |  |  | Users$Sp_Update_ProfilePicture | completed |  |  | 2025-06-27 |  | PUT ~ /api/login/user/update/profile-picture
Case Worker Portal | Profile |  |  |  | UserSettings$Sp_AddOrUpdate_UserSettings | completed |  |  | 2025-06-27 |  | POST ~ /api/login/user/settings
Case Worker Portal | Profile |  |  |  | UserSettings$Sp_Get_UserSettings | completed |  |  | 2025-06-27 |  | GET ~ /api/login/user/settings
Case Worker Portal | system admin |  |  |  | Office$Sp_Add_Office | completed | Nivetha |  | 2025-06-27 |  | POST ~ /api/login/office/add
Case Worker Portal | system admin |  |  |  | Office$Sp_Update_Office | completed | Nivetha |  | 2025-06-27 |  | PUT ~ /api/login/office/update
Case Worker Portal | system admin |  |  |  | Office$Sp_Delete_Office | completed | Nivetha |  | 2025-06-27 |  | DELETE ~ /api/login/office/delete
Case Worker Portal | system admin |  |  |  | Office$Sp_Get_Office | completed | Nivetha |  | 2025-06-27 |  | /api/login/office/details
Case Worker Portal | system admin |  |  |  | Users$Sp_Get_UserList | completed | Nivetha |  | 2025-06-27 |  | GET ~ /api/login/user/list
Case Worker Portal | system admin |  |  |  | Office$Sp_Get_OfficeList | completed | Nivetha |  | 2025-06-27 |  | GET ~ /api/arkansas/office/list
Case Worker Portal | system admin |  |  |  | User$Sp_Create_User | completed | Nivetha |  | 2025-06-27 |  | POST ~ /api/login/create/user
Case Worker Portal | system admin |  |  |  | User$Sp_Update_UserProfile | completed | Nivetha |  | 2025-06-27 |  | PUT ~ /api/login/profile
Case Worker Portal | system admin |  |  |  | UserBulkOperations$Sp_UpdateAccountStatus | completed | Nivetha |  | 2025-06-27 |  | PUT ~ /api/login/bulk/account-status
Case Worker Portal | system admin |  |  |  | UserBulkOperations$Sp_UpdateRole | completed | Nivetha |  | 2025-06-27 |  | PUT ~ /api/login/bulk/role
Case Worker Portal | system admin |  |  |  | EmailNotification$Sp_AddWithRecipients_S1 | completed | Nivetha |  | 2025-06-27 |  | POST ~ /api/login/with-recipients
Case Worker Portal | system admin |  |  |  | EmailNotification$Sp_Get_Recipients_S1 | completed | Nivetha |  | 2025-06-27 |  | GET ~ /api/login/fetch/recipients
Case Worker Portal | system admin |  |  |  | Users$Sp_Get_UserDetails | completed | Nivetha |  | 2025-06-27 |  | GET ~ /api/login/user/details
Case Worker Portal | system admin |  |  |  | Users$Sp_Get_AuditLogTimeline_S1 | completed | Nivetha |  | 2025-06-27 |  | GET ~ /api/login/audit-log/timeline
Case Worker Portal | system admin |  |  |  | Users$Sp_Delete_User | completed | Nivetha |  | 2025-06-27 |  | DELETE ~ /api/login/delete/user
Case Worker Portal | system admin |  |  |  | Office$Sp_Get_UserCount | completed | Nivetha |  | 2025-06-27 |  | GET ~ /api/login/user-count
Case Worker Portal | system admin |  |  |  | Role$Sp_Get_UsersByRole | completed | Nivetha |  | 2025-06-27 |  | GET~ /api/login/users/by-role
Case Worker Portal | system admin |  |  |  | Role$Sp_Get_RoleList | completed | Nivetha |  | 2025-06-27 |  | GET~ /api/login/role/list
Case Worker Portal | system admin |  |  |  | Role$Sp_Get_RoleDetails | completed | Nivetha |  | 2025-06-27 |  | GET~ /api/login/role/details
Case Worker Portal | system admin |  |  |  | UserBulkOperations$Sp_UpdateUserOffice | completed | Nivetha |  | 2025-06-27 |  | PUT~ /api/login/bulk/office-update
Case Worker Portal | system admin |  |  |  | dbo.User$Sp_Update_UserRole | completed | Nivetha |  | 2025-06-27 |  | PUT ~ /api/login/user/update-role
Case Worker Portal | system admin |  |  |  | dbo.Users$Sp_Update_LockStatus | completed | Nivetha |  | 2025-06-27 |  | PUT ~ /api/login/user/update-lock-status
Case Worker Portal | system admin |  |  |  | Users$Sp_Send_InvitationEmail | completed | Nivetha |  | 2025-06-27 |  | POST ~ /api/login/user/send-invitation-email
Case Worker Portal | Custom Report | Custom Report>>GET All |  |  | dbo.CustomReport$SPGetCusReports | completed |  |  | 2025-06-27 |  | GET~ /api/customreport/custom-report/list
Case Worker Portal | Custom Report | Custom Report >>Create new Custom Report |  |  | dbo.CustomReport$CreateNewCustomReport | completed |  |  | 2025-06-27 |  | POST~ /api/customreport/create
Case Worker Portal | Custom Report | Custom Report >> CheckNameAvaliability |  |  | dbo.CustomReport$CheckReportNameAvailability | completed |  |  | 2025-06-27 |  | GET~ /api/customreport/check-name-availability
Case Worker Portal | Custom Report | Custom Report >>View |  |  | dbo.CustomReport$GetReportForView | completed |  |  | 2025-06-27 |  | GET~ /api/customreport/custom-report/view
Case Worker Portal | Custom Report | Custom Report >>View |  |  | dbo.CustomReport$Sp_ExportReport | completed |  |  | 2025-06-27 | Not used | POST~ /api/customreport/custom-report/export
Case Worker Portal | Custom Report | Custom Report >>Record View Report |  |  | dbo.CustomReport$RecordReportView | completed |  |  | 2025-06-27 |  | POST~ /api/customreport/custom-report/record-view
Case Worker Portal | Custom Report | Custom Report >>Update |  |  | dbo.CustomReport$UpdateCustomReport | completed |  |  | 2025-06-27 |  | PUT~ /api/customreport/custom-report/update
Case Worker Portal | Custom Report | Custom Report >>Delete |  |  | dbo.CustomReport$DeleteReport | completed |  |  | 2025-06-27 |  | DELETE~ /api/customreport/delete
Users$Sp_Get_UserInfo
Common$SpGetWorkspaceList
| Reports | Caseload summary>>Both Chart and Table view |  |  | Reports$Sp_Get_CaseSummary | [5 empty] | /api/customreport/case/summary
| Reports | prorgram outcome >>Grid |  |  | WIOA_SP_GET_REPORTS_PROGRAM_OUTCOMES | [5 empty] | /api/arkansas/reports/program-outcomes
| Reports | Program outcome>>Comparison |  |  | WIOA_SP_GET_PROGRAM_COMPARISON | [5 empty] | /api/arkansas/program/get-comparison
| Reports | Supportive service details |  |  | WIOA_SP_GET_REPORTS_SERVICE_DETAILS | [5 empty] | api/customreport/supportive-service/details

## Client Portal
Portal | Module | Screen name | Priority | DB Team | [5 empty] | API Team | [5 empty] | UI Team
|  |  |  | Procedure | DB Status | F | ETA | Completed On | DB Comments | API EndPoint | API Resource | API Status | ETA | Completed On | API Comment | Task | Assigned To | ETA for Issue fixing | ETA for Api binding | Status | UI Completed On | Api completed on | Comments | Due date
Client Portal | Dashboard | Card Layout |  | usp_DashboardQuickNav_GetList_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | New Procedure | GET~/api/dashboard/dashboard/quick-nav/list |  | Completed | 2025-06-12 | 2025-06-16 | Working | API verification, Data Binding | Vinoth |  | 1hr 45mins
Client Portal | Dashboard | Submitted Proposal |  | Job$SpGetJobApplications | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | GET~/api/job/application/list |  | Completed | 2025-06-12 | 2025-06-16 | Working | API verification, Data Binding | Vinoth |  | 1hr 45mins
Client Portal | Dashboard | View Job Details |  | Job$SpGetJobDetails | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | GET~/api/job/details |  | Completed | 2025-06-12 | 2025-06-16 | Working | API verification, Data Binding | Vinoth |  | 1hr 45mins |  |  |  |  | Assigned To | Total ETA(hrs) | Total ETA(days)
Client Portal | Dashboard | View All Proposal Details - dulpicate |  | Job$SpGetJobApplications | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | GET~/api/job/application/list |  | Completed | 2025-06-12 | 2025-06-16 | Working | API verification, Data Binding | Vinoth |  | 1hr 45mins | [6 empty] | With buffer
Client Portal | Dashboard | Active Contract |  | Job$SpGetJobContracts | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | GET~/api/job/contracts |  | Completed | 2025-06-12 | 2025-06-16 | Working | API verification, Data Binding | Vinoth |  | 1hr 45mins
Client Portal | Dashboard | View Contract |  | Job$SpGetJobContractDetails | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | GET~/api/job/contract/detail |  | Completed | 2025-06-12 | 2025-06-16 | Working
Client Portal | Dashboard | View All messages |  | usp_User_ConversationSummary_GetList_S2 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | GET~/api/application/conversation/summary |  | Completed | 2025-06-12 | 2025-06-16 | Working
Client Portal | My Application | Personal information |  | usp_Applicant_GetDetails_S1 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 | Modified | GET~/api/application/applicant/details |  | Completed | 2025-06-12 | 2025-06-16 | Working | API verification, Data Binding | Sri karthik |  | 1hr 45mins |  |  |  |  | Ezhavendhan | 71.66 hrs | 10days
| My Application | Personal information > Personal details and contact information |  | usp_Applicant_GetDetails_S1 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 | Modified | GET~/api/application/applicant/details |  | Completed |  | 2025-06-16 | Working
| My Application | reapply |  | usp_Applicant_UpdateBase_S1 usp_Applicant_UpdateContactInformation usp_Applicant_UpdateStatus_S1 | Completed | Balagi G
| My Application | Personal information>Personal details |  | usp_Applicant_UpdateBase_S1 | Completed | Jayavarthini R |  | 2025-06-12 | Modified | PUT~/api/application/applicant/updatebase |  | Completed |  | 2025-06-16 | Working
Client Portal | My Application | Personal Information>Contact information ->Update (NEW) |  | usp_Applicant_UpdateContactInformation | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 | New Procedure | PUT~/api/application/applicant/contact-information/update |  | Completed | 2025-06-12 | 2025-06-16 | Working | API verification, Data Binding | Sri karthik |  | 1hr 45mins |  |  |  |  | Gokul | 78.00 hrs | 11days
Client Portal | My Application | Personal Information->Application Timeline |  | usp_ApplicantAuditLog_List_S1 | Completed | balagi G | 2025-06-11 | 2025-06-12 |  | GET~/api/application/applicant/details |  | Completed | 2025-06-12 | 2025-06-16 | Working
Client Portal | My Application | Screening Response |  | usp_Applicant_GetDetails_S1 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 |  | GET~/api/application/applicant/details |  | Completed | 2025-06-12 | 2025-06-16 | Working
Client Portal | My Application | Edit Screening Response |  | usp_Applicant_UpdateBase_S1 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 |  | PUT~/api/application/applicant/updatebase |  | Completed | 2025-06-13 | 2025-06-16 | Working
Client Portal | My Application | Eligibility Results |  | usp_ApplicantEligibleProgram_GetAll_S8 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 |  | GET~/api/application/applicant/eligibleprograms |  | Completed | 2025-06-13 | 2025-06-16 | Working
Client Portal | Upload Document | Get Uploaded Documents |  | usp_ApplicantDocument_GetAll_S1 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 |  | GET~/api/documents/list |  | Completed | 2025-06-13 | 2025-06-18 | Working
Client Portal | Upload Document | Delete Documents |  | usp_ApplicantDocument_Delete_S1 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 |  | DELETE~/api/documents/applicant/document/delete |  | Completed | 2025-06-13 | 2025-06-18 | Working
Client Portal | Upload Document | Upload documents |  | usp_ApplicantDocument_AddBatch_S1 | Completed | Jayavarthini R | 2025-06-11 | 2025-06-12 |  | POST~/api/documents/applicant-document/add-batch |  | Completed | 2025-06-13 | 2025-06-18 | Working | API verification, Data Binding | Kamalanathan |  | 1hr 45mins |  |  |  |  | Manoj | 51.25 hrs | 8 days
Client Portal | profile | Reviews |  | dbo.Review$GetAllByUserAndOrganization | Pending | Balagi G | 2025-06-11 |  | Doubts |  |  |  | 2025-06-13 |  | DB Pending
Client Portal | profile | update password |  | Users$Sp_Update_Password | Pending | Balagi G | 2025-06-11 |  |  | GET~/api/arkansas/calendar/appointments |  | Completed | 2025-06-13 | 2025-06-25 | Working
Client Portal | Messages | Member List |  | usp_User_ConversationSummary_GetList_S2 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | New Procedure | GET~/api/application/conversation/summary |  | Completed | 2025-06-13 | 2025-06-18 | Working
Client Portal | Messages | Message History |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | GET~/api/application/user/message-history |  | Completed | 2025-06-13 | 2025-06-18 | Working
Client Portal | Messages | Send Message |  | usp_Conversation_CreateAndInsertMessage_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | Modified | POST ~ /api/arkansas/conversation/create-insert-message |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Messages | Mark As Read Messages |  | usp_Message_ReadStatus_Update_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | New Procedure | PUT~/api/application/message/read-status/update |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Updates | Get All Updates |  | usp_Get_Notifications_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | New Procedure | GET~/api/updates/notifications |  | Completed | 2025-06-13 | 2025-06-18 | Working
Client Portal | Updates | Mark as Read Updates |  | usp_Update_Notification_ReadStatus_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | New Procedure | PUT~/api/updates/notifications/update-read-status |  | Completed | 2025-06-13 | 2025-06-18 | Working
Client Portal | Updates | Updates Actions (19 Service) |  | usp_Insert_NotificationRecipientActionLog_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | New Procedure | POST~/api/updates/notifications/action-log |  | Completed | 2025-06-13 | 2025-06-18 | Working
Client Portal | Updates | Updates Delete |  | usp_Delete_Notification_S1 | Completed | Nithyasri .S | 2025-06-11 | 2025-06-12 | New Procedure | DELETE~/api/updates/notifications/delete |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Get My Resume |  | Resume$Sp_GetAll_ResumesByUser | Completed | Balagi G | 2025-06-12 |  | Doubts --> Percentage logic | GET~/api/resume/get/all/by-user |  | Completed |  | 2025-06-25 | Working
Client Portal | Career Planing--> Resume | Get Sample Resume |  |  | pending | Balagi G |  |  | Doubts --> sample resume
Client Portal | Career Planing--> Resume | Edit Resume |  |  | pending | Balagi G
Client Portal | Career Planing--> Resume | View Resume |  | Resume$Sp_Get_ResumeFullbyid | Completed | Balagi G | 2025-06-12 | 2025-06-12 | Modified | GET~/api/resume/full-by-id |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Clone Resume |  | Resume$Sp_Clone_ResumeByID | Completed | Balagi G | 2025-06-12 | 2025-06-18 | new Procedure | POST~/api/resume/clone |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Delete Resume |  | Resume$Sp_Delete_Resume | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | DELETE~/api/resume/delete |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Save AI Resume |  | Resume$Sp_Add_ResumeFull | Completed | Balagi G | 2025-06-12 | 2025-06-20 |  | POST~/api/resume/add-full |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Update Primary Resume |  | dbo.usp_Resume_SetPrimary_S1 | Completed | Balagi G | 2025-06-12 | 2025-06-18 | New Procedure | PUT~/api/resume/set-primary |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | download resume |  | Resume$Sp_DownloadResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/resume/download |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | resume Name-> add |  | Resume$Sp_Add_Resumenameonly | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | POST ~ /api/forms/resume/add-nameonly |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | resume Name-->Get |  | Resume$Sp_Get_Resumename | Completed | Balagi G | 2025-06-12 | 2025-06-19 | New Procedure | GET~api/resume/get/resume-name |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | resume Name -->Update |  | Resume$Sp_Update_Resumename | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | PUT~api/resume/update/resumename |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Personal Information-> add |  | Resume$Sp_Update_Resumepersonalinfo | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | PUT~api/resume/update/resume/personalinfo |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Personal Information-->Get |  | Resume$Sp_Get_Resumepersonalinfo | Completed | Balagi G | 2025-06-12 | 2025-06-19 | New Procedure | GET~api/resume/get/resume-personalinfo |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Personal Information -->Update |  | Resume$Sp_Update_Resumepersonalinfo | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | PUT~api/resume/update/resume/personalinfo |  | Completed | 2025-06-30 | 2025-06-18 | Working
Client Portal | Career Planing--> Resume | Work Experience -> add |  | Resume$Sp_Add_ResumeWorkExperience | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/resume/add/work-experience |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Work Experience-->Get |  | Resume$Sp_Update_ResumeWorkExperience | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | PUT~/api/resume/update/work-experience |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Work Experience -->Update |  | Resume$Sp_GetAll_ResumeWorkExperienceByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/resume/get/work-experience/by-resume |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Education-> add |  | Resume$Sp_Add_ResumeEducation | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/resume/add/education |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Education-->Get |  | Resume$Sp_GetAll_ResumeEducationByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | GET~/api/resume/education/list |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Education -->Update |  | Resume$Sp_Update_ResumeEducation | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | PUT~/api/resume/update/resume/education |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Certificate-> add |  | Resume$Sp_Add_ResumeCertification | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~ /api/resume/resume/certification/add |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Certificate-->Get |  | Resume$Sp_GetAll_ResumeCertificationByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | GET~/api/resume/certification/list |  | Completed |  | 2025-06-24 | Working
Client Portal | Career Planing--> Resume | Certificate -->Update |  | Resume$Sp_Update_ResumeCertification | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | PUT~/api/resume/update/certification |  | Completed |  | 2025-06-24 | Working
Client Portal | Career Planing--> Resume | Skills-> add |  | Resume$Sp_Update_ResumeSkill | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | PUT~/api/resume/skill/update |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Skills-->Get |  | Resume$Sp_GetAll_ResumeSkillByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | GET~/api/resume/certification/list |  | Completed |  | 2025-06-24 | Working
Client Portal | Career Planing--> Resume | Skills -->Update |  | Resume$Sp_Update_ResumeSkill | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | PUT~/api/resume/skill/update |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Language-> add |  | Resume$Sp_Add_ResumeLanguage | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/resume/add/language |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | Language-->Get |  | Resume$Sp_GetAll_ResumeLanguageByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | GET~/api/resume/language/list |  | Completed |  | 2025-06-24 | Working
Client Portal | Career Planing--> Resume | Language -->Update |  | Resume$Sp_Update_ResumeLanguage | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | PUT~/api/resume/language/update |  | Completed |  | 2025-06-24 | Working
Client Portal | Career Planing--> Resume | Hobbies-> add |  | Resume$Sp_Update_Resumehobbies | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | PUT~/api/resume/update/hobbies |  | Completed |  | 2025-06-24 | Working
Client Portal | Career Planing--> Resume | Hobbies-->Get |  | Resume$Sp_Get_Resumehobbies | Completed | Balagi G | 2025-06-12 | 2025-06-19 | New Procedure | GET~/api/resume/get/hobbies/details |  | Completed |  | 2025-06-24 | Working
Client Portal | Career Planing--> Resume | Hobbies -->Update |  | Resume$Sp_Update_Resumehobbies | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | PUT~/api/resume/update/hobbies |  | Completed |  | 2025-06-24 | Working
Client Portal | career planing--> resume | freelancer profile--> add |  | Resume$Sp_Add_ResumeFreelanceProfile | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/resume/add/freelance |  | Completed |  | 2025-06-20 | Working
Client Portal | career planing--> resume | freelancer profile--> update |  | Resume$Sp_Update_ResumeFreelanceProfile | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | PUT~/api/resume/update/freelance |  | Completed |  | 2025-06-24 | Working
Client Portal | career planing--> resume | freelancer profile --> Get |  | Resume$Sp_GetAll_ResumeFreelanceProfileByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~api/resume/get/freelance/list |  | Completed |  | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Honor & Awards--> add |  | Resume$Sp_Add_ResumeAward | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET ~/api/resume/award/add |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Honor & Awards-->Get |  | Resume$Sp_GetAll_ResumeAwardByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | PUT ~ /api/resume/award/update |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Honor & Awards -->Update |  | Resume$Sp_Update_ResumeAward | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | POST ~ /api/resume/add/job-preference |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Job Preference-> add |  | Resume$Sp_Add_ResumeJobPreference | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | GET ~ /api/resume/get/job-preference |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Job Preference-->Get |  | Resume$Sp_Get_ResumeJobPreference | Completed | Balagi G | 2025-06-12 | 2025-06-19 | modified | PUT ~ /api/resume/update/job-preference |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Job Preference -->Update |  | Resume$Sp_Update_ResumeJobPreference | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | POST ~ /api/resume/resume/visibility/add |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Resume Visibility-> add |  | Resume$Sp_Update_ResumeVisibility | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | PUT ~ /api/resume/resume/visibility/update |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Resume Visibility-->Get |  | Resume$Sp_Get_Resumevisibility | Completed | Balagi G | 2025-06-12 | 2025-06-19 | New Procedure | GET ~ /api/resume/resume/visibility/get |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | Resume Visibility -->Update |  | Resume$Sp_Update_ResumeVisibility | Completed | Balagi G | 2025-06-12 | 2025-06-12 | New Procedure | PUT ~ /api/resume/resume/visibility/update |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | References-> add |  | Resume$Sp_Add_ResumeReference | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/resume/reference/add |  | Completed |  | 2025-06-20 | Working
Client Portal | Career Planing--> Resume | References-->Get |  | Resume$Sp_GetAll_ResumeReferenceByResume | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | GET~/api/resume/get/references |  | Completed | 2025-06-13 | 2025-06-13 | Working
Client Portal | Career Planing--> Resume | References -->Update |  | Resume$Sp_Update_ResumeReference | Completed | Balagi G | 2025-06-12 | 2025-06-12 | modified | PUT~/api/resume/reference/update |  | Completed | 2025-06-13 | 2025-06-24 | Working
Client Portal | Career Planing--> Find Work | Job Listings |  | Job$SpSearchJobs | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~ /api/job/search |  | Completed | 2025-06-16 | 2025-06-23 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Job Listings -> Save Job |  | Job$SpSaveUserJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~ /api/job/user/save |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Job Listings -> UnSave Job |  | Job$SpSaveUserJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~ /api/job/user/save |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Job Listings -> View Job |  | Job$SpGetJobDetails ,Organization$SpGetOrganizationDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/job/details |  | Completed | 2025-06-16 | 2025-06-23 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Job Listings -> View Job -> Apply Job |  | Job$SpApplyJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/job/apply |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Job Listings -> View Job -> Organization Details |  | Organization$SpGetOrganizationDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/arkansas/organization/details |  | Completed | 2025-06-16 | 2025-06-13 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Job Listings -> View Job -> Similar Jobs |  | Job$SpGetSimilarJobs | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/job/similar-jobs |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Job Listings -> View Job -> Save Job |  | Job$SpSaveUserJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~ /api/job/user/save |  | Completed | 2025-06-16 | 2025-06-23 | Working |  | Ezhavendhan
| Career Planing--> Find Work | Job Listings -> View Job -> Unsave Job |  | Job$SpSaveUserJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~ /api/job/user/save |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Find Work | Job Listings -> View Job -> Apply Job -> All Resume |  | Job$SpApplyJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/job/apply |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Find Work | Employees |  | dbo.usp_Employer_GetList_S1 | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/job/employer/list |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Find Work | Employees -> View Company Profile |  | Organization$SpGetOrganizationDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/arkansas/organization/details |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Employees -> View Company --> Company Stats |  | Organization$SpGetOrganizationDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 | Doubts --> Ratings | GET~/api/arkansas/organization/details |  | Completed | 2025-06-16 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Find Work | Employees -> View Company --> All Job |  |  | pending | Balagi G | 2025-06-12 | 2025-06-12 | doubts--> no use case |  |  |  | 2025-06-16 |  |  |  | Ezhavendhan
Client Portal | Career Planing--> Find Work | Employees --> View Company -->Review |  | dbo.Review$GetAllByUserAndOrganization | Completed | Balagi G | 2025-06-12 | 2025-06-12 | Doubts | GET~/api/organization/review/list |  | Completed | 2025-06-16 | 2025-06-25 | Working |  | Ezhavendhan
| Career Planing--> Job Invitations | All Job Invitations |  | Job$SpGetJobInvitations | Completed | Balagi G | 2025-06-12 | 2025-06-18 |  | GET~/api/job/invitations |  | Completed | 2025-06-17 | 2025-06-23 | Working |  | Ezhavendhan
| Career Planing--> Job Invitations | View Invitations |  | Job$SpGetJobInvitationDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/job/invitation-details |  | Completed | 2025-06-17 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Job Invitations | View Job Details |  | Job$SpGetJobDetails ,Organization$SpGetOrganizationDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/job/details GET~/api/arkansas/organization/details |  | Completed | 2025-06-17 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Job Invitations | Apply for the job |  | Job$SpApplyJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~/api/job/apply |  | Completed | 2025-06-17 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Job Invitations | Save this Job |  | Job$SpSaveUserJob | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | POST~ /api/job/user/save |  | Completed | 2025-06-17 | 2025-06-24 | Working |  | Ezhavendhan
Client Portal | Career Planing--> Job Invitations | Message |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 |  | GET~/api/application/user/message-history |  | Completed | 2025-06-17 | 2025-06-13 | Working |  | Ezhavendhan
| Career Planing--> Job Invitations | View Invitations --> Denied |  | Job$SpUpdateJobInvitationStatus | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | PUT~/api/job/invitation/status |  | Completed | 2025-06-17 | 2025-06-13 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Submitted Proposal |  | Job$SpGetJobApplications | Completed | Balagi G | 2025-06-12 | 2025-06-18 |  | GET~/api/job/application/list |  | Completed | 2025-06-17 | 2025-06-23 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Rejected |  | Job$SpGetJobApplications | Completed | Balagi G | 2025-06-12 | 2025-06-18 |  | GET~/api/job/application/list |  | Completed | 2025-06-17 | 2025-06-23 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Shortlisted |  | Job$SpGetJobApplications | Completed | Balagi G | 2025-06-12 | 2025-06-18 |  | GET~/api/job/application/list |  | Completed | 2025-06-17 | 2025-06-23 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Received Offers |  | Job$SpGetJobApplications | Completed | Balagi G | 2025-06-12 | 2025-06-18 |  | GET~/api/job/application/list |  | Completed | 2025-06-17 | 2025-06-23 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Submitted Proposal --> Withdraw Applications |  | Job$SpUpdateJobApplicationStatus | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | Put/api/job/update-job-application-status |  | Completed | 2025-06-17 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Submitted Proposal --> Browse Similar Opportunities |  | Job$SpGetSimilarJobs | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/job/similar-jobs |  | Completed | 2025-06-17 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Shortlisted --> View Employee Profile |  | Organization$SpGetOrganizationDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/arkansas/organization/details |  | Completed | 2025-06-17 | 2025-06-13 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Shortlisted --> View Scheduling |  | Calendar$SpGetAppointment | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~ /api/appointments/calendar/appointment |  | Completed | 2025-06-17 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Received Offers --> View Offer |  | [Job$SpGetJobOfferDetails] | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET/api/job/offer |  | Completed | 2025-06-18 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Received Offers --> View Contract Details |  | Job$SpGetJobContractDetails | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | GET~/api/job/contract/detail |  | Completed | 2025-06-18 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Received Offers --> View Offer --> Accept |  | Job$SpUpdateJobOfferStatus | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | Get/api/job/offer/status |  | Completed | 2025-06-18 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing--> Sent Applications | Received Offers --> View Offer --> Decline |  | Job$SpUpdateJobOfferStatus | Completed | Balagi G | 2025-06-12 | 2025-06-12 |  | Get/api/job/offer/status |  | Completed | 2025-06-18 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing --> Contracts | All Contract |  | dbo.Job$SpGetJobContracts | Completed | Jayavarthini R | 2025-06-13 | 2025-06-12 |  | GET~/api/job/contracts |  | Completed | 2025-06-18 | 2025-06-24 | Working |  | Ezhavendhan
Client Portal | Career Planing --> Contracts | View Contract Details --> Contract Details |  | Job$SpGetJobContractDetails | Completed | Jayavarthini R | 2025-06-13 | 2025-06-12 |  | GET~/api/job/contract/detail |  | Completed | 2025-06-18 | 2025-06-16 | Working |  | Ezhavendhan
| Career Planing --> Contracts | Pause Contract |  | Job$SpUpdateJobContractStatus | Completed | Jayavarthini R | 2025-06-13 | 2025-06-12 |  | PUT~/api/job/job-contract/update-status |  | Completed | 2025-06-18 | 2025-06-24 | Working |  | Ezhavendhan
| Career Planing --> Contracts | End Contract |  | Job$SpUpdateJobContractStatus | Completed | Jayavarthini R | 2025-06-13 | 2025-06-12 |  | GET~/api/job/contract/detail |  | Completed |  | 2025-06-16 | Working |  | Ezhavendhan
| Career Planing --> Contracts | View Contract Details --> Contract Timeline |  |  | Pending | [11 empty] | Ezhavendhan
Client Portal | Career Planing --> Contracts | View Contract Details -->Payment Information |  | Job$SpGetContractPaymentInfo | Completed | Jayavarthini R |  | 2025-06-12 | New Procedure | GET~/api/job/contract/payment-info |  | Completed | 2025-06-18 | 2025-06-25 | Working |  | Ezhavendhan
Client Portal | Career Planing --> Contracts | View Contract Details -->Contract Document |  | Job$SpGetUserContractDocuments | Completed | Jayavarthini R |  | 2025-06-12 | New Procedure | GET~/api/job/contract/documents |  | Completed | 2025-06-18 | 2025-06-25 | Working |  | Ezhavendhan
| Career Planing --> Contracts | End Contract --> Review |  | usp_EndContractAndSubmitReview | Completed | Jayavarthini R | 2025-06-13 | 2025-06-12 | New Procedure | POST~/api/job/contract/end-and-review |  | Completed | 2025-06-18 | 2025-06-25 | Working |  | Ezhavendhan
| Career Planing --> Contracts | View Contract Details --> Message |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri S | 2025-06-13 | 2025-06-12 | modified | GET~/api/application/user/message-history |  | Completed | 2025-06-18 | 2025-06-18 | Working |  | Ezhavendhan
| Career Planing --> Contracts | View Contract Details --> Timesheet --> Summary |  | Timesheet$Sp_Get_Summary | Completed | Balagi G | 2025-06-13 |  |  | GET ~ /api/timesheet/timesheet/summary |  |  | 2025-06-18 |  |  |  | Ezhavendhan
| Career Planing --> TIMESHEET | Add Timesheet |  | Timesheet$Sp_AddOrUpdate_Entry | Completed | Balagi G | 2025-06-13 | [5 empty] | 2025-06-18 |  |  |  | Ezhavendhan
Client Portal | Career Planing --> Contracts | View Contrac Details --> Timesheet --> Work Diaries |  | Timesheet$Sp_Get_WorkDiary | Completed | Balagi G | 2025-06-13 |  | Doubts - Tracking | GET ~ /api/timesheet/get/work-diary |  |  | 2025-06-18 |  |  |  | Ezhavendhan
Client Portal | Career Planing --> Contracts | View Contrac Details --> Timesheet --> Recent Transactions |  | Contract$Sp_Get_RecentTransactions | Completed | Pavan Kalyan | 2025-06-13 |  | Doubts - Transaction | GET ~ /api/contract/get/recent-transactions |  |  | 2025-06-18 |  |  |  | Ezhavendhan
Client Portal | Career Planing --> Work Diary | Time tracker |  | Sp_StartProjectTracking,Sp_StopProjectTracking | Completed | Balagi G | 2025-06-13 |  | Doubts Project |  |  |  | 2025-06-19 |  |  |  | Ezhavendhan
| Career Planing --> Work Diary | Status |  |  | Completed | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19 |  |  |  | Ezhavendhan
| Career Planing --> Work Diary | Activity Timeline |  | GetClientWorkDiary | Completed | Murugan S | 2025-06-13 |  | doubts- |  |  |  | 2025-06-19 |  |  |  | Ezhavendhan
| Career Planing --> Work Diary | Projects |  | GetWorkDiaryWeeklySummary | Completed | Murugan S | 2025-06-13 | [5 empty] | 2025-06-19 |  |  |  | Ezhavendhan
| Career Planing --> Work Diary | Settings |  |  | Pending | Murugan S | 2025-06-13 | [5 empty] | 2025-06-19 |  |  |  | Ezhavendhan
| Career Planing --> Work Diary | Weekly Summary |  | GetWorkDiaryWeeklySummary | Pending | Murugan S | 2025-06-13 | [5 empty] | 2025-06-19 |  |  |  | Ezhavendhan
| Career Planing --> Work Diary | Settings --> Update |  |  | Pending | Murugan S | 2025-06-13 | [5 empty] | 2025-06-19 |  |  |  | Ezhavendhan
| Career Planing --> Work Diary | Time tracker --> Update |  |  | Pending | Murugan S | 2025-06-13 | [5 empty] | 2025-06-19 |  |  |  | Ezhavendhan
| Timesheet | All Contract |  |  | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19
| Timesheet | View Contract |  |  | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19
| Timesheet | Daily View |  | GetTimesheetEntriesByDate | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19
| Timesheet | Daily View --> Add Timesheet |  | AddTimesheetEntry | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19
| Timesheet | Daily View --> Edit Timesheet |  | updatertimesheetentry | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19
| Timesheet | Work History |  | GetWorkHistoryByPayPeriod | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19
| Timesheet | Work History --> Record View |  |  | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-19
| Timesheet | Summary View --> Hours by Project |  | GetTimesheetSummaryByProject | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-20
| Timesheet | Summary View --> Hours by Type |  | GetTimesheetSummaryByProject | Pending | Balagi G | 2025-06-13 | [5 empty] | 2025-06-20
| Home | Notification Icon Count |  | usp_Get_Notifications_S1 | Completed | Nithyasri S | 2025-06-16 | 2025-06-12 |  | GET~/api/updates/notifications |  | Completed | 2025-06-20 | 2025-06-18 | Working
| Home | Message Icon Count |  | usp_User_ConversationSummary_GetList_S2 | Completed | Nithyasri S | 2025-06-16 | 2025-06-12 |  | GET~/api/application/conversation/summary |  | Completed | 2025-06-20 | 2025-06-18 | Working
| Home | Message Icon --> View Messages |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri S | 2025-06-16 | 2025-06-12 |  | GET~/api/application/user/message-history |  | Completed | 2025-06-20 | 2025-06-18 | Working
| Home | Notification Icon --> View Notification |  | usp_Get_Notifications_S1 | Completed | Nithyasri S | 2025-06-16 | 2025-06-12 |  | GET~/api/updates/notifications |  | Completed | 2025-06-20 | 2025-06-18 | Working
| Home | Profile |  |  | Pending | Jayavarthini R | 2025-06-16 | [5 empty] | 2025-06-20
| Home | Logout |  |  | Pending | Jayavarthini R | 2025-06-16 | [5 empty] | 2025-06-20
| Home | Profile --> Security |  |  | Pending | Jayavarthini R | 2025-06-16 | [5 empty] | 2025-06-20
| Home | Profile --> Update |  |  | Pending | Jayavarthini R | 2025-06-16 | [5 empty] | 2025-06-20
| Home | Profile --> View Review and ratings |  | Review$GetAllByUserAndOrganization usp_GetCandidateDetails | Completed | Jayavarthini R | 2025-06-16 | 2025-06-12 |  | GET~/api/organization/review/list |  | Completed | 2025-06-20 | 2025-06-25 | Working
| Home | Profile --> Security --> Update Password |  | dbo.Users$Sp_UpdatePassword | Completed | Jayavarthini R | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~ /api/login/update/password |  | Completed | 2025-06-20 | 2025-06-25 | Working
| Home | Profile --> Security --> Setup |  | Users$Sp_Update_TwoFactorDevice | Pending |  | 2025-06-16 | [5 empty] | 2025-06-20
| Home | Profile --> Security --> Two Factor Authentication --> update |  |  | Pending |  | 2025-06-16 | [5 empty] | 2025-06-20
| Home | Profile --> Settings |  |  | Pending |  | 2025-06-16 | [5 empty] | 2025-06-20
| Home | Profile --> Settings --> Update |  |  | Pending |  | 2025-06-16
| Resend Account Confirmation Email |  |  |  | Pending |  | 2025-06-16
| Forget Password Request |  |  |  | Pending
| Forget Password Confirmation |  |  |  | Pending
| timesheet | add Timesheet
update Timesheet
Get timesheet
timesheet details
Timeshhet summary
Client Portal | Timesheet |  |  | Contract$Sp_Get_RecentTransactions | [5 empty] | GET ~ /api/contract/get/recent-transactions |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Get_Summary | 1 |  |  |  |  | POST ~ /api/timesheet/add/timesheet-entry |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Get_ActiveNow | [5 empty] | GET ~ /api/timesheet/get/active-now |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Get_EntriesByDateRange | [5 empty] | GET ~/api/timesheet/get/entries-by-date-range |  | Completed
Client Portal | Timesheet >workhistory |  |  | Timesheet$Sp_Get_EntryDetails | 1 |  |  |  |  | GET ~ /api/timesheet/get/timesheet-entry |  | Completed
Client Portal | Timesheet >summary |  |  | Timesheet$Sp_Get_HoursByType ,Timesheet$Sp_Get_SummaryView | 1 |  |  |  |  | GET ~ /api/timesheet/get/hours-by-type |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Get_PendingList | [5 empty] | GET ~ /api/timesheet/timesheet/pending-list |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Get_Summary | [5 empty] | GET ~ /api/timesheet/timesheet/summary |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Get_SummaryView | [5 empty] | GET ~ /api/timesheet/get/timesheet-summary-view |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Get_WorkDiary | 1 |  |  |  |  | GET ~ /api/timesheet/get/work-diary |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_SubmitForReview | [5 empty] | POST ~ timesheet/submit-review |  | Completed
Client Portal | Timesheet |  |  | Timesheet$Sp_Update_Status_S1 | [5 empty] | PUT ~ timesheet/update-status |  | Completed
Client Portal | Work Diary |  |  | WorkDiary$Sp_GetActivityTimeline | [5 empty] | GET ~ /api/workdairy/workdiary/activity-timeline |  | Completed
Client Portal | Work Diary |  |  | WorkDiary$Sp_Get_Summary | [5 empty] | GET ~ work-diary/summary |  | Completed
Client Portal | Work Diary |  |  | WorkDiary$Sp_Get_SummaryMetrics | [5 empty] | GET ~ work-diary/summary-metrics |  | Completed
Client Portal | Work Diary |  |  | WorkDiary$Sp_Get_UserContractProjects | [5 empty] | GET ~ /api/workdairy/workdiary/user-contract-projects |  | Completed
Client Portal | Work Diary |  |  | WorkDiary$Sp_StartTracking | [5 empty] | POST ~ /api/workdairy/add/start-tracking |  | Completed
Client Portal | Work Diary |  |  | WorkDiary$Sp_StopTracking | [5 empty] | PUT ~ /api/workdairy/update/stop-tracking |  | Completed
Client Portal | Work Diary |  |  | WorkDiary$Sp_Upsert_UserSessionSettings | [5 empty] | POST ~ /api/workdairy/workdiary/upsert-user-session-settings |  | Completed
| Settings | preference >> Notification >> Insert preference |  | usp_User_NotificationPreference_Insert_S1
| Settings | preference >> Notification >> Update preference |  | usp_User_NotificationPreference_Update_S1
| Settings | preference >> Notification >> Get preference |  | usp_User_NotificationPreference_Get_S1

## Employer Portal
Portal | Module | Screen name | Priority | DB Team | [5 empty] | API Team | [5 empty] | UI Team
|  |  |  | Procedure | DB Status | DB Resource | ETA | Completed On | DB Comments | API EndPoint | API Resource | API Status | ETA | Completed On | API Comment | Task | Assigned To | ETA for Issue fixing | ETA for Api binding | Status | UI Completed On | Api completed on | Comments | Due date
Employers Portal | Dashboard | Summary |  | usp_DashboardQuickNav_GetList_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | GET ~ /api/dashboard/dashboard/quick-nav/list |  | Completed |  | 2025-06-25 | Working
Employers Portal | Dashboard | Active Jobs |  | Job$SpSearchJobs | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | Modified | GET~ /api/job/search |  | Completed | 2025-06-23 | 2025-06-23 | Working |  | Ezhavendhan | 1hr | 1hr 45mins
Employers Portal | Dashboard | Active Contracts |  | Job$SpGetJobContracts | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | Modified | GET~/api/job/contracts |  | Completed | 2025-06-23 | 2025-06-16 | Working |  | Ezhavendhan | 30mins | 1hr 45mins |  |  |  |  | Assigned To | Total ETA (hrs) | Total ETA (days)
Employers Portal | Dashboard | Active Jobs --> View Jobs |  | Job$SpGetJobDetails | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | Modified | GET~/api/job/details |  | Completed | 2025-06-23 | 2025-06-23 | Working
Employers Portal | Dashboard | Active Contract --> View Contract |  | Job$SpGetJobContractDetails | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | Modified | GET~/api/job/contract/detail |  | Completed | 2025-06-23 | 2025-06-24 | Working
Employers Portal | Company Profile | Company Profile --> Reviews |  | dbo.Review$GetAllByUserAndOrganization | Completed | Nivetha R | 2025-06-16 | 2025-06-12 | New Procedure | GET~/api/organization/review/list |  | Completed |  | 2025-06-25 | Working
Employers Portal | Company Profile | Company Profile |  | dbo.Organization$SpGetOrganizationDetails | Completed | Nivetha R | 2025-06-16 | 2025-06-12 | Modified | GET ~ /api/arkansas/organization/details |  | Completed | 2025-06-23 | 2025-06-13 | Working
Employers Portal | Company Profile | Company Stats |  | dbo.Organization$SpGetOrganizationDetails | Completed | Nivetha R | 2025-06-16 | 2025-06-12 | Modified | GET~/api/arkansas/organization/details |  | Completed | 2025-06-23 | 2025-06-13 | Working
Employers Portal | Company Profile | Profile Completion |  | dbo.Organization$SpGetOrganizationDetails | Completed | Nivetha R | 2025-06-16 | 2025-06-12 | Modified | GET~/api/arkansas/organization/details |  | Completed | 2025-06-23 | 2025-06-13 | Working
Employers Portal | Company Profile | Active Jobs |  | Job$SpSearchJobs | Completed | Nivetha R | 2025-06-16 | 2025-06-12 |  | GET~ /api/job/search |  | Completed | 2025-06-23 | 2025-06-23 | Working
Employers Portal | Company Profile | Edit Company Profile |  | dbo.Organization$SpUpdateOrganizationDetails | Completed | Nivetha R | 2025-06-16 | 2025-06-17 | New Procedure | PUT ~ /api/organization/organization/details |  | Completed | 2025-06-23 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | All Jobs |  | Job$SpSearchJobs | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | Modified | GET~ /api/job/search |  | Completed | 2025-06-23 | 2025-06-23 | Working
Employers Portal | Manage Job Posting | View Job Details |  | Job$SpGetJobDetails | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | Modified | GET~/api/job/details |  | Completed | 2025-06-23 | 2025-06-23 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job Work Authorization & Nationality >> get job Work Authorization & Nationality |  | Job$SpGetJobNationality | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-nationality |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job Skills & Qualifications >> get job Skills & Qualifications |  | Job$SpGetJobSkills | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-description |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details -->Update Compensation >> get Job Compensation |  | Job$SpGetJobSalaryDetails | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-skills |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Keywords & Visibility >> get Job Keywords & Visibility |  | Job$SpGetJobKeywords | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-keywords |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job Description >> get Job Description |  | Job$SpGetJobDesc | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-salary-details |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update basic Info >> get Job basic Info |  | Job$SpGetJobBasicInfo | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-basic-info |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Flags & Categories>> get Job Flags & Categories |  | Job$SpGetJobFlags | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-flags |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Application settings >> get Job Application settings |  | Job$SpGetJobApplicationSetting | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | GET ~ /api/job/get/job-application-settings |  | Completed |  | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> Work Authorization & Nationality |  | Job$SpUpdateJobNationality | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~ /api/job/update/job-nationality |  | Completed | 2025-06-23 | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> Skills & Qualifications |  | Job$SpUpdateJobSkills | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~ /api/job/update/job-skills |  | Completed | 2025-06-23 | 2025-06-20 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> Compensation |  | Job$SpUpdateJobSalaryDetails | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~api/job/update/job-salary-details |  | Completed |  | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> Keywords & Visibility |  | Job$SpUpdateJobKeywords | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~api/job/update/job-keywords |  | Completed |  | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> Job Description |  | Job$SpUpdateJobDesc | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~api/job/update/job-description |  | Completed |  | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> basic Info |  | Job$SpUpdateJobBasicInfo | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~api/job/update/job-basic-info |  | Completed |  | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> Job Flags & Categories |  | Job$SpUpdateJobFlags | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~api/job/update/job-flags |  | Completed |  | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Job Details --> Update Job >> Application settings |  | Job$SpUpdateJobApplicationSetting | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | PUT ~ /api/job/job/application-settings |  | Completed |  | 2025-06-25 | Working
Employers Portal | Manage Job Posting | Delete Job |  | Job$SpDeleteJob | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | New Procedure | DELETE ~ /api/job/job/delete |  | Completed | 2025-06-23 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | Close Job |  | Job$SpUpdateJobStatus | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 |  | PUT ~ /api/job/update/job-status |  | Completed | 2025-06-23 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | Draft Job --> Publish Job |  | Job$SpUpdateJobStatus | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 |  | PUT ~ /api/job/update/job-status |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | Close Job --> Reopen |  | Job$SpUpdateJobStatus | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 |  | PUT ~ /api/job/update/job-status |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | Company Job Postings --> Manual --> Create Job |  | Job$SpSaveJob | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 | Modified | POST ~ /api/job/save |  | Completed | 2025-06-24 | 2025-06-23 | Working
Employers Portal | Manage Job Posting | Company Job Postings --> AI --> Create Job |  | Job$SpSaveJob | Completed | Pavan Kalyan | 2025-06-16 | 2025-06-12 |  | POST ~ /api/job/save |  | Completed | 2025-06-24 | 2025-06-23 | Working
Employers Portal | Manage Job Posting | View --> Invite Candidates |  | usp_GetAllCandidatesByOrganization | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/job/organization/candidates |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Invite Candidates --> Invite to Apply |  | nvitation | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 | Modified | POST~/api/job/add/invitation |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Invite Candidates --> View Candidate Details |  | usp_GetCandidateDetails | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/dashboard/candidate/details |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Invite Candidates --> View Candidate Details --> Download |  | Resume$Sp_DownloadResume | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | POST~/api/resume/download |  | Completed | 2025-06-24 | 2025-06-18 | Working
Employers Portal | Manage Job Posting | View --> Invite Candidates --> View Candidate Details --> Ratings |  | Review$GetAllByUserAndOrganization | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/organization/review/list |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> To Review |  | Job$SpGetReviewProposalUserList | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 | New Procedure | GET~/api/job/proposal/review-candidates |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> To Review --> View Candidate Details |  | usp_GetCandidateDetails | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/dashboard/candidate/details |  | Completed | 2025-06-24 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> To Review --> Message |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | Modified | GET~/api/application/user/message-history |  | Completed | 2025-06-24 | 2025-06-13 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> To Review --> Make Offer |  | Job$SpAddJobOffer | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | POST/api/job/offer/add |  | Completed | 2025-06-24 | 2025-06-13 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> To Review --> Rejected |  | Job$SpUpdateJobApplicationStatus | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | Put/api/job/update-job-application-status |  | Completed | 2025-06-24 | 2025-06-24 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> To Review --> Shorlisted |  | Job$SpUpdateJobApplicationStatus | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | Put/api/job/update-job-application-status |  | Completed | 2025-06-24 | 2025-06-24 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> Shortlisted |  | Job$SpGetReviewProposalUserList | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/job/proposal/review-candidates |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> Shortlisted --> Not Interested |  | Job$SpUpdateJobApplicationStatus | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | Put/api/job/update-job-application-status |  | Completed | 2025-06-25 | 2025-06-24 | Working
Employers Portal | Manage Job Posting | View --> Review Proposals --> Shortlisted --> Schedule Interview |  | Calendar$SpAddAppointment | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-25 |  | POST ~ /api/appointments/add/appointment |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Hired --> Offers |  | Job$SpGetReviewProposalUserList | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 | New Procedure | GET~/api/job/proposal/review-candidates |  |  | 2025-06-25
Employers Portal | Manage Job Posting | View --> Hired --> Offers --> Cancel Offer |  | Job$SpUpdateJobOfferStatus | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | Get/api/job/offer/status |  | Completed | 2025-06-25 | 2025-06-24 | Working
Employers Portal | Manage Job Posting | View --> Hired --> Offers --> View Offers |  | Job$SpGetJobOfferDetails | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET/api/job/offer |  | Completed | 2025-06-25 | 2025-06-24 | Working
Employers Portal | Manage Job Posting | View --> Hired --> Hired |  | Job$SpGetReviewProposalUserList | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/job/proposal/review-candidates |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Archieved --> Not Interested |  | Job$SpGetReviewProposalUserList | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/job/proposal/review-candidates |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Manage Job Posting | View --> Archieved --> Rejected |  | Job$SpGetReviewProposalUserList | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/job/proposal/review-candidates |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Find Candidates | Find Candidates |  | usp_GetAllCandidatesByOrganization | Completed | Nivetha R | 2025-06-17 | 2025-06-12 | New Procedure | GET~/api/job/organization/candidates |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Find Candidates | Find Candidates --> Invite to Apply |  | Job$SpAddJobInvitation | Completed | Nivetha R | 2025-06-17 | 2025-06-12 |  | POST~/api/job/add/invitation |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Find Candidates | Find Candidates --> View Candidate Details |  | usp_GetCandidateDetails | Completed | Nivetha R | 2025-06-17 | 2025-06-12 | New Procedure | GET~/api/dashboard/candidate/details |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Find Candidates | Saved Candidates |  | dbo.Org$SpSaveCandidate | Completed | Nivetha R | 2025-06-17 | 2025-06-17 | New Procedure | POST~/api/dashboard/candidate/save |  | Completed | 2025-06-25 | 2025-06-25 | Working
Employers Portal | Find Candidates | find candidates --> view ratings |  | dbo.Review$GetAllByUserAndOrganization | Completed | Nivetha R | 2025-06-17 | 2025-06-12 | New Procedure | GET~/api/organization/review/list |  | Completed |  | 2025-06-25 | Working
Employers Portal | Contracts | All Contract |  | Job$SpGetJobContracts | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/job/contracts |  | Completed | 2025-06-25 | 2025-06-16 | Working
Employers Portal | Contracts | Active Contract --> View Contract |  | Job$SpGetJobContractDetails | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | GET~/api/job/contract/detail |  | Completed | 2025-06-25 | 2025-06-24 | Working
Employers Portal | Contracts | Active Contract --> View Contract --> Recent Updates |  | Job$SpGetContractActivities | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-25 | New Procedure | GET~/api/job/contract/activity/list |  | Completed | 2025-06-26 | 2025-06-26 | Working
Employers Portal | Contracts | Active Contract --> View Contract --> View Timesheet>>Summary |  | Timesheet$Sp_Get_Summary, | Pending | Pavan Kalyan | 2025-06-17 | [5 empty] | 2025-06-26
Employers Portal | Contracts | Active Contract --> View Contract --> View Timesheet>>Work dairy |  | Timesheet$Sp_Get_WorkDiary | Pending | Pavan Kalyan
Employers Portal | Contracts | Active Contract --> View Contract --> View Timesheet>>Recent Transactions |  | Contract$Sp_Get_RecentTransactions | completed | Pavan Kalyan |  |  |  | GET ~ /api/contract/get/recent-transactions
Employers Portal | Contracts | Active Contract --> View Contract --> Message |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri S | 2025-06-17 | 2025-06-12 |  | GET~/api/application/user/message-history |  | Completed | 2025-06-26 | 2025-06-18 | Working
Employers Portal | Contracts | Active Contract --> View Contract --> Pay Bonus |  | Job$SpAddJobContractBonus | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 | New Procedure | POST ~ /api/contract/bonus/add |  |  | 2025-06-26
Employers Portal | Contracts | Active Contract --> View Contract --> End Contract |  | Job$SpUpdateJobContractStatus | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | PUT~/api/job/job-contract/update-status |  | Completed | 2025-06-26 | 2025-06-24 | Working
Employers Portal | Contracts | Active Contract --> View Contract --> Pause Contract |  | Job$SpUpdateJobContractStatus | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | PUT~/api/job/job-contract/update-status |  | Completed | 2025-06-26 | 2025-06-24 | Working
Employers Portal | Contracts | Paused Contract --> View Contract --> Resume Contract |  | usp_GetAllCandidatesByOrganization | Completed | Pavan Kalyan | 2025-06-17 | 2025-06-12 |  | PUT~/api/job/job-contract/update-status |  | Completed | 2025-06-26 | 2025-06-24 | Working
|  | get contract bonus |  | Contract$SpGetContractBonusList | Completed | Pavan Kalyan |  | 2025-06-25 | new procedure | GET ~ /api/contract/bonus/list
Employers Portal | TimeSheet | All TimeSheet |  | Timesheet$GetTimesheetsByStatus | Pending | Balagi G | 2025-06-17 | [5 empty] | 2025-06-26
Employers Portal | TimeSheet | Pending Approval --> View Details |  |  | Pending | Balagi G | 2025-06-18 |  | Doubts |  |  |  | 2025-06-26
Employers Portal | TimeSheet | Pending Approval --> Approve |  | dbo.Timesheet$sp_updateTimesheetstatus | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-26
Employers Portal | TimeSheet | Pending Approval --> Reject |  |  | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-26
Employers Portal | TimeSheet | Pending Approval --> Approve All |  |  | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-26
Employers Portal | TimeSheet | Pending Approval --> View Details --> Daily View |  | Timesheet$Sp_Get_DailyTimesheetEntry | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-26
Employers Portal | TimeSheet | Pending Approval --> View Details --> Work History |  | Timesheet$Sp_Get_EntriesByDateRange | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-26
Employers Portal | TimeSheet | Pending Approval --> View Details --> Summary |  | timesheet$GetTimesheetSummaryDetails | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-26
Employers Portal | TimeSheet | TimeSheet Details --> Daily View |  | GetTimesheetEntriesByDate ,dbo.timesheet$gettimesheetentry_details | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-27
Employers Portal | TimeSheet | TimeSheet Details --> Consolidated View |  | Timesheet$Sp_Get_ConsolidatedTimesheetDetails,dbo.timesheet$gettimesheetentry_details | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-27
Employers Portal | TimeSheet | TimeSheet Details --> Summary --> Hours By Project |  | GetTimesheetSummaryByProject,dbo.timesheet$gettimesheetentry_details | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-27
Employers Portal | TimeSheet | TimeSheet Details --> Summary --> Hours By Type |  |  | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-27
Employers Portal | Work Diary | All Employees |  |  | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-27
Employers Portal | Work Diary | Active Employees --> Contract Timesheet |  |  | Pending | Balagi G | 2025-06-18 | [5 empty] | 2025-06-27
Employers Portal | Updates | Updates |  | usp_Get_Notifications_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | GET ~ /api/updates/notifications |  | Completed | 2025-06-27 | 2025-06-25 | Working
|  | Mark All as Read |  | usp_Update_Notification_ReadStatus_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | POST ~ /api/updates/notifications/update-read-status |  | Completed |  | 2025-06-25 | Working
|  | Notification Actions |  | usp_Insert_NotificationRecipientActionLog_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | PUT ~ /api/updates/notifications/action-log |  | Completed |  | 2025-06-25 | Working
Employers Portal | Updates | Delete Notification |  | usp_Delete_Notification_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | DELETE ~ /api/updates/notifications/delete |  | Completed | 2025-06-27 | 2025-06-25 | Working
Employers Portal | Messages | Messages --> Participant List |  | usp_User_ConversationSummary_GetList_S2 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | GET ~ /api/application/conversation/summary |  | Completed | 2025-06-27 | 2025-06-25 | Working
Employers Portal | Messages | Messages --> Message History |  | usp_MessageHistory_Fetch_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | Modified | GET~/api/application/user/message-history |  | Completed | 2025-06-27 | 2025-06-18 | Working
Employers Portal | Messages | Messages --> Send Message |  | usp_Conversation_CreateAndInsertMessage_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | Modified | POST ~ /api/arkansas/conversation/create-insert-message |  | Completed | 2025-06-27 | 2025-06-25 | Working
Employers Portal | Messages | Messages --> Update Message Read Status |  | usp_Message_ReadStatus_Update_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | PUT ~ /api/application/update/message-read-status |  | Completed |  | 2025-06-25 | Working
Employers Portal | Messages | Message --> Add Attachments |  | usp_MessageAttachment_Insert_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | POST ~ /api/application/insert/message-attachments |  | Completed |  | 2025-06-25 | Working
Employers Portal | Appointment |  |  |  | Pending | Pavan Kalyan | 2025-06-18 | 2025-06-12 |  |  |  |  | 2025-06-27
Employers Portal | Sign-In & SignUp |  |  |  | Pending |  | 2025-06-18 | 2025-06-12 |  |  |  |  | 2025-06-27
Employers Portal | Settings | preference >> Notification >> Insert preference |  | usp_User_NotificationPreference_Insert_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | POST ~/api/application/insert/notification-preferences |  | Completed |  | 2025-06-25 | Working
Employers Portal | Settings | preference >> Notification >> Update preference |  | usp_User_NotificationPreference_Update_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | PUT ~ /api/application/update/notification-preferences |  | Completed |  | 2025-06-25 | Working
Employers Portal | Settings | preference >> Notification >> Get preference |  | usp_User_NotificationPreference_Get_S1 | Completed | Nithyasri S | 2025-06-12 | 2025-06-12 | New Procedure | GET ~ /api/application/get/notification-preferences |  | Completed |  | 2025-06-25 | Working
Employers Portal | Profile | user profile |  | Profile$Sp_GetEmployerDetails | Completed | Nivetha R | 2025-06-18 | 2025-06-17 | New Procedure | GET ~ /api/employer/profile/employer-details |  | Completed |  | 2025-06-25 | Working
Employers Portal | Profile | edit user profile |  | Profile$Sp_UpdateEmployerProfile | Completed | Nivetha R | 2025-06-18 | 2025-06-17 | New Procedure | PUT ~ /api/employer/profile/employer/update |  | Completed |  | 2025-06-25 | Working
Employers Portal | Profile | Update user password |  | dbo.Users$Sp_UpdatePassword | Completed | Nivetha R | 2025-06-18 | 2025-06-12 | New Procedure | PUT ~ /api/login/update/password |  | Completed |  | 2025-06-25 | Working
Employers Portal | Sign Up | Add organization and employer |  | usp_Insert_Organization_Details_S1 | Completed | Nithyasri S | 2025-06-19 | 2025-06-12 | New Procedure | POST ~ /api/organization/details |  | Completed |  | 2025-06-25 | Working
Employers Portal | Sign Up | Add organization Address |  | usp_OrganizationAddress_Add_S1 | Completed | Nithyasri S | 2025-06-20 | 2025-06-12 | New Procedure | POST ~ /api/organization/address |  | Completed |  | 2025-06-25 | Working

## Execution Stmt
Procedure Name | Execution Statment
Job$SpSearchJobs | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpSearchJobs @Ai_SignedOnUser_ID = 6, @Ai_Client_ID = NULL, @Ai_Organization_ID = NULL, @As_Search_TEXT = NULL, --N'.NET', @Ac_Status_CODE = NULL, @Ac_JobCategory_CODE = NULL, @Ac_LocationType_CODE = NULL, @Ac_JobType_CODE = NULL, @Ac_EmploymentType_CODE = NULL, @Ac_ExperienceLevel_CODE = NULL, @As_Skill_TEXT = NULL, @Ai_SalaryMin_NUMB = NULL, @Ai_SalaryMax_NUMB = NULL, @Ab_Saved_INDC = 0, @Ab_PostedLastDay_INDC = 0, @Ai_Resume_ID = NULL, @Ai_Job_ID = NULL, @As_Location_TEXT = 'Chicago, IL (Hybrid)', @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @As_SortBy_CODE = N'R', @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display the output values SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Job$SpGetJobContracts | DECLARE @Ac_Msg_CODE CHAR(5); DECLARE @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobContracts @Ai_SignedOnUser_ID = 12, -- Required @Ai_Organization_ID = 1, -- Optional filter @Ai_User_ID = NULL, -- Optional filter @As_Search_TEXT = null, -- Search text @As_Status_CODE = 'A', -- Status filter (like 'A', 'I', etc.) @Ai_From_NUMB = 1, -- Pagination start @Ai_To_NUMB = 10, -- Pagination end @As_Sort_CODE = N'Recent', -- 'Recent' or 'Oldest' @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- To see output results: SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Job$SpGetJobContractDetails | DECLARE @Ai_Contract_ID INT = 1, -- Replace with actual contract ID -- @As_Contractid_TEXT NVARCHAR(100), @As_ContractTitle_TEXT NVARCHAR(100), @As_ContractDesc_TEXT NVARCHAR(4000), @As_ContractType_CODE CHAR(1), @As_ContractTypeDesc_TEXT NVARCHAR(50), @Ad_Start_DATE DATE, @Ad_End_DATE DATE, @Ai_Salary_NUMB DECIMAL(18,2), @As_PayPeriod_CODE CHAR(1), @As_PayPeriodDesc_TEXT NVARCHAR(50), @Ai_ExpectedHoursPerWeek_NUMB INT, @An_TotalContractSalary_NUMB DECIMAL(18,2), @As_PaymentType_CODE CHAR(2), @As_PaymentTypeDesc_TEXT NVARCHAR(50), @As_AdditionalInfo_TEXT NVARCHAR(MAX), @Ai_User_ID INT, @As_CandidateName_TEXT NVARCHAR(200), @Ai_Job_ID INT, @As_JobTitle_TEXT NVARCHAR(200), @As_JobType_CODE CHAR(2), @As_JobTypeDesc_TEXT NVARCHAR(50), @As_JobCategory_CODE CHAR(2), @As_JobCategoryDesc_TEXT NVARCHAR(50), @As_EmploymentType_CODE CHAR(2), @As_EmploymentTypeDesc_TEXT NVARCHAR(50), @As_LocationType_CODE CHAR(2), @As_LocationTypeDesc_TEXT NVARCHAR(50), @As_JobLocation_TEXT NVARCHAR(200), @Ai_Organization_ID INT, @As_OrganizationName_TEXT NVARCHAR(200), @As_AddressLine1_TEXT NVARCHAR(200), @As_AddressLine2_TEXT NVARCHAR(200), @As_City_TEXT NVARCHAR(100), @As_State_CODE CHAR(2), @As_PostalCode_TEXT NVARCHAR(20), @As_Country_CODE CHAR(2), @As_AddressTypeDesc_TEXT NVARCHAR(100), @Ai_CreatedBy_ID INT, @As_CreatedByName_TEXT NVARCHAR(200), @Ad_Created_DTTM DATETIME2, @Ai_UpdatedBy_ID INT, @As_UpdatedByName_TEXT NVARCHAR(200), @Ad_Updated_DTTM DATETIME2, @An_TransactionSeqEvent_NUMB BIGINT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); -- 🔥 Call the procedure EXEC dbo.Job$SpGetJobContractDetails @As_Contractid_TEXT OUTPUT, @As_ContractTitle_TEXT OUTPUT, @As_ContractDesc_TEXT OUTPUT, @As_ContractType_CODE OUTPUT, @As_ContractTypeDesc_TEXT OUTPUT, @Ad_Start_DATE OUTPUT, @Ad_End_DATE OUTPUT, @Ai_Salary_NUMB OUTPUT, @As_PayPeriod_CODE OUTPUT, @As_PayPeriodDesc_TEXT OUTPUT, @Ai_ExpectedHoursPerWeek_NUMB OUTPUT, @An_TotalContractSalary_NUMB OUTPUT, @As_PaymentType_CODE OUTPUT, @As_PaymentTypeDesc_TEXT OUTPUT, @As_AdditionalInfo_TEXT OUTPUT, @Ai_User_ID OUTPUT, @As_CandidateName_TEXT OUTPUT, @Ai_Job_ID OUTPUT, @As_JobTitle_TEXT OUTPUT, @As_JobType_CODE OUTPUT, @As_JobTypeDesc_TEXT OUTPUT, @As_JobCategory_CODE OUTPUT, @As_JobCategoryDesc_TEXT OUTPUT, @As_EmploymentType_CODE OUTPUT, @As_EmploymentTypeDesc_TEXT OUTPUT, @As_LocationType_CODE OUTPUT, @As_LocationTypeDesc_TEXT OUTPUT, @As_JobLocation_TEXT OUTPUT, @Ai_Organization_ID OUTPUT, @As_OrganizationName_TEXT OUTPUT, @As_AddressLine1_TEXT OUTPUT, @As_AddressLine2_TEXT OUTPUT, @As_City_TEXT OUTPUT, @As_State_CODE OUTPUT, @As_PostalCode_TEXT OUTPUT, @As_Country_CODE OUTPUT, @As_AddressTypeDesc_TEXT OUTPUT, @Ai_CreatedBy_ID OUTPUT, @As_CreatedByName_TEXT OUTPUT, @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID OUTPUT, @As_UpdatedByName_TEXT OUTPUT, @Ad_Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- 🔍 See results SELECT @Ai_Contract_ID AS ContractID, @As_Contractid_TEXT AS DisplayContractID, @As_ContractTitle_TEXT AS Title, @As_ContractDesc_TEXT AS Description, @As_ContractType_CODE AS ContractTypeCode, @As_ContractTypeDesc_TEXT AS ContractType, @Ad_Start_DATE AS StartDate, @Ad_End_DATE AS EndDate, @Ai_Salary_NUMB AS Salary, @As_PayPeriod_CODE AS PayPeriodCode, @As_PayPeriodDesc_TEXT AS PayPeriod, @Ai_ExpectedHoursPerWeek_NUMB AS ExpectedHoursPerWeek, @An_TotalContractSalary_NUMB AS TotalSalary, @As_PaymentType_CODE AS PaymentTypeCode, @As_PaymentTypeDesc_TEXT AS PaymentType, @As_AdditionalInfo_TEXT AS AdditionalInfo, @Ai_User_ID AS UserID, @As_CandidateName_TEXT AS Candidate, @Ai_Job_ID AS JobID, @As_JobTitle_TEXT AS JobTitle, @As_JobType_CODE AS JobTypeCode, @As_JobTypeDesc_TEXT AS JobType, @As_JobCategory_CODE AS JobCategoryCode, @As_JobCategoryDesc_TEXT AS JobCategory, @As_EmploymentType_CODE AS EmploymentTypeCode, @As_EmploymentTypeDesc_TEXT AS EmploymentType, @As_LocationType_CODE AS LocationTypeCode, @As_LocationTypeDesc_TEXT AS LocationType, @As_JobLocation_TEXT AS JobLocation, @Ai_Organization_ID AS OrganizationID, @As_OrganizationName_TEXT AS OrganizationName, @As_AddressLine1_TEXT AS AddressLine1, @As_AddressLine2_TEXT AS AddressLine2, @As_City_TEXT AS City, @As_State_CODE AS StateCode, @As_PostalCode_TEXT AS PostalCode, @As_Country_CODE AS CountryCode, @As_AddressTypeDesc_TEXT AS AddressType, @Ai_CreatedBy_ID AS CreatedByID, @As_CreatedByName_TEXT AS CreatedByName, @Ad_Created_DTTM AS CreatedDate, @Ai_UpdatedBy_ID AS UpdatedByID, @As_UpdatedByName_TEXT AS UpdatedByName, @Ad_Updated_DTTM AS UpdatedDate, @An_TransactionSeqEvent_NUMB AS TransactionSeqEvent, @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS ErrorDescription;
usp_ConversationSummary_GetAll_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ConversationSummary_GetAll_S1 @Ai_signedOnUser_ID = 1, -- <-- Replace with your signed-on user's ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the output values SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
usp_Get_Notifications_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Get_Notifications_S1 @As_Search_TEXT = null -- optional search string (can be NULL) , @Ac_ReadFilter_CODE = 'A' -- 'A' for All, 'U' for Unread, 'R' for Read , @Ai_From_NUMB = 1 -- page number for pagination , @Ai_To_NUMB = 10 -- number of rows per page , @Ai_SignedOnUser_ID = 2065 -- the user ID whose notifications are being fetched , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT , @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorDescription;
usp_Update_Notification_ReadStatus_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Update_Notification_ReadStatus_S1 @Ai_Notification_ID = 1 , @Ab_AllRead_INDC = 0 , @Ai_TransactionSeqEvent_NUMB = 1 , @Ai_SignedOnUser_ID = 1 , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT , @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ConversationSummary_GetList_S1
usp_Insert_Notifications_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_Error_Description VARCHAR(4000); EXEC usp_Insert_Notifications_S1 @Ac_NotificationType_CODE = 'JI' , @Ai_CaseMajorActivity_ID = NULL , @Ai_CaseMinorActivity_ID = NULL , @As_Action_CODE = NULL , @As_Title_TEXT = N'Job Invitation Sent to John Dae' , @As_Message_TEXT = N'You''ve sent an invitation to John Doe for the Senior Frontend Developer position.' , @As_Data_JSON = NULL , @Ai_User_ID = 1 , @Ac_Channel_CODE = 'WEB' , @Ab_Delivered_INDC = 0 , @Ab_Read_INDC = 0 , @Ad_Read_DTTM = NULL , @Ai_CreatedBy_ID = 1 , @Big_TransactionSeqEvent_NUMB = 1 , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT , @As_Error_Description = @As_Error_Description OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_Error_Description AS Message;
usp_User_NotificationPreference_Insert_S1 | DECLARE @MsgCode CHAR(5), @ErrorDesc VARCHAR(4000); EXEC usp_User_NotificationPreference_Insert_S1 @Ai_User_ID = 1, -- your user ID here @As_NotificationPrefs_JSON = N'[ {"NotificationType_CODE": "AU", "Channel_CODE": "web", "IsEnabled_INDC": 1}, {"NotificationType_CODE": "DR", "Channel_CODE": "web", "IsEnabled_INDC": 0} ]', @Ai_CreatedBy_ID = 1, -- who created this @Ai_TransactionSeqEvent_NUMB = 1, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_Error_Description = @ErrorDesc OUTPUT; -- Check output messages SELECT @MsgCode AS MsgCode, @ErrorDesc AS ErrorDescription;
usp_NotificationPreference_GetList_S1 | DECLARE @MsgCode CHAR(5), @ErrorDesc VARCHAR(4000); EXEC usp_NotificationPreference_GetList_S1 @Ai_User_ID = 1, -- replace with actual user ID @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Check output parameters SELECT @MsgCode AS MsgCode, @ErrorDesc AS ErrorDescription;
usp_User_NotificationPreference_Update_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_User_NotificationPreference_Update_S1 @Ai_User_ID = 1, @As_NotificationPref_JSON = N'[ { "NotificationType_CODE": "AU", "Channel_CODE": "WEB", "IsEnabled_INDC": 0 }, { "NotificationType_CODE": "DR", "Channel_CODE": "WEB", "IsEnabled_INDC": 1 }, { "NotificationType_CODE": "AR", "Channel_CODE": "WEB", "IsEnabled_INDC": 1 } ]', @Ai_TransactionSeqEvent_NUMB = 1, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_Conversation_CreateAndInsertMessage_S1 | DECLARE @Ai_Conversation_ID INT; DECLARE @Ai_Message_ID INT; DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_Error_Description NVARCHAR(4000); EXEC dbo.usp_Conversation_CreateAndInsertMessage_S1 @Ai_Conversation_ID = @Ai_Conversation_ID OUTPUT, -- Will return the conversation ID @As_ConversationName_TEXT = N'Important Discussion', -- Optional conversation name @Ai_Sender_ID = 1, -- Sender ID (User, Caseworker, or Organization ID) @Ac_SenderType_CODE = 'U', -- 'U' for User, 'C' for Caseworker, 'O' for Organization (Employer) @Ai_Receiver_ID = 2017, -- Receiver ID @Ac_ReceiverType_CODE = 'C', -- Receiver type code @Ai_Application_ID = NULL, -- Optional, e.g., Application ID if applicable @Ai_Organization_ID = NULL, -- Organization ID if relevant @Ac_EntityType_CODE = 'CASE', -- Entity type (e.g., CASE, CONTRACT) @Ai_Entity_ID = 5001, -- Entity ID @Ac_Topic_CODE = 'CASE_MGMT', -- Optional topic code (e.g., 'GENDISC') @As_Message_TEXT = N'Hello, I need clarification on the case.',-- Message text content @As_Attachments_JSON = N'[ -- Optional JSON for attachments { "FileName": "casefile.pdf", "FileType": "application/pdf", "FileSize": 1048576, "FilePath": "/uploads/casefile.pdf", "Checksum": "abc123def456ghi789jkl012mno345pq" } ]', @Ai_CreatedBy_ID = 1, -- Creator's user ID @Ai_TransactionSeqEvent_NUMB = 1, -- Transaction event number @Ai_Message_ID = @Ai_Message_ID OUTPUT, -- Output: Message ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, -- Output: Success ('S') or Failure ('F') @As_DescriptionError_TEXT = @As_Error_Description OUTPUT; -- Output: Error message if any -- Print outputs PRINT 'Conversation ID: ' + COALESCE(CAST(@Ai_Conversation_ID AS NVARCHAR), 'NULL'); PRINT 'Message ID: ' + COALESCE(CAST(@Ai_Message_ID AS NVARCHAR), 'NULL'); PRINT 'Message Code: ' + ISNULL(@Ac_Msg_CODE, 'NULL'); PRINT 'Error Description: ' + ISNULL(@As_Error_Description, 'None');
usp_User_ConversationSummary_GetList_S1 | DECLARE @Ac_Msg_CODE CHAR(5); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- Replace these with actual input values as per your scenario DECLARE @Ai_SignedOnUser_ID INT = 2; -- Example user ID DECLARE @As_Search_TEXT VARCHAR(200) = NULL; -- Optional search text DECLARE @Ab_UnreadOnly_INDC BIT = 0; -- 0: All, 1: Only unread DECLARE @Ai_From_NUMB INT = 1; -- Starting row number DECLARE @Ai_To_NUMB INT = 10; -- Page size (number of rows) -- Execute the procedure EXEC dbo.usp_ConversationSummary_GetList_S1 @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @As_Search_TEXT = @As_Search_TEXT, @Ab_UnreadOnly_INDC = @Ab_UnreadOnly_INDC, @Ai_From_NUMB = @Ai_From_NUMB, @Ai_To_NUMB = @Ai_To_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Print output parameters PRINT 'Message Code: ' + ISNULL(@Ac_Msg_CODE, 'NULL'); PRINT 'Error Description: ' + ISNULL(@As_DescriptionError_TEXT, 'None'); -- Note: The actual result set (list of conversations) will be returned as a query result from the procedure.
usp_MessageHistory_Fetch_S1 | DECLARE @Ai_Conversation_ID INT = 0; DECLARE @Ai_User_ID INT = 2082-- Replace with actual Conversation_ID DECLARE @As_Search_TEXT VARCHAR(200) = NULL; -- Optional, or provide search text DECLARE @Ai_Organization_ID INT = 0; -- Optional, filter by Organization_ID DECLARE @Ai_Job_ID INT = 0; -- Optional, filter by Job_ID DECLARE @Ai_SignedOnUser_ID INT = 12; -- Replace with actual SignedOnUser_ID DECLARE @Ai_From_NUMB INT = 1; -- Starting row number DECLARE @Ai_To_NUMB INT = 10; -- Page size DECLARE @Ac_Msg_Code CHAR(5); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the stored procedure EXEC dbo.usp_MessageHistory_Fetch_S1 @Ai_Conversation_ID = @Ai_Conversation_ID, @Ai_User_ID = @Ai_User_ID, @As_Search_TEXT = @As_Search_TEXT, @Ai_Organization_ID = @Ai_Organization_ID, @Ai_Job_ID = @Ai_Job_ID, @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @Ai_From_NUMB = @Ai_From_NUMB, @Ai_To_NUMB = @Ai_To_NUMB, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Print output parameters PRINT 'Message Code: ' + ISNULL(@Ac_Msg_Code, 'NULL'); PRINT 'Error Description: ' + ISNULL(@As_DescriptionError_TEXT, 'None');
usp_Insert_NotificationRecipientActionLog_S1 | DECLARE @Ai_NotificationRecipientAction_ID INT, @Ac_Msg_CODE CHAR(5), @As_Error_Description VARCHAR(4000); EXEC usp_Insert_NotificationRecipientActionLog_S1 @Ai_NotificationRecipient_ID = 101 , @Ac_Action_CODE = 'MSG' -- example: ACK = Acknowledge , @Ab_IsEnabled_INDC = 1 , @Ai_User_ID = 2 -- the user performing the action , @Ad_Action_DTTM = '2025-05-29' , @Ac_Reason_CODE = NULL -- optional , @As_Comments_TEXT = 'Acknowledged by user.' -- optional , @Ai_CreatedBy_ID = 1 , @Ad_Created_DTTM = '2025-05-29' , @An_TransactionSeqEvent_NUMB = 1 ,@Ai_NotificationRecipientAction_ID = @Ai_NotificationRecipientAction_ID OUTPUT , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT , @As_DescriptionError_TEXT = @As_Error_Description OUTPUT; SELECT @Ai_NotificationRecipientAction_ID AS OII, @Ac_Msg_CODE AS MsgCode, @As_Error_Description AS Description;
usp_Message_ReadStatus_Update_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_Error_Description VARCHAR(4000); EXEC usp_Message_ReadStatus_Update_S1 @As_MessageIDs_JSON = '[18]', @Ai_UpdatedBy_ID = 2, @An_TransactionSeqEvent_NUMB = 1, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_Error_Description OUTPUT; SELECT @Ac_Msg_Code, @As_Error_Description;
usp_Insert_Organization_Details_S1 | DECLARE @Ac CHAR(5) , @As VARCHAR(4000) , @OrgID INT , @OrgAddrID INT , @OrgMemID INT; EXEC usp_Insert_Organization_Details_S1 -- org @As_OrganizationName_TEXT = 'Test Organization' , @As_OrganizationDesc_TEXT = 'organization is used to test messages tab' , @As_WebsiteUrl_TEXT = 'https://nithutech.org' , @Ac_OrganizationType_CODE = 'BE' , @Ac_Status_CODE = 'A' , @Ac_RecruitmentStatus_CODE = 'Y' , @As_Logo_URL = 'https://cdn.nithutech/logo.png' , @As_size_text = '20+ Trainers' , @As_EmailAddress_TEXT = 'hello@nithutech.org' , -- address @Ac_AddressType_CODE = 'M' , @As_AddressLine1_TEXT = '987 Dev Lane' , @As_AddressLine2_TEXT = NULL , @As_City_TEXT = '1' , @Ac_State_CODE = 'CA' , @As_PostalCode_TEXT = '560001' , @Ac_Country_CODE = '001' , @An_Latitude_DECIMAL = NULL , @An_Longitude_DECIMAL = NULL , @Ab_IsPrimary_INDC = 1 , -- member @Ai_User_ID = 2068 , @Ac_MemberRole_CODE = 'A' , @Ad_StartDate_DATE = '2025-05-30' , @Ad_EndDate_DATE = NULL , -- certs @As_OrganizationCertification = N'[ { "CertificationName_TEXT": "AWS Training Partner", "CertificationDesc_TEXT": "Cloud Training Cert", "CertificationYear_NUMB": 2024 } ]' , -- meta @Ai_CreatedBy_ID = 1 , @An_TransactionSeqEvent_NUMB = 1 , -- outputs @Ai_Organization_ID = @OrgID OUTPUT , @Ai_OrganizationAddress_ID = @OrgAddrID OUTPUT , @Ai_OrganizationMember_ID = @OrgMemID OUTPUT , @Ac_Msg_Code = @Ac OUTPUT , @As_DescriptionError_TEXT = @As OUTPUT; SELECT @Ac AS MsgCode , @As AS MsgText , @OrgID AS Organization_ID , @OrgAddrID AS OrganizationAddress_ID , @OrgMemID AS OrganizationMember_ID;
usp_MessageAttachment_Insert_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @As_Attachments_JSON NVARCHAR(MAX) = N' [ { "FileName_TEXT": "resume.pdf", "FileType_TEXT": "application/pdf", "FileSize_NUMB": 34567, "FilePath_TEXT": "/uploads/resume.pdf", "Checksum_TEXT": "abc123def456gh789xyz012lkj345mno678qrs901tuv234wxy567z89" }, { "FileName_TEXT": "coverletter.docx", "FileType_TEXT": "application/vnd.openxmlformats-officedocument.wordprocessingml.document", "FileSize_NUMB": 22222, "FilePath_TEXT": "/uploads/coverletter.docx", "Checksum_TEXT": "zxc987vbn654lkj321qwe000rty123uio456asd789fgh234jkl567mno" } ]'; EXEC usp_MessageAttachment_Insert_S1 @Ai_Message_ID = 20, @As_Attachments_JSON = @As_Attachments_JSON, @Ai_CreatedBy_ID = 1, @Ai_TransactionSeqEvent_NUMB = 1, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorDescription;
usp_Case_CreateNew_S1 | DECLARE @Li_Case_ID INT, @Lc_Msg_CODE CHAR(1), @Ls_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_Case_CreateNew_S1 @Ai_Applicant_ID = 32, @Ai_User_ID = 2017, @Ac_CaseType_CODE = 'R', @Ac_EligibilityDetermined_CODE = 'Y', -- JSON for WIOA Programs @As_WIOAPrograms_JSON = N'[{"WIOAProgram_CODE":"AD"},{"WIOAProgram_CODE":"IN"},{"WIOAProgram_CODE":"NG"}]', -- High + Low → Priority = 'H' -- JSON for Barriers (optional example) @As_Barriers_JSON = N'[{"Barrier_CODE":"DI"},{"Barrier_CODE":"FY"}]', -- JSON for Case Documents (optional example) @As_CaseDocuments_JSON = NULL, -- Optional Case Manager Assignment @Ai_Worker_ID = 2066, @Ad_AssignmentStart_DTTM = '2025-06-02', @Ac_AssignmentStatus_CODE = 'A', -- Transaction tracking @An_TransactionSeqEvent_NUMB = 1, -- Creator @Ai_CreatedBy_ID = 1, -- Outputs @Ai_Case_ID = @Li_Case_ID OUTPUT, @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; -- Result SELECT @Li_Case_ID AS Case_ID, @Lc_Msg_CODE AS Msg_CODE, @Ls_DescriptionError_TEXT AS DescriptionError_TEXT; SELECT * FROM CASES select * from Notification select * from NotificationTemplate
usp_Delete_Notification_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Delete_Notification_S1 @Ai_Notification_ID = 1, @Ai_SignedOnuser_ID = 1, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS MsgText;
usp_DashboardQuickNav_GetList_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_DashboardQuickNav_GetList_S1 @Ac_UserType_CODE = 'c', @Ac_Screen_CODE = 'CSM', @Ai_SignedOnUser_ID = 1, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- See what the proc returned SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS MsgText;
Job$SpAddJobInvitation | DECLARE @Ai_JobInvitation_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpAddJobInvitation @Ai_User_ID = 2065, -- Candidate User_ID @Ai_Job_ID = 47, -- Job ID @As_Notes_TEXT = N'We think you’re a great fit. Let’s talk!', -- Notes @Ad_Expires_DTTM = '2025-07-04', -- 7 days from now @Ai_CreatedBy_ID = 2068, -- Employer User_ID @Ai_TransactionSeqEvent_NUMB = 1, -- Static or dynamic tracking # @Ai_JobInvitation_ID = @Ai_JobInvitation_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View results SELECT @Ai_JobInvitation_ID AS JobInvitation_ID, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS Error_Description;
Job$SpApplyJob | DECLARE @Ai_JobApplication_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpApplyJob @Ai_Job_ID = 47, -- Job being applied to @Ai_User_ID = 2065, -- User applying @Ai_Resume_ID = 10, -- Resume ID owned by user @As_CoverLetter_TEXT = N'I am excited to apply for this opportunity. Please find my resume attached.', @As_AdditionalQuestions_JSON = N'[ {"Question_ID": 1, "Answer_TEXT": "Yes, I can relocate."}, {"Question_ID": 2, "Answer_TEXT": "I have 3 years of experience in this domain."} ]', @As_FormResponses_JSON = N'[ {"Field_ID": 10, "Response_TEXT": "MBA Graduate"}, {"Field_ID": 11, "Response_TEXT": "Available immediately"} ]', @Ai_JobInvitation_ID = NULL, -- if not invited, pass NULL @Ai_CreatedBy_ID = 2065, -- typically same as user_id here @Ai_TransactionSeqEvent_NUMB = 1, -- your seq tracking @Ai_JobApplication_ID = @Ai_JobApplication_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ai_JobApplication_ID AS JobApplication_ID, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS Description;
Job$SpUpdateJobApplicationStatus | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobApplicationStatus @Ai_JobApplication_ID = 8, -- ID of the application you're updating @Ac_Status_CODE = 'REJ', -- Status code: 'REJ', 'WTD', 'SHL', etc. @As_Reason_TEXT = 'Not a good fit based on experience.', -- Optional reason for status update @Ai_UpdatedBy_ID = 2068, -- User ID of the person updating the status @Ai_OldTransactionSeqEvent_NUMB = 1, -- The current/last known Tx Seq Number (for concurrency check) @Ai_NewTransactionSeqEvent_NUMB = 1, -- New Seq Number to log this update @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS Description;
Job$SpUpdateJobApplicationStatus | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobApplicationStatus @Ai_JobApplication_ID = 8, -- ID of the application you're updating @Ac_Status_CODE = 'SHL', -- Status code: 'REJ', 'WTD', 'SHL', etc. @As_Reason_TEXT = 'Not a good fit based on experience.', -- Optional reason for status update @Ai_UpdatedBy_ID = 2068, -- User ID of the person updating the status @Ai_OldTransactionSeqEvent_NUMB = 1, -- The current/last known Tx Seq Number (for concurrency check) @Ai_NewTransactionSeqEvent_NUMB = 1, -- New Seq Number to log this update @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS Description;
usp_Get_Notifications_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Get_Notifications_S1 @As_Search_TEXT = null -- optional search string (can be NULL) , @Ac_ReadFilter_CODE = 'A' -- 'A' for All, 'U' for Unread, 'R' for Read , @Ai_PageNumber = 1 -- page number for pagination , @Ai_PageSize = 10 -- number of rows per page , @Ai_Organization_ID = NULL , @Ai_SignedOnUser_ID = 2065 -- the user ID whose notifications are being fetched , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT , @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorDescription;
Job$SpAddJobOffer | DECLARE @Ai_Offer_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpAddJobOffer @Ai_JobApplication_ID = 8 -- replace with valid JobApplication_ID ,@As_OfferDetails_TEXT = N'We are excited to offer you this role at our company.' ,@As_OfferBenefits_JSON = N'{ "health": "yes", "pto": "15 days" }' ,@Ad_Start_DATE = '2025-06-10' ,@Ad_End_DATE = '2026-06-10' ,@Ad_Expired_DTTM = '2025-06-20 23:59:59' ,@As_SalaryRange_TEXT = N'$70,000 - $90,000' ,@Ai_Salary_NUMB = 85000.00 ,@As_PayPeriod_CODE = 'M' -- Assuming 'M' means Monthly ,@As_AdditionalInfo_TEXT = N'Please respond within 7 days.' ,@Ai_ExpectedHoursPerWeek_NUMB = 40 ,@Ac_Status_CODE = 'P' -- 'P' for Pending ,@Ai_CreatedBy_ID = 1 -- Replace with Employer user ID ,@Ai_TransactionSeqEvent_NUMB = 1 -- Replace with current transaction number ,@Ai_Offer_ID = @Ai_Offer_ID OUTPUT ,@Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT ,@As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output check SELECT @Ai_Offer_ID AS Offer_ID, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
Job$SpUpdateJobOfferStatus | DECLARE @Ac_Msg_CODE CHAR(5); DECLARE @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobOfferStatus @Ai_Offer_ID = 23, -- 🔁 Replace with actual Offer_ID @Ac_Status_CODE = 'A', -- ✅ Example: 'A' = Accepted, 'R' = Rejected @Ai_OldTransactionSeqEvent_NUMB = 1, -- 🔁 Replace with actual old Seq number @Ai_UpdatedBy_ID = 2065, -- 🔁 ID of the user updating the status @Ai_NewTransactionSeqEvent_NUMB = 1, -- 🔁 Replace with new Seq number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 🧾 Check Output SELECT MsgCode = @Ac_Msg_CODE, ErrorDescription = @As_DescriptionError_TEXT;
DECLARE @Ac_Msg_CODE CHAR(5); DECLARE @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobOfferStatus @Ai_Offer_ID = 23, -- 🔁 Replace with actual Offer_ID @Ac_Status_CODE = 'A', -- ✅ Example: 'A' = Accepted, 'R' = Rejected @Ai_OldTransactionSeqEvent_NUMB = 1, -- 🔁 Replace with actual old Seq number @Ai_UpdatedBy_ID = 2065, -- 🔁 ID of the user updating the status @Ai_NewTransactionSeqEvent_NUMB = 1, -- 🔁 Replace with new Seq number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 🧾 Check Output SELECT MsgCode = @Ac_Msg_CODE, ErrorDescription = @As_DescriptionError_TEXT;
Timesheet$sp_updateTimesheetstatus | DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT NVARCHAR(200); EXEC dbo.Timesheet$sp_updateTimesheetstatus @Ai_Timesheet_ID = 5, -- 🔁 Replace with actual Timesheet ID @Ai_Reviewer_ID = 2068, -- 🔁 ID of the person reviewing the timesheet @Ac_status_CODE = 'R', -- ✅ 'A' for Approve, 'R' for Reject @As_RejectedReason_TEXT = 'Invalid hours', -- 🔁 Only required when status is 'R' @Ab_Approveall_INDC = 0, -- ✅ 1 = bulk approve, 0 = update one @Ai_SignedOnUser_ID = 2068, -- 🔁 User who's logged in and doing the update @Ai_TransactionSeqEvent_NUMB = 1, -- 🔁 Current unique event number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the result SELECT MsgCode = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
Job$SpUpdateJobContractStatus | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobContractStatus @Ai_Contract_ID = 7, -- 🔁 Replace with actual Contract_ID @As_Status_CODE = 'A', -- 🔁 'P', 'R', or 'E' @Ai_OldTransactionSeqEvent_NUMB = 1, -- 🔁 Existing transaction number in the row @Ai_UpdatedBy_ID = 2065, -- 🔁 User making the update @Ai_NewTransactionSeqEvent_NUMB = 1, -- 🔁 New unique transaction number @Ai_SignedOnuser_ID = 2065, -- 🔁 Same as above or another user @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Job$SpAddJobContractBonus | DECLARE @Ai_JobContractBonus_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpAddJobContractBonus @Ai_SignedOnUser_ID = 2068, -- Replace with valid User_ID @Ai_ContractBonus_ID = NULL, -- NULL for insert, or existing ID for update @Ai_Contract_ID = 7, -- Replace with valid Contract_ID @Ai_BonusAmount_NUMB = 5000, -- Bonus amount @Ai_TransactionSeqEvent_NUMB = 1, -- Let proc handle it or pass existing @Ai_JobContractBonus_ID = @Ai_JobContractBonus_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ai_JobContractBonus_ID AS JobContractBonus_ID, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
usp_Applicant_Insert_S1 | DECLARE @Ai_Applicant_ID INT, @Ai_User_ID INT, @Ai_Case_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Applicant_Insert_S1 @As_FirstName_TEXT = 'new', @As_MiddleName_TEXT = 'App', @As_LastName_TEXT = 'test', @Ad_DateOfBirth_DATE = '1995-07-20', @As_SocialSecurityNumber_TEXT = '134-23-5867', @As_Gender_CODE = 'M', @Ab_WorkAuthorization_INDC = 1, @As_EmploymentStatus_CODE = 'E', @Ab_LaidOffOrTerminated_INDC = 0, @Ab_ReceivingUI_INDC = 0, @Ab_VeteranOrSpouse_INDC = 0, @Ab_CriminalJustice_INDC = 0, @Ab_SeasonalAgriculturalWork_INDC = 0, @Ab_AmericanIndian_INDC = 0, @Ab_RegisteredApprenticeship_INDC = 0, @Ab_ResidentialEducation_INDC = 0, @Ab_TradeTraining_INDC = 0, @As_LowIncome_CODE = 'Y', @Ab_NeedHelpTraining_INDC = 1, @As_HighSchoolDiplomaOrGED_CODE = 'Y', @As_PhoneNumber_TEXT = '(585) 123-4567', @As_EmailAddress_TEXT='As@email.com', @As_PublicAssistance_JSON = N'[{"Benefit_CODE":"S"},{"Benefit_CODE":"T"}]', @As_Barriers_JSON = N'[{"Barrier_CODE":"BS"},{"Barrier_CODE":"HM"}]', @As_Documents_JSON = N'[{"DocumentType_CODE":"SS","FileName_TEXT":"Driver License","FilePath_TEXT":"https://fileupload.com/dl1.pdf","FileSize_NUMB":"20","FileType_TEXT":"pdf"}]', @As_Res_AddressLine1_TEXT = '123 Main St', @As_Res_AddressLine2_TEXT = NULL, @As_Res_AdditionalInfo_TEXT = NULL, @Ac_Res_State_CODE = 'CA', @As_Res_CityName_TEXT='Callosoia', @As_Res_Zip_TEXT = '75001', @As_Res_CountyName_TEXT='Refer', @Ac_Res_Country_CODE = 'AD', @As_Mail_AddressLine1_TEXT = '456 Elm St', @As_Mail_AddressLine2_TEXT = NULL, @As_Mail_AdditionalInfo_TEXT = NULL, @As_Mail_CityName_TEXT ='Lewwnark', @Ac_Mail_State_CODE = 'CA', @As_Mail_Zip_TEXT = '75001', @As_Mail_CountyName_TEXT='Alaska', @Ac_Mail_Country_CODE = 'US', @Ab_ConsentConfirmed_INDC = 1, @As_Signature_TEXT = 'John DoeBBBB', @As_SignatureDocURL_TEXT = 'https://fileupload.com/signature.pdf', @Ai_CreatedBy_ID=1, @Ai_TransactionSeqEvent_NUMB = NULL, @Ai_Applicant_ID = @Ai_Applicant_ID OUTPUT, @Ai_User_ID =@Ai_User_ID OUTPUT, @Ai_Case_ID=@Ai_Case_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; select @Ai_Applicant_ID AS Applicant_ID, @Ac_Msg_CODE AS Msg_Code, @As_DescriptionError_TEXT AS Error_Description;
usp_OrganizationAddress_Add_S1 | DECLARE @Ai_OrganizationAddress_ID INT, @Ai_Address_ID INT, @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_TransactionSeqEvent_NUMB INT = NULL; -- Let it generate if not provided EXEC dbo.usp_OrganizationAddress_Add_S1 @Ai_Organization_ID = 1, @As_AddressLine1_TEXT = '123 Main Street', @Ac_AddressType_CODE = 'H', -- example: 'H' for Headquarters or whatever your ref type is @As_AddressLine2_TEXT = 'Suite 500', @As_AdditionalInfo_TEXT = 'Building 3', @Ai_City_ID = 1, @Ac_State_CODE = 'CA', @As_Zip_TEXT = '75001', @AC_County_CODE = '001', @Ac_Country_CODE = 'US', @Ab_IsPrimary_INDC = 1, @Ai_CreatedBy_ID = 1, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ai_OrganizationAddress_ID = @Ai_OrganizationAddress_ID OUTPUT, @Ai_Address_ID = @Ai_Address_ID OUTPUT, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: Check outputs SELECT @Ai_OrganizationAddress_ID AS OrganizationAddress_ID, @Ai_Address_ID AS Address_ID, @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS Error_Description;
usp_Insert_Organization_Details_S1 | DECLARE @Ai_Organization_ID INT, @Ai_OrganizationAddress_ID INT, @Ai_OrganizationMember_ID INT, @Ai_User_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Insert_Organization_Details_S1 -- Organization Details @As_OrganizationName_TEXT = N'FutureTech Solutions', @As_EmailAddress_TEXT = 'contact@futuretech.com', @As_OrganizationDesc_TEXT = N'An innovative tech startup focused on AI solutions.', @As_WebsiteUrl_TEXT = N'https://futuretech.com', @Ac_OrganizationType_CODE = 'ST', -- Assuming 'ST' for Startup @Ac_Status_CODE = 'A', @Ac_RecruitmentStatus_CODE = 'O', -- O = Open @As_LogoURL_TEXT = 'https://cdn.futuretech.com/logo.png', @As_size_text = N'11-50 employees', @Ac_AddressType_CODE = 'H', @As_AddressLine1_TEXT = N'123 Innovation Drive', @As_AddressLine2_TEXT = N'Suite 456', @Ai_City_ID = 1, @Ac_State_CODE = 'CA', @As_PostalCode_TEXT = N'94016', @Ac_County_CODE = '001', @Ac_Country_CODE = 'US', @An_Latitude_DECIMAL = 37.7749, @An_Longitude_DECIMAL = -122.4194, @Ab_IsPrimary_INDC = 1, -- Member @As_UserName_TEXT = 'futuretech_admin', @Ac_MemberRole_CODE = 'A', @Ad_StartDate_DATE = '10-06-2025', @Ad_EndDate_DATE = NULL, -- Certification JSON (Optional) @As_OrganizationCertification_JSON = N'[ { "CertificationName_TEXT": "ISO 27001", "CertificationDesc_TEXT": "Information security management certification", "CertificationYear_NUMB": 2023 }, { "CertificationName_TEXT": "SOC 2", "CertificationDesc_TEXT": "Data security compliance for SaaS providers", "CertificationYear_NUMB": 2022 } ]', -- Tracking @Ai_CreatedBy_ID = 1, @Ai_TransactionSeqEvent_NUMB = NULL, -- Will be handled inside proc -- Outputs @Ai_Organization_ID = @Ai_Organization_ID OUTPUT, @Ai_OrganizationAddress_ID = @Ai_OrganizationAddress_ID OUTPUT, @Ai_OrganizationMember_ID = @Ai_OrganizationMember_ID OUTPUT, @Ai_User_ID = @Ai_User_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 👀 Result SELECT @Ai_Organization_ID AS Organization_ID, @Ai_OrganizationAddress_ID AS OrganizationAddress_ID, @Ai_OrganizationMember_ID AS OrganizationMember_ID, @Ai_User_ID AS User_ID, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
usp_UserAddress_Add_S2 | DECLARE @Ai_User_ID INT = 2071, -- Replace with actual User_ID @As_AddressLine1_TEXT VARCHAR(250) = '123 Main Street', @As_AddressLine2_TEXT VARCHAR(250) = 'Apt 4B', @As_AdditionalInfo_TEXT VARCHAR(250) = 'Near Park', @Ai_City_ID INT = 1, -- Replace with valid City_ID @Ac_State_CODE CHAR(2) = 'CA', @As_Zip_TEXT VARCHAR(20) = '10001', @As_County_CODE VARCHAR(10) = '001', @Ac_Country_CODE CHAR(2) = 'US', @Ac_AddressType_CODE CHAR(1) = 'R', -- 'R' for Residential, 'M' for Mailing @Ai_CreatedBy_ID INT = 1, @Ai_TransactionSeqEvent_NUMB INT = 1, -- Replace with actual Transaction Event Number @Ai_UserAddress_ID INT, @Ai_Address_ID INT, @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_UserAddress_Add_S2 @Ai_User_ID, @As_AddressLine1_TEXT, @As_AddressLine2_TEXT, @As_AdditionalInfo_TEXT, @Ai_City_ID, @Ac_State_CODE, @As_Zip_TEXT, @As_County_CODE, @Ac_Country_CODE, @Ac_AddressType_CODE, @Ai_CreatedBy_ID, @Ai_TransactionSeqEvent_NUMB, @Ai_UserAddress_ID OUTPUT, @Ai_Address_ID OUTPUT, @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ai_UserAddress_ID AS UserAddress_ID, @Ai_Address_ID AS Address_ID, @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS Description;
usp_User_Add_S1 | DECLARE @Ai_User_ID INT, @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_User_Add_S1 @Ai_Applicant_ID = NULL, -- or pass actual Applicant ID @As_Username_TEXT = 'nithu.dev', -- optional, can be NULL to auto-generate @As_FirstName_TEXT = 'Nithu', @As_MiddleName_TEXT = NULL, @As_LastName_TEXT = 'Developer', @Ad_BirthDate_DATE = '1990-06-10', @Ac_SSN_TEXT = N'123456789', -- must be ###-##-#### @Ac_Gender_CODE = 'M', -- assuming 'M' is valid in RefGender @As_EmailAddress_TEXT = 'nithu@example.com', @As_PhoneNumber_TEXT = '555-123-4567', @As_Passwordhash_TEXT = NULL, -- optional, pass if available @As_PasswordSalt_TEXT = NULL, -- optional, pass if available @As_Reference_ID = 'REF001', @Ac_UserType_CODE = 'U', -- example user type code, must exist in RefUserType @Ai_CreatedBy_ID = 1, -- ID of the creator user @Ai_TransactionSeqEvent_NUMB = NULL, -- NULL to auto-generate @Ai_User_ID = @Ai_User_ID OUTPUT, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check results: SELECT @Ai_User_ID AS NewUserID, @Ac_Msg_Code AS MessageCode, @As_DescriptionError_TEXT AS MessageDescription;
usp_Applicant_Insert_S1 | DECLARE @Ai_Applicant_ID INT, @Ai_User_ID INT, @Ai_Case_ID INT, @Ai_TransactionSeqEvent_NUMB BIGINT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Applicant_Insert_S1 @As_FirstName_TEXT = 'Finals', @As_MiddleName_TEXT = 'Apps', @As_LastName_TEXT = 'tests', @Ad_DateOfBirth_DATE = '1985-10-25', @As_SocialSecurityNumber_TEXT = '123-45-6789', @As_Gender_CODE = 'M', @Ab_WorkAuthorization_INDC = 1, @As_EmploymentStatus_CODE = 'E', @Ab_LaidOffOrTerminated_INDC = 0, @Ab_ReceivingUI_INDC = 0, @Ab_VeteranOrSpouse_INDC = 0, @Ab_CriminalJustice_INDC = 0, @Ab_SeasonalAgriculturalWork_INDC = 0, @Ab_AmericanIndian_INDC = 0, @Ab_RegisteredApprenticeship_INDC = 0, @Ab_ResidentialEducation_INDC = 0, @Ab_TradeTraining_INDC = 0, @As_LowIncome_CODE = 'N', @Ab_NeedHelpTraining_INDC = 0, @As_HighSchoolDiplomaOrGED_CODE = 'Y', @As_PhoneNumber_TEXT = '5551234567', @As_EmailAddress_TEXT = 'filetest2@example.com', @As_PublicAssistance_JSON = N'[{"Benefit_CODE":"S"}, {"Benefit_CODE":"T"}]', @As_Barriers_JSON = N'[{"Barrier_CODE":"BS"}]', @As_Documents_JSON = N'[{"DocumentType_CODE":"SS","FileName_TEXT":"social_security_card.pdf","FilePath_TEXT":"/uploads/applicant_docs/","FileSize_NUMB":20,"FileType_TEXT":"pdf"}]', @As_Res_AddressLine1_TEXT = '123 Main St', @As_Res_AddressLine2_TEXT = NULL, @As_Res_AdditionalInfo_TEXT = NULL, @Ac_Res_State_CODE = 'AL', @As_Res_CityName_TEXT = 'New York', -- You must ensure this city exists in RefCity @As_Res_Zip_TEXT = '36003', @As_Res_CountyName_TEXT = 'Autauga County', -- Match this with RefCounty @Ac_Res_Country_CODE = 'US', @As_Mail_AddressLine1_TEXT = '123 Main St', @As_Mail_AddressLine2_TEXT = NULL, @As_Mail_AdditionalInfo_TEXT = NULL, @As_Mail_CityName_TEXT = 'New York', @Ac_Mail_State_CODE = 'AL', @As_Mail_Zip_TEXT = '90001', @As_Mail_CountyName_TEXT = 'Autauga County', @Ac_Mail_Country_CODE = 'US', @Ab_ConsentConfirmed_INDC = 1, @As_Signature_TEXT = 'John DoeTY', @As_SignatureDocURL_TEXT = 'http://example.com/signature.pdf', @Ai_CreatedBy_ID = 2099, @Ai_TransactionSeqEvent_NUMB = NULL, @Ai_Applicant_ID = @Ai_Applicant_ID OUTPUT, @Ai_User_ID = @Ai_User_ID OUTPUT, @Ai_Case_ID = @Ai_Case_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Final Output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @Ai_Applicant_ID AS ApplicantID, @Ai_User_ID AS UserID, @Ai_Case_ID AS CaseID;
usp_ReviewApplication_GetList_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ReviewApplication_GetList_S1 @As_SearchText = null, -- Search text (nullable) @As_Status = 'P', -- Status code filter (nullable) @As_Program_CODE = null, -- Program code filter (nullable) @As_SortColumn = 'Created_DTTM', -- Sort column, default 'Created_DTTM' @As_SortOrder = 'DESC', -- Sort order, 'ASC' or 'DESC' @Ai_From_numb = 1, -- Page number for pagination @Ai_To_Numb = 10, -- Number of rows per page @Ai_SignedOnUser_ID = 2066, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output status: SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantEligibleProgram_AddAll_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantEligibleProgram_AddAll_S1 @Ai_Applicant_ID = 50, @Ab_RecentDisaster_INDC = 0, @Ab_AdminEnroll_INDC = 0, @Ai_UpdatedBy_ID = 1, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_Applicant_UpdateBase_S1 | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.usp_Applicant_UpdateBase_S1 @Ai_Applicant_ID = 235, @As_FirstName_TEXT = 'John', @As_MiddleName_TEXT = 'M', @As_LastName_TEXT = 'Doe', @Ad_DateOfBirth_DATE = '1990-05-12', @As_SocialSecurityNumber_TEXT= '123-45-6789', @As_Gender_CODE = 'M', @Ab_WorkAuthorization_INDC = 1, @As_EmploymentStatus_CODE = 'E', @Ab_LaidOffOrTerminated_INDC = 0, @Ab_ReceivingUI_INDC = 0, @Ab_VeteranOrSpouse_INDC = 0, @Ab_CriminalJustice_INDC = 0, @Ab_SeasonalAgriculturalWork_INDC = 0, @Ab_AmericanIndian_INDC = 0, @Ab_RegisteredApprenticeship_INDC = 0, @Ab_ResidentialEducation_INDC = 0, @Ab_TradeTraining_INDC = 0, @As_LowIncome_CODE = 'Y', @Ab_NeedHelpTraining_INDC = 1, @As_HighSchoolDiplomaOrGED_CODE = 'Y', -- New params @As_EmailAddress_TEXT = null, @As_PhoneNumber_TEXT = '555-123-4567', @Ab_SelectiveService_INDC = 1, @Ab_TwoFactorEnabled_INDC = 0, @As_LogoURL_TEXT = 'https://example.com/profilepic.jpg', @As_PublicAssistance_JSON = N'[{"Benefit_CODE":"S"}, {"Benefit_CODE":"T"}]', @As_Barriers_JSON = N'[{"Barrier_CODE":"BS"}]', @Ai_UpdatedBy_ID = 1, @An_OldTransactionSeqEvent_NUMB = 1173, @An_NewTransactionSeqEvent_NUMB = 1173, -- OUTPUT params @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
usp_Applicant_UpdateStatus_S1 | DECLARE @Ai_RowsAffected INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.usp_Applicant_UpdateStatus_S1 @Ai_ApplicantID = 13, @Ab_IsReapply_INDC=0,-- Replace with real applicant ID @As_ApplicantStatus_CODE = 'D', -- For example: 'R' for Rejected, 'I' for Incomplete, etc. @As_CancelReason_TEXT = 'I need more contact information', -- Reason text if status is 'I' or 'R' @Ai_UpdatedBy_ID = 12, -- Replace with actual user ID @An_OldTransactionSeqEvent_NUMB = 30, -- Replace with real old transaction number @An_NewTransactionSeqEvent_NUMB = 1, -- Replace with new transaction number @Ai_RowsAffected = @Ai_RowsAffected OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Debug prints PRINT 'Rows Affected: ' + CAST(@Ai_RowsAffected AS VARCHAR); PRINT 'Msg Code: ' + @Ac_Msg_CODE; PRINT 'Error/Status Message: ' + ISNULL(@As_DescriptionError_TEXT, 'No message');
usp_Message_ReadStatus_Update_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_Message_ReadStatus_Update_S1 @As_MessageIDs_JSON = NULL, -- Example JSON array of message IDs @Ai_Conversation_ID = 17, -- Example conversation ID @Ai_UpdatedBy_ID = 1, -- The user who marked as read @An_TransactionSeqEvent_NUMB = 1, -- Transaction sequence number @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results PRINT 'Message Code: ' + @Ac_Msg_Code; PRINT 'Description: ' + ISNULL(@As_DescriptionError_TEXT, 'No message');
dbo.Organization$SpGetOrganizationDetails | DECLARE @Ai_Organization_ID INT = 1, -- Replace with actual Organization ID -- Output variables @As_OrganizationName_TEXT NVARCHAR(200), @As_OrganizationDesc_TEXT NVARCHAR(1000), @As_WebsiteUrl_TEXT NVARCHAR(255), @Ac_OrganizationType_CODE CHAR(2), @As_OrganizationTypeDesc_TEXT NVARCHAR(50), @Ac_RecruitmentStatus_CODE CHAR(1), @As_RecruitmentStatusDesc_TEXT NVARCHAR(20), @Ac_Status_CODE CHAR(1), @As_StatusDesc_TEXT NVARCHAR(50), @As_LogoURL_TEXT NVARCHAR(1500), @As_Size_TEXT NVARCHAR(255), @As_EmailAddress_TEXT NVARCHAR(255), @As_PrimaryPhone_TEXT NVARCHAR(50), @Ai_CreatedBy_ID INT, @As_CreatedByName_TEXT NVARCHAR(200), @Ad_Created_DTTM DATETIME, @Ai_UpdatedBy_ID INT, @As_UpdatedByName_TEXT NVARCHAR(200), @Ad_Updated_DTTM DATETIME, @An_TransactionSeqEvent_NUMB BIGINT, @Ai_ActiveContractsCount_NUMB INT, @An_AvgDaysToFillPosition_NUMB INT, @An_OverallRating_NUMB DECIMAL(3, 2), @As_Ratings_TEXT NVARCHAR(50), @An_ReviewCount_NUMB INT, @As_AddressesJSON_TEXT NVARCHAR(MAX), @As_ContactsJSON_TEXT NVARCHAR(MAX), @As_CertificationsJSON_TEXT NVARCHAR(MAX), @As_ProfileCompletionJSON_TEXT NVARCHAR(MAX), @An_JobCount_NUMB int, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); -- Execute the stored procedure EXEC dbo.Organization$SpGetOrganizationDetails @Ai_Organization_ID = @Ai_Organization_ID, @As_OrganizationName_TEXT = @As_OrganizationName_TEXT OUTPUT, @As_OrganizationDesc_TEXT = @As_OrganizationDesc_TEXT OUTPUT, @As_WebsiteUrl_TEXT = @As_WebsiteUrl_TEXT OUTPUT, @Ac_OrganizationType_CODE = @Ac_OrganizationType_CODE OUTPUT, @As_OrganizationTypeDesc_TEXT = @As_OrganizationTypeDesc_TEXT OUTPUT, @Ac_RecruitmentStatus_CODE = @Ac_RecruitmentStatus_CODE OUTPUT, @As_RecruitmentStatusDesc_TEXT = @As_RecruitmentStatusDesc_TEXT OUTPUT, @Ac_Status_CODE = @Ac_Status_CODE OUTPUT, @As_StatusDesc_TEXT = @As_StatusDesc_TEXT OUTPUT, @As_LogoURL_TEXT = @As_LogoURL_TEXT OUTPUT, @As_Size_TEXT = @As_Size_TEXT OUTPUT, @As_EmailAddress_TEXT = @As_EmailAddress_TEXT OUTPUT, @As_PrimaryPhone_TEXT = @As_PrimaryPhone_TEXT OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @As_CreatedByName_TEXT = @As_CreatedByName_TEXT OUTPUT, @Ad_Created_DTTM = @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @As_UpdatedByName_TEXT = @As_UpdatedByName_TEXT OUTPUT, @Ad_Updated_DTTM = @Ad_Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ai_ActiveContractsCount_NUMB = @Ai_ActiveContractsCount_NUMB OUTPUT, @An_AvgDaysToFillPosition_NUMB = @An_AvgDaysToFillPosition_NUMB OUTPUT, @An_OverallRating_NUMB = @An_OverallRating_NUMB OUTPUT, @As_Ratings_TEXT = @As_Ratings_TEXT OUTPUT, @An_ReviewCount_NUMB = @An_ReviewCount_NUMB OUTPUT, @As_AddressesJSON_TEXT = @As_AddressesJSON_TEXT OUTPUT, @As_ContactsJSON_TEXT = @As_ContactsJSON_TEXT OUTPUT, @As_CertificationsJSON_TEXT = @As_CertificationsJSON_TEXT OUTPUT, @As_ProfileCompletionJSON_TEXT = @As_ProfileCompletionJSON_TEXT OUTPUT, @An_JobCount_NUMB = @An_JobCount_NUMB output, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display results SELECT @Ac_Msg_CODE AS ResultCode, @As_DescriptionError_TEXT AS Message, @As_OrganizationName_TEXT AS OrganizationName, @As_OrganizationDesc_TEXT AS OrganizationDescription, @As_WebsiteUrl_TEXT AS WebsiteUrl, @Ac_OrganizationType_CODE AS OrganizationTypeCode, @As_OrganizationTypeDesc_TEXT AS OrganizationTypeDescription, @Ac_RecruitmentStatus_CODE AS RecruitmentStatusCode, @As_RecruitmentStatusDesc_TEXT AS RecruitmentStatusDescription, @Ac_Status_CODE AS StatusCode, @As_StatusDesc_TEXT AS StatusDescription, @As_LogoURL_TEXT AS LogoUrl, @As_Size_TEXT AS Size, @As_EmailAddress_TEXT AS EmailAddress, @As_PrimaryPhone_TEXT AS PrimaryPhone, @Ai_CreatedBy_ID AS CreatedByID, @As_CreatedByName_TEXT AS CreatedByName, @Ad_Created_DTTM AS CreatedDate, @Ai_UpdatedBy_ID AS UpdatedByID, @As_UpdatedByName_TEXT AS UpdatedByName, @Ad_Updated_DTTM AS UpdatedDate, @An_TransactionSeqEvent_NUMB AS TransactionSequence, @Ai_ActiveContractsCount_NUMB AS ActiveContractsCount, @An_AvgDaysToFillPosition_NUMB AS AvgDaysToFillPosition, @An_OverallRating_NUMB AS OverallRating, @As_Ratings_TEXT AS RatingsText, @An_ReviewCount_NUMB AS ReviewCount, @As_AddressesJSON_TEXT AS AddressesJSON, @As_ContactsJSON_TEXT AS ContactsJSON, @As_CertificationsJSON_TEXT AS CertificationsJSON, @As_ProfileCompletionJSON_TEXT AS ProfileCompletionJSON, @An_JobCount_NUMB AS jobcount ;
dbo.Review$GetAllByUserAndOrganization | /* Example 1: Get candidate reviews (user reviews with type 'C')*/ DECLARE @OverallRating DECIMAL(3, 2) DECLARE @ReviewCount INT DECLARE @MsgCode CHAR(5) DECLARE @ErrorDesc NVARCHAR(4000) -- Execute for user reviews (type 'C') EXEC dbo.Review$GetAllByUserAndOrganization @Ai_User_ID = 2, -- Specific user ID @Ai_Organization_ID = NULL, -- NULL to get only user reviews @As_OverallRating_NUMB = @OverallRating OUTPUT, @An_ReviewCount_NUMB = @ReviewCount OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT -- Display output parameters for user reviews SELECT @OverallRating AS OverallRating, @ReviewCount AS ReviewCount, @MsgCode AS MessageCode, @ErrorDesc AS ErrorDescription, 'Candidate Reviews' AS ReviewType -- Example 2: Get organization reviews (type 'O') DECLARE @OrgOverallRating DECIMAL(3, 2) DECLARE @OrgReviewCount INT DECLARE @OrgMsgCode CHAR(5) DECLARE @OrgErrorDesc NVARCHAR(4000) -- Execute for organization reviews (type 'O') EXEC dbo.Review$GetAllByUserAndOrganization @Ai_User_ID = NULL, -- NULL to get only org reviews @Ai_Organization_ID = 1, -- Specific organization ID @As_OverallRating_NUMB = @OrgOverallRating OUTPUT, @An_ReviewCount_NUMB = @OrgReviewCount OUTPUT, @Ac_Msg_CODE = @OrgMsgCode OUTPUT, @As_DescriptionError_TEXT = @OrgErrorDesc OUTPUT -- Display output parameters for organization reviews SELECT @OrgOverallRating AS OverallRating, @OrgReviewCount AS ReviewCount, @OrgMsgCode AS MessageCode, @OrgErrorDesc AS ErrorDescription, 'Organization Reviews' AS ReviewType -- Example 3: Get both user and org reviews (if needed) -- Note: This would require modifying the procedure to handle both simultaneously -- Currently the procedure filters for one type at a time
Job$SpSearchJobs | -- Declare output variables DECLARE @MsgCode CHAR(5), @ErrorDesc NVARCHAR(4000); -- Execute the stored procedure EXEC dbo.Job$SpSearchJobs @Ai_SignedOnUser_ID = 1, @Ai_Client_ID = 1, @Ai_Organization_ID = NULL, @As_Search_TEXT = NULL, @Ac_Status_CODE = NULL, @Ac_JobCategory_CODE = NULL, @Ac_LocationType_CODE = NULL, @Ac_JobType_CODE = NULL, @Ac_EmploymentType_CODE = NULL, @Ac_ExperienceLevel_CODE = NULL, @As_Skill_TEXT = NULL, @Ai_SalaryMin_NUMB = NULL, @Ai_SalaryMax_NUMB = NULL, @Ab_Saved_INDC = 0, @Ab_PostedLastDay_INDC = 0, @Ai_Resume_ID = NULL, @Ai_Job_ID = NULL, @As_Location_TEXT = NULL, @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @As_SortBy_CODE = 'R', @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Output the status SELECT @MsgCode AS MsgCode, @ErrorDesc AS ErrorDescription;
dbo.Organization$SpUpdateOrganizationDetails | DECLARE @Ac_Msg_CODE CHAR(5) DECLARE @As_DescriptionError_TEXT NVARCHAR(4000) DECLARE @An_NewTransactionSeqEvent_NUMB BIGINT -- Sample certification JSON DECLARE @CertificationsJSON NVARCHAR(MAX) = '[ { "CertificationTitle_TEXT": "ISO 9001", "CertificationDesc_TEXT": "Quality Management Certification", "CertificationYear_NUMB": 2023 } ]' -- Sample address JSON DECLARE @AddressesJSON NVARCHAR(MAX) = '[ { "OrganizationAddress_ID": 5, "Address_ID": 10, "AddressType_CODE": "HQ", "AddressLine1_TEXT": "123 Main St", "AddressLine2_TEXT": "Suite 400", "CityName_TEXT": "New York", "State_CODE": "NY", "Country_CODE": "US", "County_CODE": "NYC", "IsPrimary_INDC": true } ]' EXEC dbo.Organization$SpUpdateOrganizationDetails @Ai_Organization_ID = 1, -- Organization ID to update @As_OrganizationName_TEXT = 'Updated Org Name', -- New organization name @As_OrganizationDesc_TEXT = 'Updated description', -- New description @As_WebsiteUrl_TEXT = 'https://updated.org', -- New website URL @Ac_OrganizationType_CODE = 'CO', -- Organization type code @As_Size_TEXT = '500-1000', -- Organization size @As_EmailAddress_TEXT = 'info@updated.org', -- Email address @As_LogoURL_TEXT = 'https://updated.org/logo.png', -- Logo URL @An_OldTransactionSeqEvent_NUMB = 1, -- Previous transaction sequence @An_NewTransactionSeqEvent_NUMB = NULL, -- Will be populated by procedure @Ai_UpdatedBy_ID = 2, -- User ID making the update @As_PrimaryPhone_TEXT = '555-123-4567', -- Primary phone number @As_CertificationsJSON_TEXT = @CertificationsJSON, -- Certifications JSON @As_AddressesJSON_TEXT = @AddressesJSON, -- Addresses JSON @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, -- Output status code @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT -- Output message -- Check the results SELECT @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS Message, @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeq
Profile$Sp_GetEmployerDetails | DECLARE @ResultCode CHAR(1) DECLARE @Message NVARCHAR(200) -- EXECUTE THE PROCEDURE EXEC [dbo].[Profile$Sp_GetEmployerDetails] @Ai_SignedOnUser_ID = 2, -- Replace with actual user ID @Ai_Organization_ID = 1, -- Replace with actual organization ID @Ac_Msg_CODE = @ResultCode OUTPUT, -- Output status code (S=Success, E=Error) @As_DescriptionError_TEXT = @Message OUTPUT -- Output message -- CHECK RESULTS IF @ResultCode = 'S' BEGIN PRINT 'Successfully retrieved employer details' -- The result set will contain the employer details END ELSE BEGIN PRINT 'Error: ' + @Message END
Profile$Sp_UpdateEmployerProfile | DECLARE @MsgCode2 CHAR(1) DECLARE @ErrorDesc2 NVARCHAR(200) EXEC [dbo].[Profile$Sp_UpdateEmployerProfile] @Ai_SignedOnUser_ID = 2, @Ai_Organization_ID = 1, @As_FullName_TEXT = 'John Q. Smith', @As_CompanyName_TEXT = 'Global', @An_OldTransactionSeqEvent_NUMB = 2, @An_NewTransactionSeqEvent_NUMB = 2, @Ac_Msg_CODE = @MsgCode2 OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc2 OUTPUT SELECT @MsgCode2 AS StatusCode, @ErrorDesc2 AS Message
dbo.Org$SpSaveCandidate | DECLARE @SavedCandidate_ID INT DECLARE @Msg_CODE CHAR(5) DECLARE @Error_TEXT NVARCHAR(4000) -- Then execute the unsave operation EXEC dbo.Org$SpSaveCandidate @Ai_CandidateUser_ID = 1, -- Candidate User ID to unsave @Ai_Organization_ID = 1, -- Organization ID unsaving the candidate @Ai_Resume_ID = 2, -- Resume ID of the candidate @Ai_CreatedBy_ID = 101, -- User ID who is performing the unsave @Ai_TransactionSeqEvent_NUMB = 987654322, -- New transaction sequence number @Ab_Save_INDC = 1, -- 0 = Unsave operation @Ai_SavedCandidate_ID = @SavedCandidate_ID OUTPUT, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Error_TEXT OUTPUT SELECT @SavedCandidate_ID AS SavedCandidate_ID, @Msg_CODE AS ResultCode, @Error_TEXT AS ErrorMessage
usp_GetAllCandidatesByOrganization | DECLARE @Msg_CODE CHAR(1) DECLARE @Error_TEXT VARCHAR(4000) EXEC usp_GetAllCandidatesByOrganization @Ai_SignedOnUser_ID = 1, -- Organization/User ID @As_SearchTerm_TEXT = NULL, -- Optional search term @Ai_Job_ID = NULL, -- Optional job ID to match candidates @Ai_RowFrom_NUMB = 1, -- Pagination start @Ai_RowTo_NUMB = 10, -- Pagination end @As_SortBy_CODE = 'relevance', -- Sorting option @As_SkillNameJSON_TEXT ='["teamwork" ,"sql"]', -- JSON array of required skills @Ai_MinExperience_NUMB = 0, -- Minimum years experience @Ai_MaxExperience_NUMB = 10, -- Maximum years experience @As_Location_TEXT = NULL, -- Location filter @Ac_InvitationStatus_CODE = NULL, -- 'S' for saved candidates only @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Error_TEXT OUTPUT -- Check results/errors SELECT @Msg_CODE AS Status, @Error_TEXT AS ErrorMessage
usp_GetCandidateDetails | DECLARE @ResultCode CHAR(1) DECLARE @ErrorMessage VARCHAR(4000) -- OPTION 1: Get candidate details by User_ID (returns primary resume) EXEC [dbo].[usp_GetCandidateDetails] @Ai_User_ID = 2, -- Replace with actual candidate User_ID @Ai_Resume_ID = NULL, -- Not needed when searching by User_ID @Ac_Msg_CODE = @ResultCode OUTPUT, -- Output status code (S=Success, F=Failure) @As_DescriptionError_TEXT = @ErrorMessage OUTPUT -- Check results IF @ResultCode = 'S' PRINT 'Candidate details retrieved successfully' ELSE PRINT 'Error: ' + @ErrorMessage
dbo.Resume$Sp_DownloadResume | DECLARE @Ai_Resume_ID INT = 2; -- Replace with actual resume ID DECLARE @Ai_SignedOnUser_ID INT = 1; -- Replace with actual user ID DECLARE @As_Template_CODE CHAR(2) = 'T3'; DECLARE @As_Format_CODE CHAR(4) = 'PDF'; -- Replace with valid format code (PDF, DOCX, etc.) DECLARE @Ai_CreatedBy_ID INT = 1; -- Replace with creator user ID DECLARE @An_TransactionSeqEvent_NUMB BIGINT = 1; -- Replace with transaction sequence number -- Output parameter declarations DECLARE @Ai_Download_ID INT; DECLARE @As_DownloadTypeName_TEXT NVARCHAR(100); -- Resume detail outputs DECLARE @Ai_User_ID INT ; DECLARE @As_ResumeName_TEXT NVARCHAR(100); DECLARE @Ab_IsPrimary_INDC BIT; DECLARE @As_FullName_TEXT NVARCHAR(100); DECLARE @As_ProfessionalTitle_TEXT NVARCHAR(100); DECLARE @As_Email_TEXT NVARCHAR(100); DECLARE @As_profileURL_TEXT NVARCHAR(100); DECLARE @As_Phone_TEXT NVARCHAR(20); DECLARE @As_Location_TEXT NVARCHAR(100); DECLARE @As_LinkedInURL_TEXT NVARCHAR(200); DECLARE @As_NotableProjects_TEXT NVARCHAR(200); DECLARE @Ac_resumevisibility_CODE CHAR(1); DECLARE @As_ProfessionalSummary_TEXT NVARCHAR(1000); DECLARE @As_HobbiesAndInterests_TEXT NVARCHAR(1000); DECLARE @Ad_Created_DTTM DATETIME; DECLARE @Ai_UpdatedBy_ID INT; DECLARE @Ad_Updated_DTTM DATETIME; DECLARE @As_WorkExperienceJson_TEXT NVARCHAR(MAX); DECLARE @As_EducationJson_TEXT NVARCHAR(MAX); DECLARE @As_CertificationsJson_TEXT NVARCHAR(MAX); DECLARE @As_SkillsJson_TEXT NVARCHAR(MAX); DECLARE @As_LanguagesJson_TEXT NVARCHAR(MAX); DECLARE @As_AwardsJson_TEXT NVARCHAR(MAX); DECLARE @As_ReferencesJson_TEXT NVARCHAR(MAX); DECLARE @As_FreelanceProfilesJson_TEXT NVARCHAR(MAX); DECLARE @As_JobPreferencesJson_TEXT NVARCHAR(MAX); DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT NVARCHAR(200); -- Execute the procedure EXEC dbo.Resume$Sp_DownloadResume @Ai_Resume_ID = @Ai_Resume_ID, @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @As_Template_CODE = @As_Template_CODE, @As_Format_CODE = @As_Format_CODE, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ai_Download_ID = @Ai_Download_ID OUTPUT, @As_DownloadTypeName_TEXT = @As_DownloadTypeName_TEXT OUTPUT, @Ai_User_ID = @Ai_User_ID output , @As_ResumeName_TEXT = @As_ResumeName_TEXT OUTPUT, @Ab_IsPrimary_INDC = @Ab_IsPrimary_INDC OUTPUT, @As_FullName_TEXT = @As_FullName_TEXT OUTPUT, @As_ProfessionalTitle_TEXT = @As_ProfessionalTitle_TEXT OUTPUT, @As_Email_TEXT = @As_Email_TEXT OUTPUT, @As_profileURL_TEXT = @As_profileURL_TEXT OUTPUT, @As_Phone_TEXT = @As_Phone_TEXT OUTPUT, @As_Location_TEXT = @As_Location_TEXT OUTPUT, @As_LinkedInURL_TEXT = @As_LinkedInURL_TEXT OUTPUT, @As_NotableProjects_TEXT = @As_NotableProjects_TEXT OUTPUT, @Ac_resumevisibility_CODE = @Ac_resumevisibility_CODE OUTPUT, @As_ProfessionalSummary_TEXT = @As_ProfessionalSummary_TEXT OUTPUT, @As_HobbiesAndInterests_TEXT = @As_HobbiesAndInterests_TEXT OUTPUT, @Ad_Created_DTTM = @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @Ad_Updated_DTTM = @Ad_Updated_DTTM OUTPUT, @As_WorkExperienceJson_TEXT = @As_WorkExperienceJson_TEXT OUTPUT, @As_EducationJson_TEXT = @As_EducationJson_TEXT OUTPUT, @As_CertificationsJson_TEXT = @As_CertificationsJson_TEXT OUTPUT, @As_SkillsJson_TEXT = @As_SkillsJson_TEXT OUTPUT, @As_LanguagesJson_TEXT = @As_LanguagesJson_TEXT OUTPUT, @As_AwardsJson_TEXT = @As_AwardsJson_TEXT OUTPUT, @As_ReferencesJson_TEXT = @As_ReferencesJson_TEXT OUTPUT, @As_FreelanceProfilesJson_TEXT = @As_FreelanceProfilesJson_TEXT OUTPUT, @As_JobPreferencesJson_TEXT = @As_JobPreferencesJson_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display results SELECT @Ac_Msg_CODE AS ErrorCode, @As_DescriptionError_TEXT AS ErrorMessage, @Ai_Download_ID AS DownloadID, @As_DownloadTypeName_TEXT AS DownloadTypeName; -- Display resume details SELECT @Ai_User_ID AS ResumeHolderID , @As_ResumeName_TEXT AS ResumeName, @Ab_IsPrimary_INDC AS IsPrimary, @As_FullName_TEXT AS FullName, @As_ProfessionalTitle_TEXT AS ProfessionalTitle, @As_Email_TEXT AS Email, @As_profileURL_TEXT AS ProfileURL, @As_Phone_TEXT AS Phone, @As_Location_TEXT AS Location, @As_LinkedInURL_TEXT AS LinkedInURL, @As_NotableProjects_TEXT AS Projects, @Ac_resumevisibility_CODE AS Resumevisibility, @As_ProfessionalSummary_TEXT AS ProfessionalSummary, @As_HobbiesAndInterests_TEXT AS HobbiesAndInterests, @Ai_CreatedBy_ID AS CreatedByID, @Ad_Created_DTTM AS CreatedDate, @Ai_UpdatedBy_ID AS UpdatedByID, @Ad_Updated_DTTM AS UpdatedDate, @An_TransactionSeqEvent_NUMB AS TransactionSequenceNumber; -- Display JSON data (you may want to convert these to tables if needed) SELECT @As_WorkExperienceJson_TEXT AS WorkExperience, @As_EducationJson_TEXT AS Education, @As_CertificationsJson_TEXT AS Certifications, @As_SkillsJson_TEXT AS Skills, @As_LanguagesJson_TEXT AS Languages, @As_AwardsJson_TEXT AS Awards, @As_ReferencesJson_TEXT AS ResumeReferences, @As_FreelanceProfilesJson_TEXT AS FreelanceProfiles, @As_JobPreferencesJson_TEXT AS JobPreferences;
dbo.Users$Sp_UpdatePassword | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_UpdatePassword @Ai_User_ID = 2000, -- Replace with actual user ID @As_CurrentPassword_TEXT = 'AnotherSecurePass456!', @As_NewPassword_TEXT = 'NewPass@456', @As_ConfirmPassword_TEXT = 'NewPass@456', @Ai_UpdatedBy_ID = 1, @An_NewTransactionSeqEvent_NUMB =null, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS StatusMessage;
Job$SpAddJobInvitation | DECLARE @Ai_User_ID INT = 2017; -- Candidate User ID (must exist in Users table) DECLARE @Ai_Job_ID INT = 12; -- Job ID (must exist in Job table) DECLARE @As_Notes_TEXT NVARCHAR(MAX) = 'We were impressed by your skills and would like to invite you to apply for this position.'; DECLARE @Ad_Expires_DTTM DATETIME = null; -- Expires in 14 days DECLARE @Ai_CreatedBy_ID INT = 2017; -- Recruiter User ID (must exist in Users table) DECLARE @Ai_TransactionSeqEvent_NUMB BIGINT = 1000005; -- Transaction sequence number -- Declare variables for output parameters DECLARE @Ai_JobInvitation_ID INT; DECLARE @Ac_Msg_CODE CHAR(5); DECLARE @As_DescriptionError_TEXT NVARCHAR(4000); -- Execute the stored procedure EXEC [dbo].[Job$SpAddJobInvitation] @Ai_User_ID = @Ai_User_ID, @Ai_Job_ID = @Ai_Job_ID, @As_Notes_TEXT = @As_Notes_TEXT, @Ad_Expires_DTTM = @Ad_Expires_DTTM, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ai_JobInvitation_ID = @Ai_JobInvitation_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display the results SELECT @Ai_JobInvitation_ID AS NewJobInvitationID, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS MessageDescription;
dbo.usp_Applicant_UpdateContactInformation | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.usp_Applicant_UpdateContactInformation @Ai_Applicant_ID = 21, -- Replace with actual Applicant_ID @As_PhoneNumber_TEXT = '555-1234', -- Replace with actual phone number @As_EmailAddress_TEXT = 'applicant@example.com', -- Replace with actual email @As_AddressLine1_TEXT = '123 Main St', -- Replace with actual address line 1 @As_AddressLine2_TEXT = 'Apt 4B', -- Optional @As_AdditionalInfo_TEXT = 'Near park', -- Optional @Ai_City_ID = 101, -- Replace with actual City_ID @Ac_State_CODE = 'NY', -- Replace with actual State Code @As_Zip_TEXT = '10001', -- Replace with actual Zip @As_County_CODE = '061', -- Optional @Ac_Country_CODE = 'US', -- Usually default 'US' @Ai_UpdatedBy_ID = 456, -- Replace with User ID who is updating @An_NewTransactionSeqEvent_NUMB = 999, @An_OldTransactionSeqEvent_NUMB = 248,-- Replace with new transaction number -- Output parameters @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
Job$SpGetContractPaymentInfo | DECLARE @PaymentMethod NVARCHAR(200), @PaymentSchedule NVARCHAR(200), @MsgCode CHAR(5), @MsgDesc NVARCHAR(4000); EXEC dbo.Job$SpGetContractPaymentInfo @Ai_User_ID = 1, @Ai_Contract_ID = 7, @As_PaymentMethod_TEXT = @PaymentMethod OUTPUT, @As_PaymentSchedule_TEXT = @PaymentSchedule OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgDesc OUTPUT; SELECT @PaymentMethod AS PaymentMethod, @PaymentSchedule AS PaymentSchedule, @MsgCode AS StatusCode, @MsgDesc AS StatusMessage;
Job$SpGetUserContractDocuments | DECLARE @MsgCode CHAR(5), @MsgDesc NVARCHAR(4000); EXEC dbo.Job$SpGetUserContractDocuments @Ai_User_ID = 2, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgDesc OUTPUT; SELECT @MsgCode AS StatusCode, @MsgDesc AS StatusMessage;
dbo.Timesheet$sp_updateTimesheetstatus | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(200); EXEC dbo.Timesheet$sp_updateTimesheetstatus @Ai_Timesheet_ID = 1, -- Replace with actual Timesheet ID @Ai_Reviewer_ID = 1, -- Replace with actual Reviewer/User ID @Ac_status_CODE = 'R', -- Use 'A' for Approve or 'R' for Reject @As_RejectedReason_TEXT = 'Insufficient details', -- Required if status = 'R' @Ab_Approveall_INDC = 0, -- 1 = Approve all pending, 0 = Just one @Ai_SignedOnUser_ID = 202, -- Who is performing the action @Ai_TransactionSeqEvent_NUMB = 987654321, -- Unique event number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
usp_EndContractAndSubmitReview | DECLARE @Ac_Msg_CODE CHAR(1) , @As_DescriptionError_TEXT VARCHAR(4000), @Ai_Contract_ID INT = 1, -- Replace with actual Contract ID @Ai_Rating_NUMB INT = 4, -- Organization's rating of candidate @As_Review_TEXT NVARCHAR(2000) = N'Excellent candidate!', @Ai_CreatedBy_ID INT = 1, -- Organization user ID @Ac_ReviewType_CODE CHAR(1) = 'O' ,-- Organization-to-Candidate @Ai_TransactionSeqEvent_NUMB BIGINT =1; EXEC [dbo].[usp_EndContractAndSubmitReview] @Ai_Contract_ID = @Ai_Contract_ID, @Ai_Rating_NUMB = @Ai_Rating_NUMB, @As_Review_TEXT = @As_Review_TEXT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID, @Ac_ReviewType_CODE = @Ac_ReviewType_CODE, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check results IF @Ac_Msg_CODE = 0 PRINT 'Success: ' + @As_DescriptionError_TEXT; ELSE PRINT 'Error ' + CAST(@Ac_Msg_CODE AS VARCHAR) + ': ' + @As_DescriptionError_TEXT; GO
usp_UserAddress_GetDetails_S1 | DECLARE @As_Address_TEXT NVARCHAR(MAX), @MsgCode CHAR(1), @ErrorDesc NVARCHAR(4000); EXEC usp_UserAddress_GetDetails_S1 @Ai_User_ID = 2082, -- 👈 Replace with the actual User_ID @Ac_AddressType_CODE = NULL, -- or pass a specific value if needed @As_Address_TEXT = @As_Address_TEXT OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Optional: Check the outputs SELECT @MsgCode AS Msg_CODE,@As_Address_TEXT AS ADDR,@ErrorDesc
usp_OrganizationProgram_List_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_OrganizationProgram_List_S1 @Ai_Organization_ID = 1, -- Optional, pass NULL if not filtering by Org @As_ProgramName_TEXT = null, -- Optional, pass NULL if not filtering by name @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output status SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_OrganizationProgramService_List_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_OrganizationProgramService_List_S1 @Ai_Organization_ID = 1, -- Optional, pass NULL for all @Ai_Program_ID = 4, -- Optional, pass NULL for all @Ab_Custom_INDC = 0, -- 0 = Default programs, 1 = Custom programs @As_ServiceName_TEXT = NULL, -- Optional, partial search @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Show result message SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_Case_Update_S1 | DECLARE @Ai_RowsAffected INT; DECLARE @Ac_Msg_CODE CHAR(5); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_Case_Update_S1 @Ai_Case_ID = 69, @Ai_User_ID = 2083, -- Client update fields @As_FirstName_TEXT = N'John', @As_MiddleName_TEXT = N'A', @As_LastName_TEXT = N'Doe', @Ac_Gender_CODE = 'M', @Ad_DateOfBirth_DATE = '1990-01-15', @As_SocialSecurityNumber_TEXT = '123-47-6879', @As_EmailAddress_TEXT = 'john.doNNNNNNe@example.com', @As_PhoneNumber_TEXT = '5551234567', -- Case details @Ad_CaseStartDate_DATE = NULL, @Ac_Priority_CODE = NULL, @Ac_CaseType_CODE = NULL, @Ac_EligibilityDetermined_CODE = NULL, @Ac_EmploymentStatus_CODE = NULL, @Ac_EducationAttainment_CODE = NULL, @Ac_PreferredLanguage_CODE = NULL, @Ac_ReferralSource_CODE = NULL, @As_InitialNotes_TEXT = NULL, @Ac_ReasonForLayoff_CODE = NULL, @Ab_ReceivingUI_INDC = 1, @Ac_Disaster_CODE = NULL, @As_AffectedAreas_TEXT = NULL, -- JSON inputs (null or sample) @At_TVP_WIOAPrograms_JSON = NULL, @At_TVP_Barriers_JSON = NULL, @At_TVP_CaseDocuments_JSON = NULL, -- Case manager assignment @Ai_Worker_ID = NULL, @Ad_AssignmentStart_DTTM = NULL, @Ac_AssignmentStatus_CODE = NULL, -- Optimistic concurrency @An_OldTransactionSeqEvent_NUMB = 211, @An_NewTransactionSeqEvent_NUMB = 1, -- Outputs @Ai_RowsAffected = @Ai_RowsAffected OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check results SELECT @Ai_RowsAffected AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorDescription;
usp_UserAddress_Add_S2 | DECLARE @Li_User_ID INT = 2083; -- example user ID DECLARE @Ls_AddressLine1_TEXT VARCHAR(250) = '123 Main St'; DECLARE @Ls_AddressLine2_TEXT VARCHAR(250) = null; DECLARE @Ls_AdditionalInfo_TEXT VARCHAR(250) = null; DECLARE @Li_City_ID INT = 1; DECLARE @Lc_State_CODE CHAR(2) = 'CA'; DECLARE @Ls_Zip_TEXT VARCHAR(20) = '90001'; DECLARE @Ls_County_CODE VARCHAR(10) = '001'; DECLARE @Lc_Country_CODE CHAR(2) = 'US'; DECLARE @Lc_AddressType_CODE CHAR(1) = 'R'; -- R = Residential, M = Mailing DECLARE @Li_CreatedBy_ID INT = 1; -- Output Params DECLARE @Li_UserAddress_ID INT; DECLARE @Li_Address_ID INT; DECLARE @Lc_Msg_Code CHAR(5); DECLARE @Ls_DescriptionError_TEXT VARCHAR(4000); DECLARE @Li_TransactionSeqEvent_NUMB INT = NULL; EXEC usp_UserAddress_Add_S2 @Ai_User_ID = @Li_User_ID , @As_AddressLine1_TEXT = @Ls_AddressLine1_TEXT , @As_AddressLine2_TEXT = @Ls_AddressLine2_TEXT , @As_AdditionalInfo_TEXT = @Ls_AdditionalInfo_TEXT , @Ai_City_ID = @Li_City_ID , @Ac_State_CODE = @Lc_State_CODE , @As_Zip_TEXT = @Ls_Zip_TEXT , @As_County_CODE = @Ls_County_CODE , @Ac_Country_CODE = @Lc_Country_CODE , @Ac_AddressType_CODE = @Lc_AddressType_CODE , @Ai_CreatedBy_ID = @Li_CreatedBy_ID , @Ai_TransactionSeqEvent_NUMB = @Li_TransactionSeqEvent_NUMB , @Ai_UserAddress_ID = @Li_UserAddress_ID OUTPUT , @Ai_Address_ID = @Li_Address_ID OUTPUT , @Ac_Msg_Code = @Lc_Msg_Code OUTPUT , @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; -- Check the output SELECT UserAddress_ID = @Li_UserAddress_ID , Address_ID = @Li_Address_ID , MsgCode = @Lc_Msg_Code , ErrorDescription = @Ls_DescriptionError_TEXT;
usp_CaseProgramservice_Delete_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_Desc VARCHAR(4000); EXEC usp_CaseProgramservice_Delete_S1 @Ai_CaseProgramService_ID = 1, @Ai_SignedOnuser_ID = 1, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_Desc OUTPUT; SELECT @Ac_Msg_Code, @As_Desc;
usp_Service_Insert_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Service_Insert_S1 @As_ServiceName_TEXT = N'Test Custom Service', @As_ServiceDesc_TEXT = N'test for custom client service', @As_ServiceCategory_CODE = N'AS', @Ac_Status_CODE = 'A', -- Assuming 'A' means Active @As_Notes_TEXT = N'This is a pilot service for new applicants', @Ai_CreatedBy_ID = 12, @Ai_TransactionSeqEvent_NUMB = 1, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ServiceNotes_Update_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_TransactionSeqEvent_NUMB BIGINT = 0; -- Pass 0 to trigger sequence event creation EXEC usp_ServiceNotes_Update_S1 @As_ServiceIDs_TEXT = '1', -- ✅ Comma-separated service IDs @As_Notes_TEXT = N'Updated notes for selected services', @Ai_UpdatedBy_ID = 1234, -- ✅ Your user ID @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB , @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 🔍 Optional: Check the results SELECT @Ac_Msg_Code AS Msg_Code, @Ai_TransactionSeqEvent_NUMB AS Transaction_ID, @As_DescriptionError_TEXT AS Description;
usp_Service_Update_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_TransactionSeqEvent_NUMB BIGINT = 0; -- Set to 0 to auto-generate one EXEC usp_Service_Update_S1 @Ai_CustomService_ID = 2 -- Replace with actual CustomService_ID ,@As_ServiceName_TEXT = N'Workforce Coaching' ,@As_ServiceDesc_TEXT = N'One-on-one career coaching and resume support.' ,@As_ServiceCategory_CODE = N'co' -- Replace with a valid code ,@Ac_Status_CODE = 'A' ,@As_Notes_TEXT = N'Updated to reflect new features.' ,@Ai_UpdatedBy_ID = 12 -- Replace with current user ID ,@Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB ,@Ac_Msg_Code = @Ac_Msg_Code OUTPUT ,@As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View results SELECT @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS DescriptionError;
usp_Service_Delete_S1 | DECLARE @MsgCode CHAR(5), @MsgText VARCHAR(4000), @TxnNum BIGINT = 0; -- Initialize to 0 to auto-generate if needed EXEC usp_Service_Delete_S1 @Ai_CustomService_ID = 1, -- ID of the service you want to delete @Ai_TransactionSeqEvent_NUMB = @TxnNum, @Ai_SignedOnUser_ID = 1, -- ID of the user performing the delete @Ac_Msg_Code = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @MsgCode AS MsgCode, @MsgText AS MsgText
usp_EndContractAndSubmitReview | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Get_service_S1 @Ai_Service_ID = NULL, -- Or provide a specific ID @As_ServiceName_TEXT = NULL, -- Or partial/full name to filter @Ac_Servicecategory_CODE = 'AS', @Ac_Status_CODE = 'A', -- e.g., 'A' (Active), 'I' (Inactive) @Ai_From_NUMB = 1, -- Paging start @Ai_To_NUMB = 10, -- Paging end @Ai_SignedonUser_ID = 12, -- Logged-in user @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output messages SELECT @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS Description;
usp_CaseService_Insert_S2 | DECLARE @Ai_CaseService_ID INT, @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Optional: initialize transaction event number if known -- SET @Ai_TransactionSeqEvent_NUMB = 123456; -- if you already have one EXEC usp_CaseService_Insert_S2 @Ai_Case_ID = 68, -- Replace with actual Case_ID @Ai_Service_ID = 3, -- Replace with actual Service_ID @Ac_Priority_CODE = 'H', -- Example: H for High, M for Medium, L for Low @Ac_Status_CODE = 'A', -- A = Active, C = Completed, etc. @Ai_AssignedTo_ID = 2066, -- User ID the case is assigned to @Ad_Due_DATE = '2025-06-25', -- Replace with actual due date @As_Notes_TEXT = 'Initial assessment scheduled.', -- Optional notes @An_Amount_NUMB = NULL, -- Optional amount (null if not applicable) @Ai_CreatedBy_ID = 12, -- The user creating this record @Ai_TransactionSeqEvent_NUMB = 0, @Ai_CaseService_ID = @Ai_CaseService_ID OUTPUT, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- ✅ Check Output SELECT @Ai_CaseService_ID AS CaseService_ID, @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS Msg_Description;
usp_CaseService_Update_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_TransactionSeqEvent_NUMB BIGINT = 0; -- Set to 0 to auto-generate EXEC usp_CaseService_Update_S1 @Ai_CaseService_ID = 1, -- Your existing CaseService_ID @Ai_Case_ID = 2066, -- Updated Case_ID @Ai_Service_ID = 2, -- Updated Service_ID @Ac_Priority_CODE = 'H', -- Example: 'H' = High @Ac_Status_CODE = 'A', -- Example: 'A' = Active @Ai_AssignedTo_ID = 12, -- User ID assigned @Ad_Due_DATE = '2025-06-30', -- New due date @As_Notes_TEXT = 'Updated service note.', -- Optional notes @An_Amount_NUMB = NULL, -- Updated amount @Ai_UpdatedBy_ID = 7, -- Modifier user ID @Ai_TransactionSeqEvent_NUMB = 0, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Show the result SELECT MsgCode = @Ac_Msg_Code, Message = @As_DescriptionError_TEXT
usp_CaseService_Delete_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the delete procedure EXEC dbo.usp_CaseService_Delete_S1 @Ai_CaseService_ID = 1, -- Replace with actual CaseService_ID @Ai_TransactionSeqEvent_NUMB = 0, @Ai_SignedOnuser_ID = 7, -- Replace with actual signed-in user ID @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT MsgCode = @Ac_Msg_Code, Message = @As_DescriptionError_TEXT;
usp_Case_Service_Bycase_Get_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Case_Service_Bycase_Get_S1 @Ai_Case_ID = 68, -- Replace with your Case ID @As_SearchText = NULL, -- Optional: e.g., 'Training' @Ac_Status_CODE = NULL, -- Optional filter @Ac_ServiceCategory_CODE = NULL, -- Optional filter (e.g., 'AD') @Ac_Priority_CODE = NULL, -- Optional filter (e.g., 'H') @Ai_AssignedTo_ID = NULL, -- Optional filter (user ID) @Ai_From_NUMB = 1, -- Pagination start @Ai_To_NUMB = 10, -- Pagination end @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: view the message code and description SELECT @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS DescriptionError;
usp_Case_CreateNew_S1 | DECLARE @Ai_Case_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Case_CreateNew_S1 @Ai_Applicant_ID = 75 ,@Ai_User_ID = 2090 ,@Ac_CaseType_CODE = 'U' ,@Ac_EligibilityDetermined_CODE = 'Y' ,@As_WIOAPrograms_JSON = NULL ,@As_Barriers_JSON = '[{"Barrier_CODE":"BS"},{"Barrier_CODE":"HM"}]' ,@As_CaseDocuments_JSON = '[{"DocumentType_CODE":"SS","FileName_TEXT":"Driver License","FilePath_TEXT":"https://fileupload.com/dl1.pdf","FileSize_NUMB":"20","FileType_TEXT":"pdf"}]' ,@Ai_Worker_ID = 2066 ,@Ad_AssignmentStart_DTTM = '2025-06-18 06:02:11.120' ,@Ac_AssignmentStatus_CODE = 'A' ,@An_TransactionSeqEvent_NUMB = 325 ,@Ai_CreatedBy_ID = 0 ,@Ai_Case_ID = @Ai_Case_ID OUTPUT ,@Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT ,@As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ai_Case_ID AS case_ID,@Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description
usp_MyCaseload_List_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_MyCaseload_List_S1 @As_Program_CODE = NULL, -- Example: 'AD' @As_userName_TEXT = NULL, -- Example: 'john' @Ai_Case_ID = NULL, -- Example: 101 @Ac_ActivityStatus_CODE = NULL, -- Example: 'P' @Ac_Status_CODE = NULL, -- Example: 'A' @Ac_MajorActivity_CODE = NULL, -- Example: 'REG' @Ai_SignedOnUser_ID = 1, -- Required: Provide valid User_ID @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS DescriptionError;
usp_AssessmentSubmission_Add_S1 | DECLARE @Ai_AssessmentSubmission_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @Atvps_ProgServ NVARCHAR(MAX), @Ai_TransactionSeqEvent_NUMB BIGINT = 0; -- Sample JSON: Replace with real Program/Service codes SET @Atvps_ProgServ = N'[ { "Program_CODE": "AD", "Service_CODE": "CCO" }, { "Program_CODE": "AD", "Service_CODE": "JSA" } ]'; EXEC dbo.usp_AssessmentSubmission_Add_S1 @Ai_Case_ID = 78, @Ai_SubmittedBy_ID = 1, @As_CareerGoals_TEXT = N'Become a software developer', @As_CurrentJobSearch_TEXT = N'Applying to junior roles weekly', @As_SpecificCareerGoal_TEXT = N'.NET Full Stack Developer', @As_HighestEducation_TEXT = N'Bachelor of Science in IT', @As_LicensesCertificates_TEXT = N'Microsoft Azure Fundamentals', @As_SkillsToImprove_TEXT = N'C#, SQL Server, Communication', @As_EmploymentStatus_TEXT = N'Unemployed', @As_PastJobs_TEXT = N'Tech support, Data entry', @As_RecentLayoffs_TEXT = N'Company downsizing last quarter', @As_EmploymentBarriers_TEXT = N'Limited work experience', @As_HelpNeeded_TEXT = N'Resume building, Interview coaching', @As_TrainingInterest_TEXT = N'Yes, interested in coding bootcamp', @As_OtherServicesReceive_TEXT = N'Food assistance, housing support', @As_NeedsAssessmentNotes_TEXT = N'Motivated client with high learning potential', @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Atvps_ProgServ = @Atvps_ProgServ, @Ai_AssessmentSubmission_ID = @Ai_AssessmentSubmission_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT AssessmentSubmission_ID = @Ai_AssessmentSubmission_ID, Msg_CODE = @Ac_Msg_CODE, Error_Description = @As_DescriptionError_TEXT;
usp_Get_ProgramTimeline_ByCase_S1 | DECLARE @Ac_Msg_Code CHAR(5); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_Get_ProgramTimeline_ByCase_S1 @Ai_Case_ID = 86, -- Replace with your actual Case_ID @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optionally, check the outputs SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_Referral_Add_S1 | DECLARE @Ai_Referral_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); -- Optional: Generate a transaction sequence ID beforehand (if you don't want proc to do it) -- EXEC dbo.TransactionSeqEvent$Sp_Add -- @As_EventType_CODE = 'ADD_RFRL', -- @Ai_CreatedBy_ID = 101, -- @Ai_TransactionSeqEvent_ID = @An_TransactionSeqEvent_NUMB OUTPUT, -- @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, -- @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; EXEC usp_Referral_Add_S1 @Ai_Case_ID = 93, @Ai_Organization_ID = NULL, @Ai_CaseWorker_ID = 2066, @Ai_Service_ID = 1, @Ab_FollowUp_INDC = 1, @Ad_FollowupDate_DTTM = '2025-07-05', @Ac_Status_CODE = 'P', @As_ReferralTitle_TEXT = 'Need assistance for housing', @As_ReferralDesc_TEXT = 'Client urgently requires temporary housing due to recent eviction.', @As_Notes_TEXT = 'Priority client, follow up in 3 days.', @Ai_CreatedBy_ID = 2099, @An_TransactionSeqEvent_NUMB = 0, @Ai_Referral_ID = @Ai_Referral_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View result SELECT Referral_ID = @Ai_Referral_ID, MsgCode = @Ac_Msg_CODE, Msg = @As_DescriptionError_TEXT
usp_Sent_Referral_Get_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_Sent_Referral_Get_S1 @Ai_SignedOnUser_ID = 2099, -- Replace with signed-in user ID @As_ReferralTitle_TEXT = NULL, @Ai_Referral_ID = 1,-- Or 'Dental Referral' if filtering @Ai_Case_ID = 93, @Ac_Status_CODE = NULL, -- Or 'P' / 'C' etc. @As_ClientName_TEXT = NULL, -- Or 'John Doe' @Ai_Service_ID = NULL, -- Or 123 @Ab_FollowUp_INDC = NULL, -- Or 1/0 @As_Search_TEXT = NULL, -- Optional global search text @Ai_From_NUMB = 1, -- Page number @Ai_To_NUMB = 10, -- Page size @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: view result message SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_Referral_Update_Status_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000), -- Let the proc create it if needed @Ai_RowsAffected_NUMB INT; EXEC usp_Referral_Update_Status_S1 @Ai_Referral_ID = 1, -- Replace with actual Referral_ID @Ac_Status_CODE = 'C', -- e.g., 'P'=Pending, 'C'=Completed @Ai_UpdatedBy_ID = 2099, -- Logged-in user ID @An_OldTransactionSeqEvent_NUMB = 466, -- Get this from the record you're updating @An_NewTransactionSeqEvent_NUMB = 1, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output for debugging/logging SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @Ai_RowsAffected_NUMB AS RowsAffected;
EXEC usp_User_NotificationPreference_Get_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_User_NotificationPreference_Get_S1 @Ai_User_ID = 1, -- Replace with the actual user ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: Output message for logging/debug SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Job$SpGetReviewProposalUserList | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- ╔═ Execute Procedure ═╗ EXEC dbo.Job$SpGetReviewProposalUserList @Ai_SignedOnUser_ID = 2, @Ai_Organization_ID = 1, -- [Required] Organization ID @As_SearchName_TEXT = NULL, -- [Optional] Partial/full applicant name @Ac_ApplicationStatus_CODE = 'SUB', -- [Optional] e.g., 'APR', 'REJ', 'PND' @Ai_Job_ID = 12, -- [Optional] Specific job ID @Ai_RowFrom_NUMB = 1, -- Pagination Start Row (1-based) @Ai_RowTo_NUMB = 25, -- Pagination End Row @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- ╔═ View Status Output ═╗ SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Job$SpUpdateJobNationality | DECLARE @Ai_Job_ID INT = 25, -- Target Job ID @Ac_WorkAuth_CODE CHAR(2) = 'US', -- e.g., 'US' for US Citizen @Ac_PreferredNationality_CODE CHAR(2) = 'PR', -- e.g., 'PR' for Permanent Resident @As_OtherNationality_JSON NVARCHAR(MAX) = N'["IN", "CA", "UK"]', -- Optional JSON list @Ai_UpdatedBy_ID INT = 2, -- User performing the update @Ai_TransactionSeqEvent_NUMB BIGINT = 0, -- Transaction sequence for tracking @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Job$SpUpdateJobNationality @Ai_Job_ID = @Ai_Job_ID, @Ac_WorkAuth_CODE = @Ac_WorkAuth_CODE, @Ac_PreferredNationality_CODE = @Ac_PreferredNationality_CODE, @As_OtherNationality_JSON = @As_OtherNationality_JSON, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Job$SpUpdateJobSkills | DECLARE @Ai_Job_ID INT = 25, @As_Skill_JSON NVARCHAR(MAX) = N'["Java", "SQL", "Agile"]', @Ai_RequiredExpMin_NUMB INT = 2, @Ai_RequiredExpMax_NUMB INT = 5, @Ac_ExperienceLevel_CODE CHAR(2) = 'MI', -- Mid-level @Ac_EducationLevel_CODE CHAR(2) = 'HS', -- Undergraduate @Ai_UpdatedBy_ID INT = 2, @Ai_TransactionSeqEvent_NUMB BIGINT = 0, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobSkills @Ai_Job_ID = @Ai_Job_ID, @As_Skill_JSON = @As_Skill_JSON, @Ai_RequiredExpMin_NUMB = @Ai_RequiredExpMin_NUMB, @Ai_RequiredExpMax_NUMB = @Ai_RequiredExpMax_NUMB, @Ac_ExperienceLevel_CODE = @Ac_ExperienceLevel_CODE, @Ac_EducationLevel_CODE = @Ac_EducationLevel_CODE, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Job$SpUpdateJobSalaryDetails | DECLARE @Ai_Job_ID INT = 25, @Ac_PayStructure_CODE CHAR(2) = 'MO', -- Annual @Ai_SalaryMin_NUMB INT = 50000, @Ai_SalaryMax_NUMB INT = 80000, @Ai_UpdatedBy_ID INT = 2, @Ai_TransactionSeqEvent_NUMB BIGINT = 0, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobSalaryDetails @Ai_Job_ID = @Ai_Job_ID, @Ac_PayStructure_CODE = @Ac_PayStructure_CODE, @Ai_SalaryMin_NUMB = @Ai_SalaryMin_NUMB, @Ai_SalaryMax_NUMB = @Ai_SalaryMax_NUMB, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Job$SpUpdateJobKeywords | DECLARE @Ai_Job_ID INT = 25, @As_Keyword_JSON NVARCHAR(MAX) = '["cloud", "AI", "data science"]', @Ac_Visibility_CODE CHAR(1) = 'U', -- P = Public @Ai_UpdatedBy_ID INT = 2, @Ai_TransactionSeqEvent_NUMB BIGINT = 0, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Job$SpUpdateJobKeywords @Ai_Job_ID = @Ai_Job_ID, @As_Keyword_JSON = @As_Keyword_JSON, @Ac_Visibility_CODE = @Ac_Visibility_CODE, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Job$SpUpdateJobDesc | DECLARE @Ai_Job_ID INT = 25, -- Replace with actual Job ID @As_Description_TEXT NVARCHAR(MAX) = N'Full-stack software engineering role focused on scalable web apps.', @As_Requirements_TEXT NVARCHAR(MAX) = N'3+ years experience with .NET and Angular. Strong SQL skills required.', @As_Benefits_TEXT NVARCHAR(MAX) = N'Health, Vision, Dental, 401K, Flexible Hours.', @Ai_UpdatedBy_ID INT = 2, -- Typically the admin or recruiter ID @Ai_TransactionSeqEvent_NUMB BIGINT = 0, -- Replace with proper transaction sequence @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobDesc @Ai_Job_ID = @Ai_Job_ID, @As_Description_TEXT = @As_Description_TEXT, @As_Requirements_TEXT = @As_Requirements_TEXT, @As_Benefits_TEXT = @As_Benefits_TEXT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Job$SpUpdateJobBasicInfo | DECLARE @Ai_Job_ID INT = 25, @As_Title_TEXT NVARCHAR(100) = N'Senior SQL Developer', @As_Location_TEXT NVARCHAR(200) = N'New York, NY', @Ac_LocationType_CODE CHAR(2) = 'ON', -- Example: 'ON' = Onsite, 'RM' = Remote @Ac_EmploymentType_CODE CHAR(2) = 'FT', -- Example: 'FT' = Full-time @Ac_JobType_CODE CHAR(2) = 'P', -- Example: 'PR' = Permanent @Ai_UpdatedBy_ID INT = 2001, @Ai_TransactionSeqEvent_NUMB BIGINT = 202406120001, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobBasicInfo @Ai_Job_ID = @Ai_Job_ID, @As_Title_TEXT = @As_Title_TEXT, @As_Location_TEXT = @As_Location_TEXT, @Ac_LocationType_CODE = @Ac_LocationType_CODE, @Ac_EmploymentType_CODE = @Ac_EmploymentType_CODE, @Ac_JobType_CODE = @Ac_JobType_CODE, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the status and message SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Job$SpUpdateJobFlags | DECLARE @Ai_Job_ID INT = 25, @As_JobFlag_JSON NVARCHAR(MAX) = N'["UG", "RO"]', -- Example: Urgent Hiring (UG), Remote Option (RO) @As_ONetCategories_JSON NVARCHAR(MAX) = N'["15-114", "15-113"]', -- O*NET SOC codes example (optional) @Ai_UpdatedBy_ID INT = 2, @Ai_TransactionSeqEvent_NUMB BIGINT = 0, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobFlags @Ai_Job_ID = @Ai_Job_ID, @As_JobFlag_JSON = @As_JobFlag_JSON, @As_ONetCategories_JSON = @As_ONetCategories_JSON, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display the output status and message SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Job$SpUpdateJobApplicationSetting | DECLARE @Ai_Job_ID INT = 25, @As_Requirement_JSON NVARCHAR(MAX) = N'["RS", "CL"]', -- Example: Resume (RS), Cover Letter (CL) @As_ContactEmails_JSON NVARCHAR(MAX) = N'["hr@example.com", "recruiter@example.com"]', @Ad_Deadline_DATE DATE = '2025-07-31', @Ai_UpdatedBy_ID INT = 2, @Ai_TransactionSeqEvent_NUMB BIGINT = 0, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpUpdateJobApplicationSetting @Ai_Job_ID = @Ai_Job_ID, @As_Requirement_JSON = @As_Requirement_JSON, @As_ContactEmails_JSON = @As_ContactEmails_JSON, @Ad_Deadline_DATE = @Ad_Deadline_DATE, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results to verify success or failure SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Job$SpAddJobContractBonus | DECLARE @Ai_JobContractBonus_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); -- ╔═ Execute Procedure ═╗ EXEC dbo.Job$SpAddJobContractBonus @Ai_SignedOnUser_ID = 1, -- ID of user performing the insert (typically admin/staff) @Ai_ContractBonus_ID = 1, @Ai_Contract_ID = 3, -- The Contract ID to which bonus is being added @Ai_BonusAmount_NUMB = 1500, -- Bonus amount, in system's base currency (e.g., USD) @Ai_TransactionSeqEvent_NUMB = 0, -- Event tracking number @Ai_JobContractBonus_ID = @Ai_JobContractBonus_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- ╔═ Output the Result ═╗ SELECT @Ai_JobContractBonus_ID AS NewBonusID, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Job$SpDeleteJob | DECLARE @Ai_Job_ID INT = 50, -- Replace with a valid Job_ID @Ai_DeletedBy_ID INT = 12, -- ID of the user deleting the job @Ai_OldTransactionSeqEvent_NUMB BIGINT = 1000001, @Ai_NewTransactionSeqEvent_NUMB BIGINT = 0, -- Optional tracking ID @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpDeleteJob @Ai_Job_ID = @Ai_Job_ID, @Ai_DeletedBy_ID = @Ai_DeletedBy_ID, @Ai_OldTransactionSeqEvent_NUMB = @Ai_OldTransactionSeqEvent_NUMB, @Ai_NewTransactionSeqEvent_NUMB = @Ai_NewTransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Job$SpGetJobBasicInfo | DECLARE @Ai_Job_ID INT = 12, -- example Job ID @As_Title_TEXT NVARCHAR(100), @As_Location_TEXT NVARCHAR(200), @Ac_LocationType_CODE CHAR(2), @As_LocationTypeDesc_TEXT NVARCHAR(100), @Ac_EmploymentType_CODE CHAR(2), @As_EmploymentTypeDesc_TEXT NVARCHAR(100), @Ac_JobType_CODE CHAR(2), @As_JobTypeDesc_TEXT NVARCHAR(100), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobBasicInfo @Ai_Job_ID = @Ai_Job_ID, @As_Title_TEXT = @As_Title_TEXT OUTPUT, @As_Location_TEXT = @As_Location_TEXT OUTPUT, @Ac_LocationType_CODE = @Ac_LocationType_CODE OUTPUT, @As_LocationTypeDesc_TEXT = @As_LocationTypeDesc_TEXT OUTPUT, @Ac_EmploymentType_CODE = @Ac_EmploymentType_CODE OUTPUT, @As_EmploymentTypeDesc_TEXT = @As_EmploymentTypeDesc_TEXT OUTPUT, @Ac_JobType_CODE = @Ac_JobType_CODE OUTPUT, @As_JobTypeDesc_TEXT = @As_JobTypeDesc_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View Output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorDescription, @As_Title_TEXT AS JobTitle, @As_Location_TEXT AS JobLocation, @Ac_LocationType_CODE AS LocationTypeCode, @As_LocationTypeDesc_TEXT AS LocationTypeDesc, @Ac_EmploymentType_CODE AS EmploymentTypeCode, @As_EmploymentTypeDesc_TEXT AS EmploymentTypeDesc, @Ac_JobType_CODE AS JobTypeCode, @As_JobTypeDesc_TEXT AS JobTypeDesc;
Job$SpGetJobDesc | DECLARE @Ai_Job_ID INT = 12, -- Example Job ID @As_Description_TEXT NVARCHAR(MAX), @As_Requirements_TEXT NVARCHAR(MAX), @As_Benefits_TEXT NVARCHAR(MAX), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobDesc @Ai_Job_ID = @Ai_Job_ID, @As_Description_TEXT = @As_Description_TEXT OUTPUT, @As_Requirements_TEXT = @As_Requirements_TEXT OUTPUT, @As_Benefits_TEXT = @As_Benefits_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View Outputs SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage, @As_Description_TEXT AS JobDescription, @As_Requirements_TEXT AS JobRequirements, @As_Benefits_TEXT AS JobBenefits;
Job$SpGetJobSalaryDetails | DECLARE @Ai_Job_ID INT = 12, -- Replace with a valid Job_ID @Ac_PayStructure_CODE CHAR(2), @As_PayStructureDesc_TEXT NVARCHAR(100), @Ai_SalaryMin_NUMB INT, @Ai_SalaryMax_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobSalaryDetails @Ai_Job_ID = @Ai_Job_ID, @Ac_PayStructure_CODE = @Ac_PayStructure_CODE OUTPUT, @As_PayStructureDesc_TEXT = @As_PayStructureDesc_TEXT OUTPUT, @Ai_SalaryMin_NUMB = @Ai_SalaryMin_NUMB OUTPUT, @Ai_SalaryMax_NUMB = @Ai_SalaryMax_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage, @Ac_PayStructure_CODE AS PayStructureCode, @As_PayStructureDesc_TEXT AS PayStructureDesc, @Ai_SalaryMin_NUMB AS SalaryMin, @Ai_SalaryMax_NUMB AS SalaryMax;
Job$SpGetJobNationality | DECLARE @Ai_Job_ID INT = 12, -- Replace with actual Job_ID @Ac_WorkAuth_CODE CHAR(2), @Ac_PreferredNationality_CODE CHAR(2), @As_OtherNationality_JSON NVARCHAR(MAX), @As_WorkAuthDesc_TEXT NVARCHAR(100), @As_PreferredNationalityDesc_TEXT NVARCHAR(100), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobNationality @Ai_Job_ID = @Ai_Job_ID, @Ac_WorkAuth_CODE = @Ac_WorkAuth_CODE OUTPUT, @Ac_PreferredNationality_CODE = @Ac_PreferredNationality_CODE OUTPUT, @As_OtherNationality_JSON = @As_OtherNationality_JSON OUTPUT, @As_WorkAuthDesc_TEXT = @As_WorkAuthDesc_TEXT OUTPUT, @As_PreferredNationalityDesc_TEXT = @As_PreferredNationalityDesc_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View Output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage, @Ac_WorkAuth_CODE AS WorkAuthCode, @As_WorkAuthDesc_TEXT AS WorkAuthDescription, @Ac_PreferredNationality_CODE AS PreferredNationalityCode, @As_PreferredNationalityDesc_TEXT AS PreferredNationalityDescription, @As_OtherNationality_JSON AS OtherNationalitiesJSON;
Job$SpGetJobSkills | DECLARE @Ai_Job_ID INT = 53, -- Example Job_ID @Ac_ExperienceLevel_CODE CHAR(2), @As_ExperienceLevelDesc_TEXT NVARCHAR(100), @Ai_RequiredExpMin_NUMB INT, @Ai_RequiredExpMax_NUMB INT, @As_Skill_JSON NVARCHAR(MAX), @Ac_EducationLevel_CODE CHAR(2), @As_EducationLevelDesc_TEXT NVARCHAR(100), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobSkills @Ai_Job_ID = @Ai_Job_ID, @Ac_ExperienceLevel_CODE = @Ac_ExperienceLevel_CODE OUTPUT, @As_ExperienceLevelDesc_TEXT = @As_ExperienceLevelDesc_TEXT OUTPUT, @Ai_RequiredExpMin_NUMB = @Ai_RequiredExpMin_NUMB OUTPUT, @Ai_RequiredExpMax_NUMB = @Ai_RequiredExpMax_NUMB OUTPUT, @As_Skill_JSON = @As_Skill_JSON OUTPUT, @Ac_EducationLevel_CODE = @Ac_EducationLevel_CODE OUTPUT, @As_EducationLevelDesc_TEXT = @As_EducationLevelDesc_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output Review SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorText, @Ac_ExperienceLevel_CODE AS ExperienceLevelCode, @As_ExperienceLevelDesc_TEXT AS ExperienceLevelDesc, @Ai_RequiredExpMin_NUMB AS MinYearsExperience, @Ai_RequiredExpMax_NUMB AS MaxYearsExperience, @As_Skill_JSON AS SkillsJSON, @Ac_EducationLevel_CODE AS EducationLevelCode, @As_EducationLevelDesc_TEXT AS EducationLevelDesc;
Job$SpGetJobApplicationSetting | DECLARE @Ai_Job_ID INT = 12, -- Replace with valid Job_ID @Ad_Deadline_DATE DATE, @As_Requirement_JSON NVARCHAR(MAX), @As_ContactEmails_JSON NVARCHAR(MAX), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobApplicationSetting @Ai_Job_ID = @Ai_Job_ID, @Ad_Deadline_DATE = @Ad_Deadline_DATE OUTPUT, @As_Requirement_JSON = @As_Requirement_JSON OUTPUT, @As_ContactEmails_JSON = @As_ContactEmails_JSON OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output Check SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorDescription, @Ad_Deadline_DATE AS ApplicationDeadline, @As_Requirement_JSON AS RequirementsJSON, @As_ContactEmails_JSON AS ContactEmailsJSON;
Job$SpGetJobKeywords | DECLARE @Ai_Job_ID INT = 12, -- Replace with actual Job_ID @Ac_Visibility_CODE CHAR(1), @As_VisibilityDesc_TEXT NVARCHAR(100), @As_Keyword_JSON NVARCHAR(MAX), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobKeywords @Ai_Job_ID = @Ai_Job_ID, @Ac_Visibility_CODE = @Ac_Visibility_CODE OUTPUT, @As_VisibilityDesc_TEXT = @As_VisibilityDesc_TEXT OUTPUT, @As_Keyword_JSON = @As_Keyword_JSON OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output Check SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage, @Ac_Visibility_CODE AS VisibilityCode, @As_VisibilityDesc_TEXT AS VisibilityDescription, @As_Keyword_JSON AS KeywordJSON;
Job$SpGetJobFlags | DECLARE @Ai_Job_ID INT = 12, -- Replace with actual Job ID @As_JobFlag_JSON NVARCHAR(MAX), @As_ONetCategories_JSON NVARCHAR(MAX), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpGetJobFlags @Ai_Job_ID = @Ai_Job_ID, @As_JobFlag_JSON = @As_JobFlag_JSON OUTPUT, @As_ONetCategories_JSON = @As_ONetCategories_JSON OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output Result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage, @As_JobFlag_JSON AS JobFlags, @As_ONetCategories_JSON AS ONETCategories;
Contract$SpGetContractBonusList | DECLARE @Ai_SignedOnUser_ID INT = 2017, -- Current logged-in user @Ai_User_ID INT = NULL, -- Optional: target contract user @Ai_Organization_ID INT = 1, -- Optional: specific organization @Ai_Contract_ID INT = NULL, -- Optional: filter by one contract @Ai_From_NUMB INT = 1, -- Pagination start @Ai_To_NUMB INT = 10, -- Pagination end @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Contract$SpGetContractBonusList @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @Ai_User_ID = @Ai_User_ID, @Ai_Organization_ID = @Ai_Organization_ID, @Ai_Contract_ID = @Ai_Contract_ID, @Ai_From_NUMB = @Ai_From_NUMB, @Ai_To_NUMB = @Ai_To_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View response codes SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Calendar$SpGetTempCalendarShareLink | DECLARE @As_CalendarShareLink_TEXT VARCHAR(MAX), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC Calendar$SpGetTempCalendarShareLink @As_CalendarShareLink_TEXT = @As_CalendarShareLink_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Review output results SELECT @As_CalendarShareLink_TEXT AS ShareLink, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Calendar$SpAddShareLink | DECLARE @Ai_CalendarShareLink_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$SpAddShareLink @Ai_Calendar_ID = 1, -- Example Calendar ID @As_ShareLinkUrl_TEXT = '29F7C22F', @Ab_Expired_BIT = 0, -- 0 = Active @Ai_CreatedBy_ID = 6, @Ai_UpdatedBy_ID = 6, -- Optional @An_TransactionSeqEvent_NUMB = 0, -- Optional @Ai_CalendarShareLink_ID = @Ai_CalendarShareLink_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result review SELECT @Ai_CalendarShareLink_ID AS CalendarShareLink_ID, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Calendar$SpUpdateExpireShareLink | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$SpUpdateExpireShareLink @As_ShareLinkUrl_TEXT = '29F7C22F', @Ab_Expired_BIT = 1, -- 1 to mark as expired @Ai_UpdatedBy_ID = 8, -- User performing the update @An_TransactionSeqEvent_NUMB = 0, -- Optional trace event @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the outcome SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Calendar$SpGetShareLinkWorkspace | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$SpGetShareLinkWorkspace @As_CalendarShareLink_TEXT = '29F7C22F', @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Calendar$GetCalendarUnAvailabilitySlots | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$GetCalendarUnAvailabilitySlots @Ai_Calendar_ID = 1, @As_UnitMemberIDs_JSON = null, -- N'[1, 2]', -- Example: list of User_IDs (or pass NULL for all) @Ad_From_DATE = '2025-06-24', @Ad_To_DATE = '2025-06-26', @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT MsgCode = @Ac_Msg_CODE, ErrorDescription = @As_DescriptionError_TEXT;
usp_Referral_Update_S1 | DECLARE @Msg_Code CHAR(1), @Err_Text NVARCHAR(4000); EXEC dbo.usp_Referral_Update_S1 @Ai_Referral_ID = 1, -- 🔑 existing referral ID @Ai_Service_ID = 2, @Ai_Case_ID = 93, @As_ReferralTitle_TEXT = 'Career Counseling', @As_ReferralDescription_TEXT = 'Referral for advanced career planning and training support.', @Ab_RequiresFollowUp_INDC = 1, @Ad_FollowupDate_DTTM = '2025-07-10', @Ai_UpdatedBy_ID = 1002, @An_TransactionSeqEvent_NUMB = 1, -- your event tracking ID @Ac_Msg_CODE = @Msg_Code OUTPUT, @As_DescriptionError_TEXT = @Err_Text OUTPUT; SELECT @Msg_Code AS MsgCode, @Err_Text AS Description;
usp_Referral_FollowUp_History_S1 | DECLARE @Msg_CODE CHAR(1), @Msg_TEXT NVARCHAR(4000); EXEC usp_Referral_FollowUp_History_S1 @Ai_Referral_ID = 1, -- Replace with actual Referral_ID @Ai_ReferralNote_ID = NULL, -- Pass specific note ID or NULL for all @Ab_IncludeDeleted_INDC = 0, -- 0 = Exclude deleted notes, 1 = Include @Ai_From_NUMB = 1, -- Page start (e.g., 1 = first page) @Ai_To_NUMB = 10, -- Page size (e.g., 10 rows per page) @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Msg_TEXT OUTPUT; -- Optional: see results SELECT @Msg_CODE AS Msg_CODE, @Msg_TEXT AS Description;
usp_ReferralNote_Add_S1 | DECLARE @ReferralNote_ID INT, @Msg_CODE CHAR(1), @Msg_TEXT NVARCHAR(4000); EXEC usp_ReferralNote_Add_S1 @Ai_Referral_ID = 1, -- Replace with actual referral ID @As_Note_TEXT = N'This is a new follow-up note2.', -- Note content @Ai_CreatedBy_ID = 12, -- Logged-in user ID @An_TransactionSeqEvent_NUMB = 1, -- Unique transaction event number @Ai_ReferralNote_ID = @ReferralNote_ID OUTPUT, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Msg_TEXT OUTPUT; -- Check results SELECT @ReferralNote_ID AS ReferralNote_ID, @Msg_CODE AS Msg_CODE, @Msg_TEXT AS Description;
usp_ReferralOutcome_Update_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_ReferralOutcome_Update_S1 @Ai_Referral_ID = 1, -- Replace with actual Referral_ID @As_ReferralOutcome_CODE = 'sp', -- Example: 'AC' for Accepted @As_ReferralOutcome_TEXT = 'service alreadshgidsfrg', -- Example outcome description @Ai_UpdatedBy_ID = 2066, -- Caseworker ID who is updating @An_TransactionSeqEvent_NUMB = 1, -- Transaction sequence event number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Announcement_Add | DECLARE @As_Title_TEXT NVARCHAR(200) = 'System Maintenance Notice'; DECLARE @As_MessageBody_TEXT NVARCHAR(MAX) = 'The system will be down for maintenance on Saturday from 2-4 AM.'; DECLARE @Ac_AnnouncementType_CODE CHAR(1) = 'I'; -- Information type DECLARE @Ad_Start_DATE DATE = '2025-07-01'; DECLARE @Ad_Expiry_DATE DATE = NULL; DECLARE @Ai_SignedOnUser_ID INT = 123; -- Admin user ID DECLARE @Ai_TransactionSeqEvent_NUMB BIGINT = 0; -- Auto-generate DECLARE @Ai_Announcement_ID INT; DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- EXECUTE PROCEDURE EXEC [dbo].[Announcement_Add] @As_Title_TEXT = @As_Title_TEXT, @As_MessageBody_TEXT = @As_MessageBody_TEXT, @Ac_AnnouncementType_CODE = @Ac_AnnouncementType_CODE, @Ad_Start_DATE = @Ad_Start_DATE, @Ad_Expiry_DATE = @Ad_Expiry_DATE, @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ai_Announcement_ID = @Ai_Announcement_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- CHECK RESULTS IF @Ac_Msg_CODE = 'S' PRINT 'Success! New Announcement ID: ' + CAST(@Ai_Announcement_ID AS VARCHAR); ELSE PRINT 'Error: ' + @As_DescriptionError_TEXT;
Announcement_Update | DECLARE @Ai_Announcement_ID INT = 5; -- Existing announcement ID to update DECLARE @As_Title_TEXT NVARCHAR(200) = 'Updated Maintenance Notice'; DECLARE @As_MessageBody_TEXT NVARCHAR(MAX) = 'Updated: System maintenance extended to 5 AM.'; DECLARE @Ac_AnnouncementType_CODE CHAR(1) = 'W'; -- Warning type DECLARE @Ad_Start_DATE DATE = '2025-07-01'; DECLARE @Ad_Expiry_DATE DATE = '2025-07-10'; -- Extended expiry DECLARE @Ai_SignedOnUser_ID INT = 456; -- Different admin user DECLARE @An_OldTransactionSeqEvent_NUMB BIGINT; -- Get current seq before update DECLARE @Ai_TransactionSeqEvent_NUMB BIGINT = 0; DECLARE @Ai_RowsAffected_NUMB INT; DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- Get current transaction sequence for concurrency check SELECT @An_OldTransactionSeqEvent_NUMB = TransactionSeqEvent_NUMB FROM dbo.Announcement WHERE Announcement_ID = @Ai_Announcement_ID; -- EXECUTE PROCEDURE EXEC [dbo].[Announcement_Update] @Ai_Announcement_ID = @Ai_Announcement_ID, @As_Title_TEXT = @As_Title_TEXT, @As_MessageBody_TEXT = @As_MessageBody_TEXT, @Ac_AnnouncementType_CODE = @Ac_AnnouncementType_CODE, @Ad_Start_DATE = @Ad_Start_DATE, @Ad_Expiry_DATE = @Ad_Expiry_DATE, @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @An_OldTransactionSeqEvent_NUMB = @An_OldTransactionSeqEvent_NUMB, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- CHECK RESULTS IF @Ac_Msg_CODE = 'S' PRINT 'Success! Rows updated: ' + CAST(@Ai_RowsAffected_NUMB AS VARCHAR); ELSE PRINT 'Error: ' + @As_DescriptionError_TEXT;
Announcement_Delete | DECLARE @Ai_Announcement_ID INT = 5; -- Announcement to delete DECLARE @Ai_SignedOnUser_ID INT = 789; -- Admin user performing deletion DECLARE @An_OldTransactionSeqEvent_NUMB BIGINT; -- Get current seq before delete DECLARE @Ai_TransactionSeqEvent_NUMB BIGINT = 0; DECLARE @Ai_RowsAffected_NUMB INT; DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- Get current transaction sequence for concurrency check SELECT @An_OldTransactionSeqEvent_NUMB = TransactionSeqEvent_NUMB FROM dbo.Announcement WHERE Announcement_ID = @Ai_Announcement_ID; -- EXECUTE PROCEDURE EXEC [dbo].[Announcement_Delete] @Ai_Announcement_ID = @Ai_Announcement_ID, @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @An_OldTransactionSeqEvent_NUMB = @An_OldTransactionSeqEvent_NUMB, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- CHECK RESULTS IF @Ac_Msg_CODE = 'S' PRINT 'Success! Rows deleted: ' + CAST(@Ai_RowsAffected_NUMB AS VARCHAR); ELSE PRINT 'Error: ' + @As_DescriptionError_TEXT;
Announcement_RetrieveAll | DECLARE @As_Search_TEXT NVARCHAR(255) = NULL; DECLARE @Ac_Type_CODE CHAR(1) = NULL; DECLARE @Ac_Status_CODE CHAR(1) = 'A'; -- Active only DECLARE @Ad_From_DATE DATE = null; DECLARE @Ad_To_DATE DATE = NULL; DECLARE @Ai_RowFrom_NUMB INT = 1; DECLARE @Ai_RowTo_NUMB INT = 10; DECLARE @As_SortColumn_TEXT NVARCHAR(50) = NULL; DECLARE @Ac_SortDirection_CODE CHAR(4) = NULL; DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- EXECUTE PROCEDURE EXEC [dbo].[Announcement_RetrieveAll] @As_Search_TEXT = @As_Search_TEXT, @Ac_Type_CODE = @Ac_Type_CODE, @Ac_Status_CODE = @Ac_Status_CODE, @Ad_From_DATE = @Ad_From_DATE, @Ad_To_DATE = @Ad_To_DATE, @Ai_RowFrom_NUMB = @Ai_RowFrom_NUMB, @Ai_RowTo_NUMB = @Ai_RowTo_NUMB, @As_SortColumn_TEXT = @As_SortColumn_TEXT, @Ac_SortDirection_CODE = @Ac_SortDirection_CODE, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- CHECK RESULTS IF @Ac_Msg_CODE = 'S' PRINT 'Procedure executed successfully'; ELSE PRINT 'Error: ' + @As_DescriptionError_TEXT;
Office$Sp_Insert_Office_S1 | DECLARE @Ai_Office_ID INT; DECLARE @Ai_Address_ID INT; DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure with sample values EXEC [dbo].[Office$Sp_Insert_Office_S1] @Ai_Organization_ID = 1, -- Organization ID (must exist in Organization table) @Ai_SubOrganization_ID = NULL, -- Optional sub-organization ID @As_OfficeName_TEXT = 'Main Headquarters',-- Office name @As_AddressLine1_TEXT = '123 Business St',-- Address line 1 @As_AddressLine2_TEXT = 'Suite 400', -- Optional address line 2 @Ai_City_ID = 123, -- City ID (must exist in reference table) @Ac_State_CODE = 'AK', -- State code (2 characters) @As_County_CODE = '001', -- County code @As_Zip_TEXT = '10001', -- Zip code @Ac_OfficeType_CODE = 'CC', -- Office type code (must exist in RefOfficeType) @Ai_TransactionSeqEvent_NUMB = NULL , @Ai_SignedOnUser_ID = 101, -- User ID of creator @Ai_Office_ID = @Ai_Office_ID OUTPUT, -- Output parameter for new Office ID @Ai_Address_ID = @Ai_Address_ID OUTPUT, -- Output parameter for new Address ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, -- Output status code (S=Success, F=Failure) @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Error description -- Check the results SELECT @Ai_Office_ID AS NewOfficeID, @Ai_Address_ID AS NewAddressID, @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS ErrorMessage;
Organization_Sp_Retrieve_All_S1 | DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure (default returns active organizations) EXEC [dbo].[Organization_Sp_Retrieve_All_S1] @Ac_Status_CODE = 'A', -- Optional: can be changed to filter by different status @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check execution status SELECT @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS ErrorMessage;
usp_Received_Referral_Get_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_Received_Referral_Get_S1 @As_Search_TEXT = NULL, @As_ReferralTitle_TEXT = NULL, @Ac_Status_CODE = NULL, @As_ClientName_TEXT = NULL, @Ai_Service_ID = NULL, @Ab_FollowUp_INDC = NULL, @Ai_Referral_ID = NULL, @Ai_Case_ID = NULL, @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @Ai_SignedOnUser_ID = 2066, -- 🔁 Replace with signed-on user's ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: Check status SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
usp_DetailedPlan_User_Get_S1 | DECLARE @Msg CHAR(1), @Err NVARCHAR(4000); EXEC dbo.usp_DetailedPlan_User_Get_S1 @Ai_SignedOnUser_ID = 12, -- replace with actual signed-on caseworker user ID @Ai_From_NUMB = 1, -- page number (1 = first page) @Ai_To_NUMB = 10, -- records per page @As_Search_TEXT = null, -- optional: search text across first, middle, last name @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @Err OUTPUT; -- Output status SELECT @Msg AS Msg_CODE, @Err AS Description;
usp_IssPlan_Goals_Get_S1 | DECLARE @Msg CHAR(1), @ErrMsg NVARCHAR(4000); EXEC usp_IssPlan_Goals_Get_S1 @Ai_Case_ID = 101, @Ai_IssPlan_ID = NULL, @Ai_IssGoal_ID = NULL, @Ac_Status_CODE = NULL, @Ai_From_NUMB = 1, @Ai_To_NUMB = 5, @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @ErrMsg OUTPUT; SELECT @Msg AS MsgCode, @ErrMsg AS Message;
usp_Goal_Add_S1 | DECLARE @Msg CHAR(1), @MsgText NVARCHAR(500), @GoalID INT; EXEC usp_Goal_Add_S1 @Ai_Case_ID = 97, @Ai_IssPlan_ID = 124, @As_GoalTitle_TEXT = 'Obtain Driver’s License', @As_GoalDescription_TEXT = 'Complete all steps required to receive a valid driver’s license', @Ac_Category_CODE = 'js', @Ac_Program_CODE = 'AD', @Ac_Service_CODE = null, @Ad_Due_DATE = '2025-10-01', @Ac_Status_CODE = 'N', @As_Notes_TEXT = 'Client to complete driving school first', @Ad_Completed_DTTM = NULL, @As_ActionItems_JSON = N' [ { "ActionDescription_TEXT": "Enroll in driving school", "DueDate_DATE": "2025-10-01", "ResponsibleParty_ID": 2099, "Program_CODE": "AD", "Referral_TEXT": "Refer to ABC Driving School", "Notes_TEXT": "Ask for weekday classes", "Status_CODE": "I" }, { "ActionDescription_TEXT": "Schedule driving test", "DueDate_DATE": "2025-10-20", "ResponsibleParty_ID": 2099, "Program_CODE": "AD", "Referral_TEXT": "", "Notes_TEXT": "After school certificate is obtained", "Status_CODE": "I" } ]', @Ai_CreatedBy_ID = 12, @An_TransactionSeqEvent_NUMB = 1, @Ai_IssGoal_ID = @GoalID OUTPUT, @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @Msg AS Msg, @MsgText AS Message, @GoalID AS NewGoalID;
IssGoal_Update_S1 | DECLARE @Ai_Goal_ID INT = 189, @As_GoalTitle_TEXT NVARCHAR(100) = 'Update Resume and Apply Jobs', @As_GoalDescription_TEXT NVARCHAR(500) = 'Update resume and submit to at least 5 positions', @Ac_Category_CODE CHAR(10) = 'EM', @Ac_Program_CODE CHAR(2) = 'YT', @Ac_Service_CODE CHAR(2) = NULL, @Ad_Due_DATE DATE = '2025-10-15', @Ac_Status_CODE CHAR(1) = 'N', @As_Notes_TEXT NVARCHAR(MAX) = 'Updated goal with timeline adjustment', @Ai_UpdatedBy_ID INT = 12, @An_TransactionSeqEvent_NUMB BIGINT = 1, @Aj_ActionItems_JSON NVARCHAR(MAX) = N' [ { "ActionDescription_TEXT": "Create updated resume", "DueDate_DATE": "2025-10-05", "ResponsibleParty_ID": 2099, "Status_CODE": "i", "Program_CODE": "YT", "Service_CODE": null, "Notes_TEXT": "Use career center template", "Referral_TEXT": "Referred by counselor" }, { "ActionDescription_TEXT": "Apply to 5 jobs", "DueDate_DATE": "2025-10-10", "ResponsibleParty_ID": 2099, "Status_CODE": "i", "Program_CODE": "YT", "Service_CODE": null, "Notes_TEXT": "Track submissions in notebook", "Referral_TEXT": "Indeed/LinkedIn" } ]', @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(500); EXEC dbo.IssGoal_Update_S1 @Ai_Goal_ID, @As_GoalTitle_TEXT, @As_GoalDescription_TEXT, @Ac_Category_CODE, @Ac_Program_CODE, @Ac_Service_CODE, @Ad_Due_DATE, @Ac_Status_CODE, @As_Notes_TEXT, @Ai_UpdatedBy_ID, @An_TransactionSeqEvent_NUMB, @Aj_ActionItems_JSON, @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @Ai_RowsAffected_NUMB AS RowsAffected;
IssGoal_Delete_S1 | DECLARE @GoalID INT = 53, -- Replace 123 with your actual IssGoal_ID @TransactionSeqEventNum BIGINT = 0, -- 0 means generate a new transaction event inside procedure @SignedOnUserID INT = 12, -- Replace 456 with the ID of the user performing the delete @MsgCode CHAR(1), @Description VARCHAR(4000); EXEC dbo.IssGoal_Delete_S1 @Ai_IssGoal_ID = @GoalID, @An_TransactionSeqEvent_NUMB = @TransactionSeqEventNum, @Ai_SignedOnUser_ID = @SignedOnUserID, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @Description OUTPUT; -- Check the output SELECT @MsgCode AS MsgCode, @Description AS Description;
IssGoal_UpdateStatus_S1 | DECLARE @GoalID INT = 52, -- Replace 123 with your actual IssGoal_ID @NewStatus CHAR(1) = 'C', -- Replace 'C' with the new status code you want to set @UpdatedByID INT = 12, -- Replace 456 with your user ID @CurrentTransactionSeqNum BIGINT = 1, -- Replace 7890 with the current TransactionSeqEvent_NUMB for this goal @MsgCode CHAR(1), @Description VARCHAR(4000); EXEC dbo.IssGoal_UpdateStatus_S1 @Ai_IssGoal_ID = @GoalID, @As_Status_CODE = @NewStatus, @Ai_UpdatedBy_ID = @UpdatedByID, @An_TransactionSeqEvent_NUMB = @CurrentTransactionSeqNum, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @Description OUTPUT; SELECT @MsgCode AS MsgCode, @Description AS Description;
Applicant_Get_With_Documents_S1 | -- DECLARE OUTPUT PARAMETERS DECLARE @Ac_Msg_CODE CHAR(5); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); DECLARE @Ai_SignedOnUser_ID INT = 16756; -- Replace with actual user ID DECLARE @Ai_RowFrom_NUMB INT = 1; -- Start from first record DECLARE @Ai_RowTo_NUMB INT = 20; -- Get first 20 records -- EXECUTE THE PROCEDURE EXEC [dbo].[Applicant_Get_With_Documents_S1] @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @Ai_RowFrom_NUMB = @Ai_RowFrom_NUMB, @Ai_RowTo_NUMB = @Ai_RowTo_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- CHECK RESULTS SELECT @Ac_Msg_CODE AS Status_Code, @As_DescriptionError_TEXT AS Error_Message;
usp_GoalActionItem_Add_S1 | DECLARE @ActionItem_ID INT, @MsgCode CHAR(1), @MsgText NVARCHAR(500); EXEC usp_GoalActionItem_Add_S1 @Ai_IssGoal_ID = 12, @Ai_IssPlan_ID = 1, @Ai_Case_ID = 101, @As_ActionDescription_TEXT = N'Schedule mock interview', @Ad_DueDate_DATE = '2025-07-10', @Ai_ResponsibleParty_ID = 12, @Ac_Program_CODE = 'AD', @Ac_Service_CODE = NULL, @As_Referral_TEXT = N'Referral to job coach', @As_Notes_TEXT = N'Follow up next week', @Ac_Status_CODE = 'A', @Ai_CreatedBy_ID = 1, @An_TransactionSeqEvent_NUMB = 1, @Ai_IssActionItem_ID = @ActionItem_ID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @ActionItem_ID AS ActionItem_ID, @MsgCode AS MsgCode, @MsgText AS Message;
usp_GoalActionItem_Update_S1 | DECLARE @ActionItemID INT = 4, -- Existing IssActionItem_ID to update @ActionDescription NVARCHAR(500) = N'Updated resume coaching step', @DueDate DATE = '2025-07-15', @ResponsiblePartyID INT = 12, @ProgramCode CHAR(2) = 'AD', @ServiceCode CHAR(2) = NULL, @ReferralText NVARCHAR(500) = N'Referral to career counselor', @NotesText NVARCHAR(4000) = N'Progressing well, next review in a week.', @StatusCode CHAR(1) = 'C', -- I = In Progress @UpdatedByID INT = 12, -- Signed-in user ID @TransactionSeqEvent_NUMB BIGINT = 0, -- Let procedure create new one if needed @RowsAffected INT, @MsgCode CHAR(1), @MsgText NVARCHAR(500); EXEC usp_GoalActionItem_Update_S1 @Ai_IssActionItem_ID = @ActionItemID, @As_ActionDescription_TEXT = @ActionDescription, @Ad_DueDate_DATE = @DueDate, @Ai_ResponsibleParty_ID = @ResponsiblePartyID, @Ac_Program_CODE = @ProgramCode, @Ac_Service_CODE = @ServiceCode, @As_Referral_TEXT = @ReferralText, @As_Notes_TEXT = @NotesText, @Ac_Status_CODE = @StatusCode, @Ai_UpdatedBy_ID = @UpdatedByID, @An_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB, -- ✅ Just pass it in @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @RowsAffected AS RowsAffected, @MsgCode AS MsgCode, @MsgText AS Description;
usp_GoalActionItem_Delete_S1 | DECLARE @RowsAffected INT, @MsgCode CHAR(1), @MsgText NVARCHAR(500), @TxnSeq BIGINT = 0; EXEC usp_GoalActionItem_Delete_S1 @Ai_IssActionItem_ID = 7, @An_TransactionSeqEvent_NUMB = @TxnSeq, @Ai_SignedOnUser_ID = 7, @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @RowsAffected AS RowsAffected, @MsgCode AS MsgCode, @MsgText AS Message;
usp_GoalActionItem_GetDetail_S1 | DECLARE @ActionItemID INT = 4, -- Replace with the actual ActionItem_ID you want to get details for @IssGoal_ID INT, @IssPlan_ID INT, @ActionDescription_TEXT NVARCHAR(500), @DueDate_DATE DATE, @ResponsibleParty_ID INT, @ResponsibleParty_TEXT NVARCHAR(100), @Program_CODE CHAR(2), @Program_DESC NVARCHAR(400), @Service_CODE CHAR(2), @Service_DESC NVARCHAR(400), @Referral_TEXT NVARCHAR(500), @Notes_TEXT NVARCHAR(4000), @Status_CODE CHAR(1), @Status_DESC NVARCHAR(100), @CreatedBy_ID INT, @UpdatedBy_ID INT, @Created_DTTM DATETIME, @Updated_DTTM DATETIME, @TransactionSeqEvent_NUMB BIGINT, @Msg_CODE CHAR(1), @DescriptionError_TEXT NVARCHAR(500); EXEC usp_GoalActionItem_GetDetail_S1 @Ai_IssActionItem_ID = @ActionItemID, @Ai_IssGoal_ID = @IssGoal_ID OUTPUT, @Ai_IssPlan_ID = @IssPlan_ID OUTPUT, @As_ActionDescription_TEXT = @ActionDescription_TEXT OUTPUT, @Ad_DueDate_DATE = @DueDate_DATE OUTPUT, @Ai_ResponsibleParty_ID = @ResponsibleParty_ID OUTPUT, @As_ResponsibleParty_TEXT = @ResponsibleParty_TEXT OUTPUT, @Ac_Program_CODE = @Program_CODE OUTPUT, @As_Program_DESC = @Program_DESC OUTPUT, @Ac_Service_CODE = @Service_CODE OUTPUT, @As_Service_DESC = @Service_DESC OUTPUT, @As_Referral_TEXT = @Referral_TEXT OUTPUT, @As_Notes_TEXT = @Notes_TEXT OUTPUT, @Ac_Status_CODE = @Status_CODE OUTPUT, @As_Status_DESC = @Status_DESC OUTPUT, @Ai_CreatedBy_ID = @CreatedBy_ID OUTPUT, @Ai_UpdatedBy_ID = @UpdatedBy_ID OUTPUT, @Ad_Created_DTTM = @Created_DTTM OUTPUT, @Ad_Updated_DTTM = @Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB OUTPUT, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- Optional: Display the results for verification SELECT @IssGoal_ID AS IssGoal_ID, @IssPlan_ID AS IssPlan_ID, @ActionDescription_TEXT AS ActionDescription, @DueDate_DATE AS DueDate, @ResponsibleParty_ID AS ResponsiblePartyID, @ResponsibleParty_TEXT AS ResponsiblePartyName, @Program_CODE AS ProgramCode, @Program_DESC AS ProgramDescription, @Service_CODE AS ServiceCode, @Service_DESC AS ServiceDescription, @Referral_TEXT AS ReferralText, @Notes_TEXT AS Notes, @Status_CODE AS StatusCode, @Status_DESC AS StatusDescription, @CreatedBy_ID AS CreatedByID, @UpdatedBy_ID AS UpdatedByID, @Created_DTTM AS CreatedDateTime, @Updated_DTTM AS UpdatedDateTime, @TransactionSeqEvent_NUMB AS TransactionSeqEventNumber, @Msg_CODE AS MessageCode, @DescriptionError_TEXT AS MessageDescription;
usp_GoalActionItem_UpdateStatus_S1 | DECLARE @IssActionItemID INT = 4, -- The ID of the action item you want to update @StatusCode CHAR(1) = 'C', -- New status code, e.g., 'C' for Completed @TransactionSeqEvent_NUMB BIGINT = 1, -- Your transaction sequence number @UpdatedByID INT = 12, -- User ID performing the update @RowsAffected INT, @MsgCode CHAR(1), @MsgText NVARCHAR(500); EXEC usp_GoalActionItem_UpdateStatus_S1 @Ai_IssActionItem_ID = @IssActionItemID, @Ac_Status_CODE = @StatusCode, @An_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB, @Ai_UpdatedBy_ID = @UpdatedByID, @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @RowsAffected AS RowsAffected, @MsgCode AS MsgCode, @MsgText AS Description;
usp_UserProgress_Milestones_Add_S1 | DECLARE @Json NVARCHAR(MAX) = N' [ { "MileStoneName_TEXT": "Initial Assesment", "OrderSeq_NUMB": 1, "Custom_INDC": 0 }, { "MileStoneName_TEXT": "carrer Planning", "OrderSeq_NUMB": 2, "Custom_INDC": 0 }, { "MileStoneName_TEXT": "Skill Training", "OrderSeq_NUMB": 3, "Custom_INDC": 0 }, { "MileStoneName_TEXT": "Employment", "OrderSeq_NUMB": 4, "Custom_INDC": 0 } ]'; DECLARE @MsgCode CHAR(1), @MsgText NVARCHAR(500), @ProgressID INT, @Txn BIGINT = 1; EXEC usp_UserProgress_Milestones_Add_S1 @Ai_Case_ID = 93, @Ac_Program_CODE = 'AD', @As_Milestones_JSON = @Json, @Ai_CreatedBy_ID = 2099, @An_TransactionSeqEvent_NUMB = @Txn, @Ai_UserProgress_ID = @ProgressID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @MsgCode AS MsgCode, @MsgText AS Message, @ProgressID AS UserProgressID;
usp_UserProgress_GetParticipants_S1 | DECLARE @SearchText NVARCHAR(100) = NULL, -- Optional: part of first/middle/last name @FromRow INT = 1, -- Paging start @ToRow INT = 10, -- Paging end @SignedOnUserID INT = 2099, -- Replace with actual logged-in user ID @MsgCode CHAR(1), @MsgText NVARCHAR(500); EXEC usp_UserProgress_GetParticipants_S1 @As_Search_TEXT = @SearchText, @Ai_From_NUMB = @FromRow, @Ai_To_NUMB = @ToRow, @Ai_SignedOnUser_ID = @SignedOnUserID, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; -- Check result SELECT @MsgCode AS MsgCode, @MsgText AS Description;
usp_UserProgress_Milestones_Get_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(500); EXEC usp_UserProgress_Milestones_Get_S1 @Ai_Case_ID = 93, -- Replace with actual Case_ID @Ac_Program_CODE = NULL, -- Or 'YT', 'AD', etc. if filtering by program @Ac_Status_CODE = NULL, -- Or 'A', 'C', etc. for Active, Completed, etc. @Ai_From_NUMB = 1, -- Paging start @Ai_To_NUMB = 10, -- Paging limit @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: view output message and description SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
usp_ProgressOutcome_Add_S1 | DECLARE @Ai_UserProgress_ID INT = 1, @As_EmploymentStatus_CODE CHAR(2) = 'FT', @As_WageIncrease_TEXT NVARCHAR(200) = 'Increased by 20%', @As_Skills_JSON NVARCHAR(MAX) = N'["Communication","Leadership"]', @As_Certification_JSON NVARCHAR(MAX) = N'["AWS Certified","PMP"]', @Ai_CreatedBy_ID INT = 1, @An_TransactionSeqEvent_NUMB BIGINT = 100001, @Ac_Msg_CODE CHAR(5), @As_Error_Description VARCHAR(4000); -- Execute the procedure EXEC usp_ProgressOutcome_Add_S1 @Ai_UserProgress_ID, @As_EmploymentStatus_CODE, @As_WageIncrease_TEXT, @As_Skills_JSON, @As_Certification_JSON, @Ai_CreatedBy_ID, @An_TransactionSeqEvent_NUMB, @Ac_Msg_CODE OUTPUT, @As_Error_Description OUTPUT; -- Show output values SELECT @Ac_Msg_CODE AS MsgCode, @As_Error_Description AS ErrorMessage;
usp_ProgressOutcome_Update_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_Error_Description VARCHAR(4000); EXEC usp_ProgressOutcome_Update_S1 @Ai_UserProgress_ID = 1 -- Replace with actual ID ,@Ac_EmploymentStatus_CODE = 'SE' -- 'SE' for "Seeking Employment" (example) ,@As_WageIncrease_TEXT = 'DGHRY' -- From the screenshot ,@As_Skills_JSON = '["Microsoft Office", "Customer Service", "Time Management"]' ,@As_Certification_JSON = '["Microsoft Office Specialist", "DHDRYJ"]' ,@Ai_UpdatedBy_ID = 2099 -- Assuming user ID 1 is updating ,@An_TransactionSeqEvent_NUMB = 1 -- Replace with actual event number ,@Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT ,@As_Error_Description = @As_Error_Description OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_Error_Description AS ErrorDescription;
usp_UserProgress_DeleteByCase_S1 | DECLARE @MsgCode CHAR(1), @ErrorMsg VARCHAR(4000); EXEC dbo.usp_UserProgress_DeleteByCase_S1 @Ai_Case_ID = 93, -- Replace with the actual Case_ID you want to soft-delete progress for @Ai_UpdatedBy_ID = 2099, -- Replace with the user ID performing the operation @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorMsg OUTPUT; -- Check result IF @MsgCode = 'S' PRINT 'UserProgress records soft-deleted successfully.'; ELSE PRINT 'Error: ' + ISNULL(@ErrorMsg, 'Unknown error occurred.');
usp_ProgressOutcome_Get_S1 | DECLARE @MsgCode CHAR(5), @ErrorDesc VARCHAR(4000); -- Example: Calling with a specific UserProgress_ID EXEC dbo.usp_ProgressOutcome_Get_S1 @Ai_UserProgress_ID = 1, -- Replace with actual UserProgress_ID @Ai_Case_ID = NULL, -- Optional, can be NULL @Ac_Msg_CODE = @MsgCode OUTPUT, @As_Error_Description = @ErrorDesc OUTPUT; -- Check the results IF @MsgCode = 'S' PRINT 'Data fetched successfully.'; ELSE PRINT 'Error occurred: ' + ISNULL(@ErrorDesc, 'Unknown error');
usp_ProgressMilestones_UpdateStatus_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_ProgressMilestones_UpdateStatus_S1 @Ai_Case_ID = 93, -- Replace with actual Case_ID @As_Milestones_JSON = N'[ { "MileStone_ID": 1, "Status_code": "C", "Notes_TEXT": "Completed on time" }, { "MileStone_ID": 2, "Status_code": "P", "Notes_TEXT": "Pending external review" }, { "MileStone_ID": 3, "Status_code": "C", "Notes_TEXT": "Not started yet" } ]', @Ac_CaseStatus_CODE = 'A', -- e.g., 'A' for Active, 'C' for Closed @Ai_UpdatedBy_ID = 2099, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ProgressMilestones_Notes_List_S1 | DECLARE @MsgCode CHAR(1), @ErrorMessage VARCHAR(4000); EXEC dbo.usp_ProgressMilestones_Notes_List_S1 @Ac_Program_CODE = NULL, -- Or e.g., 'YT' @Ai_Case_ID = 93, -- Replace with actual Case_ID @Ai_From_NUMB = 1, -- Start row @Ai_To_NUMB = 10, -- End row @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorMessage OUTPUT; -- Output message PRINT 'Message Code: ' + @MsgCode; PRINT 'Description: ' + ISNULL(@ErrorMessage, 'No message returned.');
usp_Get_CaseNote_s3 | DECLARE @MsgCode VARCHAR(5), @ErrMsg VARCHAR(4000); EXEC dbo.usp_Get_CaseNote_s3 @Ai_Case_ID = 14, @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrMsg OUTPUT; PRINT 'Message Code: ' + @MsgCode; PRINT 'Error/Success Message: ' + @ErrMsg;
Applicant$Sp_GetAllApplicants | DECLARE @Ai_SignedOnWorker_ID INT DECLARE @Ac_Msg_CODE CHAR(1) DECLARE @As_DescriptionError_TEXT VARCHAR(4000) -- Step 2: Execute the procedure EXEC dbo.Applicant$Sp_GetAllApplicants @Ai_SignedOnWorker_ID = 1, @Ai_RowFrom_NUMB = 1, @Ai_RowTo_NUMB = 10, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT -- Step 3: Check execution status IF @Ac_Msg_CODE = 'S' BEGIN PRINT 'Procedure executed successfully' -- The result set with applicants is automatically returned END ELSE IF @Ac_Msg_CODE = 'F' BEGIN PRINT 'Procedure failed with error: ' + @As_DescriptionError_TEXT END ELSE BEGIN PRINT 'Unknown status code: ' + @Ac_Msg_CODE END
usp_ApplicantDocument_UpdateVerificationStatus_S1 | DECLARE @Ai_ApplicantDocument_ID INT = 2, -- Document ID to update @Ac_VerificationStatus_CODE CHAR(1) = 'V', -- New status ('V'=Verified, 'R'=Rejected, etc.) @As_VerificationComment_TEXT NVARCHAR(500) = 'Document meets all requirements', -- Optional comment @Ai_UpdatedBy_ID INT = 678, -- User ID performing verification @An_TransactionSeqEvent_NUMB BIGINT = 1234567890, -- Transaction sequence number @Ai_RowsAffected_NUMB INT, -- Output: Number of rows updated @Ac_Msg_CODE CHAR(1), -- Output: 'S' or 'F' @As_DescriptionError_TEXT VARCHAR(4000); -- Output: Error message EXEC usp_ApplicantDocument_UpdateVerificationStatus_S1 @Ai_ApplicantDocument_ID = @Ai_ApplicantDocument_ID, @Ac_VerificationStatus_CODE = @Ac_VerificationStatus_CODE, @An_OldTransactionSeqEvent_NUMB = 1, @As_VerificationComment_TEXT = @As_VerificationComment_TEXT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS ResultCode, @As_DescriptionError_TEXT AS ErrorMessage;
usp_ApplicantDocument_UpdateMetadata_S1 | DECLARE @Ai_ApplicantDocument_ID INT = 2, -- Document ID to update @As_FileName_TEXT NVARCHAR(255) = 'UpdatedDocument.pdf', -- New file name @Ac_DocumentType_CODE CHAR(2) = 'DT', -- New document type code @Ai_UpdatedBy_ID INT = 456, -- User ID performing the update @An_TransactionSeqEvent_NUMB BIGINT = 987654321, -- Transaction sequence number @Ai_RowsAffected_NUMB INT, -- Output: Number of rows updated @Ac_Msg_CODE CHAR(1), -- Output: 'S' or 'F' @As_DescriptionError_TEXT VARCHAR(4000); -- Output: Error message EXEC usp_ApplicantDocument_UpdateMetadata_S1 @Ai_ApplicantDocument_ID = @Ai_ApplicantDocument_ID, @As_FileName_TEXT = @As_FileName_TEXT, @Ac_DocumentType_CODE = @Ac_DocumentType_CODE, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB = 1, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS ResultCode, @As_DescriptionError_TEXT AS ErrorMessage;
dbo.CustomReport$SPGetCusReports | --For Getting All Reports DECLARE @Msg CHAR(1), @ErrorDesc VARCHAR(4000); EXEC dbo.CustomReport$SPGetCusReports @Ai_SignedOnUser_ID = 2, @Ac_TabType_TEXT = 'All', @As_SearchName_TEXT = Null, @Ai_RowFrom_NUMB = 1, @Ai_RowTo_NUMB = 10, @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; SELECT Status = @Msg, Error_Description = @ErrorDesc; --For Getting My Reports DECLARE @Msg CHAR(1), @ErrorDesc VARCHAR(4000); EXEC dbo.CustomReport$SPGetCusReports @Ai_SignedOnUser_ID = 2, @Ac_TabType_TEXT = 'My', @As_SearchName_TEXT = 'Report 10', @Ai_RowFrom_NUMB = 1, @Ai_RowTo_NUMB = 10, @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; SELECT Status = @Msg, Error_Description = @ErrorDesc;
dbo.CustomReport$CreateNewCustomReport | DECLARE @NewReportID INT, @MsgCode CHAR(1), @ErrorDescription VARCHAR(4000); EXEC dbo.CustomReport$CreateNewCustomReport @As_ReportName_TEXT = 'Client Report New', @As_ReportDescription_TEXT = N'Report desc', @As_ClientProfileFields_TEXT = 'Applicant_Status,Eligibility_Status', @Ai_SignedOnUser_ID = 1, @An_TransactionSeqEvent_NUMB = 2002, @Ai_NewReportID_ID = @NewReportID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Optional: See the output SELECT @NewReportID AS NewReportID, @MsgCode AS MsgCode, @ErrorDescription AS ErrorMessage;
dbo.CustomReport$CheckReportNameAvailability | /* Check 1: Empty report name */ DECLARE @Status CHAR(1), @ErrorMsg VARCHAR(4000); EXEC dbo.CustomReport$CheckReportNameAvailability @As_ProposedName_TEXT = '', @Ai_SignedOnUser_ID = 1, @Ac_Msg_CODE = @Status OUTPUT, @As_DescriptionError_TEXT = @ErrorMsg OUTPUT; SELECT @Status AS [Status], @ErrorMsg AS [ErrorMsg]; /* Check 2: Name longer than 100 characters */ DECLARE @Status CHAR(1), @ErrorMsg VARCHAR(4000); EXEC dbo.CustomReport$CheckReportNameAvailability @As_ProposedName_TEXT = 'ThisIsAVeryLongReportNameThatExcee dsTheMaximumAllowedLengthOfOneHundredCharactersForValidationTesting', @Ai_SignedOnUser_ID = 1, @Ac_Msg_CODE = @Status OUTPUT, @As_DescriptionError_TEXT = @ErrorMsg OUTPUT; SELECT @Status AS [Status], @ErrorMsg AS [ErrorMsg]; /* Check 3: Unique report name (should be available) */ DECLARE @Status CHAR(1), @ErrorMsg VARCHAR(4000); EXEC dbo.CustomReport$CheckReportNameAvailability @As_ProposedName_TEXT = 'UniqueReportName123', @Ai_SignedOnUser_ID = 1, @Ac_Msg_CODE = @Status OUTPUT, @As_DescriptionError_TEXT = @ErrorMsg OUTPUT; SELECT @Status AS [Status], @ErrorMsg AS [ErrorMsg]; /* Check 4: Existing report name (should suggest alternatives) */ DECLARE @Status CHAR(1), @ErrorMsg VARCHAR(4000); EXEC dbo.CustomReport$CheckReportNameAvailability @As_ProposedName_TEXT = 'ExistingReport', @Ai_SignedOnUser_ID = 1, @Ac_Msg_CODE = @Status OUTPUT, @As_DescriptionError_TEXT = @ErrorMsg OUTPUT; SELECT @Status AS [Status], @ErrorMsg AS [ErrorMsg]; /* Check 5: Find similar names */ DECLARE @Status CHAR(1), @ErrorMsg VARCHAR(4000); EXEC dbo.CustomReport$CheckReportNameAvailability @As_ProposedName_TEXT = 'Sales', @Ai_SignedOnUser_ID = 1, @Ac_Msg_CODE = @Status OUTPUT, @As_DescriptionError_TEXT = @ErrorMsg OUTPUT; SELECT @Status AS [Status], @ErrorMsg AS [ErrorMsg]; /* Check 6: Special characters in name */ DECLARE @Status CHAR(1), @ErrorMsg VARCHAR(4000); EXEC dbo.CustomReport$CheckReportNameAvailability @As_ProposedName_TEXT = 'Revenue_Report-(Q3)', @Ai_SignedOnUser_ID = 1, @Ac_Msg_CODE = @Status OUTPUT, @As_DescriptionError_TEXT = @ErrorMsg OUTPUT; SELECT @Status AS [Status], @ErrorMsg AS [ErrorMsg];
dbo.CustomReport$GetReportForView | DECLARE @MsgCode CHAR(1), @ErrorDesc VARCHAR(4000) EXEC dbo.CustomReport$GetReportForView @Ai_CustomReport_ID = 16, @Ai_SignedOnUser_ID = 1, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Check results select @MsgCode As Msg_code, @ErrorDesc As Error_Description select * from customreport;
dbo.CustomReport$Sp_ExportReport | DECLARE @MsgCode CHAR(1), @ErrDesc VARCHAR(4000); EXEC dbo.CustomReport$Sp_ExportReport @Ai_CustomReport_ID = 16, @Ai_SignedOnUser_ID = 2, @As_Format_CODE = 'XCEL', @An_TransactionSeqEvent_NUMB = 990, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrDesc OUTPUT; SELECT @MsgCode AS Status, @ErrDesc AS Message; select * from customreport; select * from ReportDownload;
dbo.CustomReport$RecordReportView | DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.CustomReport$RecordReportView @Ai_CustomReport_ID = 12, -- Example Report ID @Ai_SignedOnUser_ID = 1, -- Example User ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display the output values SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
dbo.CustomReport$UpdateCustomReport | DECLARE @MsgCode CHAR(1), @ErrorDescription VARCHAR(4000); EXEC dbo.CustomReport$UpdateCustomReport @Ai_ReportID_ID = 9, @Ai_SignedOnUser_ID = 1, @As_ReportName_TEXT = 'ExistingReport', @As_ReportDescription_TEXT = 'New description', @As_ClientProfileFields_TEXT = 'Program_Type,Submission_Date,Phone_Number', @Ai_UpdatedBy_ID = 2044, @An_NewTransactionSeqEvent_NUMB = 300, @An_OldTransactionSeqEvent_NUMB = 3001, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; SELECT @MsgCode AS Status, @ErrorDescription AS Message; select * from CustomReport
dbo.CustomReport$DeleteReport | DECLARE @MsgCode CHAR(1); DECLARE @MsgText VARCHAR(4000); EXEC dbo.CustomReport$DeleteReport @Ai_CustomReport_ID = 1, @Ai_SignedOnUser_ID = 1, @An_TransactionSeqEvent_NUMB = 1, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @MsgCode AS MsgCode, @MsgText AS MsgText;
Users$Sp_Get_UserInfo | DECLARE -- Input parameters @Ai_InputUser_ID INT = 2, -- Replace with actual user ID -- Output parameters (all parameters from the procedure) @Ai_User_ID INT, @As_Username_TEXT NVARCHAR(100), @As_FirstName_TEXT NVARCHAR(100), @As_MiddleName_TEXT NVARCHAR(100), @As_LastName_TEXT NVARCHAR(100), @Ad_BirthDate_DATE DATE, @As_SSN_TEXT CHAR(9), @As_PhoneNumber_TEXT NVARCHAR(20), @As_EmailAddress_TEXT NVARCHAR(255), @As_ProfileURL_TEXT NVARCHAR(400), @Ac_Gender_CODE CHAR(1), @As_GenderDesc_TEXT NVARCHAR(50), @Ac_UserType_CODE CHAR(1), @As_UserTypeDesc_TEXT NVARCHAR(50), @Ai_CreatedBy_ID INT, @Ld_Created_DTTM DATETIME2, @Ai_UpdatedBy_ID INT, @Ld_Updated_DTTM DATETIME2, @An_TransactionSeqEvent_NUMB BIGINT, @Ab_TwoFactorEnabled_INDC BIT, @Ab_IsLocked_INDC BIT, @Ad_LastPasswordChange_DTTM DATETIME2, @Ai_LoginCount_NUMB INT, @Ad_LastLogin_DTTM DATETIME2, @Ai_Role_ID INT, @Ac_Role_CODE CHAR(10), @As_RoleDesc_TEXT NVARCHAR(100), @Ai_Office_ID INT, @As_OfficeName_TEXT NVARCHAR(100), @Ac_OfficeCounty_CODE CHAR(10), @As_OfficeCountyName_TEXT NVARCHAR(100), @Ac_OfficeType_CODE CHAR(10), @As_OfficeTypeDesc_TEXT NVARCHAR(100), @Ac_EmploymentStatus_CODE CHAR(2), @As_EmploymentStatusDesc_TEXT NVARCHAR(100), @Ac_AccountStatus_CODE CHAR(1), @As_AccountStatusDesc_TEXT NVARCHAR(50), @Ab_ForceReset_INDC BIT, @As_AddressLine1_TEXT NVARCHAR(200), @As_AddressLine2_TEXT NVARCHAR(200), @As_City_TEXT NVARCHAR(100), @Ac_State_CODE CHAR(2), @As_PostalCode_TEXT NVARCHAR(20), @Ac_Country_CODE CHAR(2), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_Get_UserInfo @Ai_InputUser_ID = @Ai_InputUser_ID, @As_InputEmailAddress_TEXT = NULL, @Ai_User_ID = @Ai_User_ID OUTPUT, @As_Username_TEXT = @As_Username_TEXT OUTPUT, @As_FirstName_TEXT = @As_FirstName_TEXT OUTPUT, @As_MiddleName_TEXT = @As_MiddleName_TEXT OUTPUT, @As_LastName_TEXT = @As_LastName_TEXT OUTPUT, @Ad_BirthDate_DATE = @Ad_BirthDate_DATE OUTPUT, @As_SSN_TEXT = @As_SSN_TEXT OUTPUT, @As_PhoneNumber_TEXT = @As_PhoneNumber_TEXT OUTPUT, @As_EmailAddress_TEXT = @As_EmailAddress_TEXT OUTPUT, @As_ProfileURL_TEXT = @As_ProfileURL_TEXT OUTPUT, @Ac_Gender_CODE = @Ac_Gender_CODE OUTPUT, @As_GenderDesc_TEXT = @As_GenderDesc_TEXT OUTPUT, @Ac_UserType_CODE = @Ac_UserType_CODE OUTPUT, @As_UserTypeDesc_TEXT = @As_UserTypeDesc_TEXT OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @Ld_Created_DTTM = @Ld_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @Ld_Updated_DTTM = @Ld_Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ab_TwoFactorEnabled_INDC = @Ab_TwoFactorEnabled_INDC OUTPUT, @Ab_IsLocked_INDC = @Ab_IsLocked_INDC OUTPUT, @Ad_LastPasswordChange_DTTM = @Ad_LastPasswordChange_DTTM OUTPUT, @Ai_LoginCount_NUMB = @Ai_LoginCount_NUMB OUTPUT, @Ad_LastLogin_DTTM = @Ad_LastLogin_DTTM OUTPUT, @Ai_Role_ID = @Ai_Role_ID OUTPUT, @Ac_Role_CODE = @Ac_Role_CODE OUTPUT, @As_RoleDesc_TEXT = @As_RoleDesc_TEXT OUTPUT, @Ai_Office_ID = @Ai_Office_ID OUTPUT, @As_OfficeName_TEXT = @As_OfficeName_TEXT OUTPUT, @Ac_OfficeCounty_CODE = @Ac_OfficeCounty_CODE OUTPUT, @As_OfficeCountyName_TEXT = @As_OfficeCountyName_TEXT OUTPUT, @Ac_OfficeType_CODE = @Ac_OfficeType_CODE OUTPUT, @As_OfficeTypeDesc_TEXT = @As_OfficeTypeDesc_TEXT OUTPUT, @Ac_EmploymentStatus_CODE = @Ac_EmploymentStatus_CODE OUTPUT, @As_EmploymentStatusDesc_TEXT = @As_EmploymentStatusDesc_TEXT OUTPUT, @Ac_AccountStatus_CODE = @Ac_AccountStatus_CODE OUTPUT, @As_AccountStatusDesc_TEXT = @As_AccountStatusDesc_TEXT OUTPUT, @Ab_ForceReset_INDC = @Ab_ForceReset_INDC OUTPUT, @As_AddressLine1_TEXT = @As_AddressLine1_TEXT OUTPUT, @As_AddressLine2_TEXT = @As_AddressLine2_TEXT OUTPUT, @As_City_TEXT = @As_City_TEXT OUTPUT, @Ac_State_CODE = @Ac_State_CODE OUTPUT, @As_PostalCode_TEXT = @As_PostalCode_TEXT OUTPUT, @Ac_Country_CODE = @Ac_Country_CODE OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the result SELECT @Ac_Msg_CODE AS ResultCode, @As_DescriptionError_TEXT AS ResultMessage, @Ai_User_ID AS UserID, @As_Username_TEXT AS Username, @As_FirstName_TEXT AS FirstName, @As_LastName_TEXT AS LastName, @As_EmailAddress_TEXT AS Email, @As_ProfileURL_TEXT as logo;
usp_TwoFactorDevice_Add_S1 | DECLARE @DeviceID INT; DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); EXEC dbo.usp_TwoFactorDevice_Add_S1 @Ai_User_ID = 1, -- User ID to register device for @Ac_MethodCode_CODE = 'TO', -- 'TO' for TOTP method @As_SecretBase_TEXT = 'JBSWY3DPEHPK3PXP', -- Base32 secret @As_DeviceName_TEXT = 'My Auth App', -- Optional device name @Ai_CreatedBy_ID = 1, -- User ID of creator (often same as user) @Ai_TransactionSeqEvent_NUMB = NULL, -- Optional transaction sequence @Ai_Device_ID = @DeviceID OUTPUT, -- Returns new device ID @Ac_Msg_CODE = @MsgCode OUTPUT, -- Returns 'S' or 'F' @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Returns status/error message -- Check results SELECT @DeviceID AS DeviceID, @MsgCode AS MsgCode, @ErrorDesc AS ErrorDescription;
usp_TwoFactorDevice_UpdateStatus_S1 | DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); -- Execute the update (example: deactivating a device) EXEC dbo.usp_TwoFactorDevice_UpdateStatus_S1 @Ai_Device_ID = 3, -- Device ID to update @Ab_IsActive_INDC = 0, -- Set to 0 to deactivate, 1 to activate @An_OldTransactionSeqEvent_NUMB = 603, -- Current version @An_NewTransactionSeqEvent_NUMB = null, -- New version @Ai_UpdatedBy_ID = 1, -- User ID performing the update @Ac_Msg_CODE = @MsgCode OUTPUT, -- Returns 'S' or 'F' @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Returns status/error message -- Check results SELECT @MsgCode AS StatusCode, @ErrorDesc AS Message;
usp_TwoFactorDevice_Get_S1 | DECLARE @DeviceID INT = 1; -- Replace with actual device ID DECLARE @UserID INT = 1; -- Alternative: could specify user ID instead -- Declare output variables DECLARE @OutDeviceID INT; DECLARE @MethodCode CHAR(2); DECLARE @MethodDesc NVARCHAR(100); DECLARE @SecretBase NVARCHAR(64); DECLARE @DeviceName NVARCHAR(100); DECLARE @IsActive BIT; DECLARE @IssuedDTTM DATETIME2; DECLARE @LastUsedDTTM DATETIME2; DECLARE @CreatedByID INT; DECLARE @CreatedDTTM DATETIME2; DECLARE @UpdatedByID INT; DECLARE @UpdatedDTTM DATETIME2; DECLARE @TransactionSeq BIGINT; DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); -- Execute the procedure EXEC dbo.usp_TwoFactorDevice_Get_S1 @Ai_InputDevice_ID = @DeviceID, @Ai_User_ID = @UserID, @Ai_Device_ID = @OutDeviceID OUTPUT, @Ac_MethodCode_CODE = @MethodCode OUTPUT, @As_MethodDesc_TEXT = @MethodDesc OUTPUT, @As_SecretBase_TEXT = @SecretBase OUTPUT, @As_DeviceName_TEXT = @DeviceName OUTPUT, @Ab_IsActive_INDC = @IsActive OUTPUT, @Ad_Issued_DTTM = @IssuedDTTM OUTPUT, @Ad_LastUsed_DTTM = @LastUsedDTTM OUTPUT, @Ai_CreatedBy_ID = @CreatedByID OUTPUT, @Ad_Created_DTTM = @CreatedDTTM OUTPUT, @Ai_UpdatedBy_ID = @UpdatedByID OUTPUT, @Ad_Updated_DTTM = @UpdatedDTTM OUTPUT, @Ai_TransactionSeqEvent_NUMB = @TransactionSeq OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Display results SELECT @MsgCode AS StatusCode, @ErrorDesc AS Message, @OutDeviceID AS DeviceID, @MethodCode AS MethodCode, @MethodDesc AS MethodDescription, @DeviceName AS DeviceName, @IsActive AS IsActive, @IssuedDTTM AS IssuedDate, @LastUsedDTTM AS LastUsedDate, @CreatedByID AS CreatedBy, @CreatedDTTM AS CreatedDate, @UpdatedByID AS UpdatedBy, @UpdatedDTTM AS UpdatedDate, @TransactionSeq AS TransactionSequence;
usp_TwoFactorDevice_Update_S1 | DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); DECLARE @NewTransactionSeq BIGINT; -- First get the current TransactionSeqEvent_NUMB for the device DECLARE @CurrentTransactionSeq BIGINT; SELECT @CurrentTransactionSeq = TransactionSeqEvent_NUMB FROM dbo.TwoFactorDevice WHERE Device_ID = 3; -- Replace with actual device ID -- Execute the update procedure EXEC dbo.usp_TwoFactorDevice_Update_S1 @Ai_Device_ID = 3, -- Device ID to update @As_DeviceName_TEXT = 'My Updated Device', -- New device name @As_SecretBase_TEXT = 'NEWSECRETBASE32KEY',-- New Base32 secret @Ai_UpdatedBy_ID = 456, -- User ID performing the update @An_OldTransactionSeqEvent_NUMB = @CurrentTransactionSeq, -- Current version @An_NewTransactionSeqEvent_NUMB = @NewTransactionSeq , -- New version (auto-generated if NULL) @Ac_Msg_CODE = @MsgCode OUTPUT, -- Returns 'S' or 'F' @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Returns status/error message -- Check results SELECT @MsgCode AS StatusCode, @ErrorDesc AS Message;
usp_TwoFactorRecoveryCode_Add_S1 | DECLARE @RecoveryCodeID INT; DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); DECLARE @TransactionSeq BIGINT = NULL; -- Will be generated if NULL -- Execute the procedure to add a recovery code EXEC dbo.usp_TwoFactorRecoveryCode_Add_S1 @Ai_UserID = 1, -- User ID the code is for @Ai_Device_ID = 3, -- Associated 2FA device ID @As_RecoveryCode_TEXT = 'A1B2C3D4', -- 8-character recovery code @Ai_CreatedBy_ID = 1, -- User ID creating the code @Ai_TransactionSeqEvent_NUMB = @TransactionSeq, -- Transaction sequence (auto-generated if NULL) @Ai_RecoveryCodeID = @RecoveryCodeID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Check results SELECT @MsgCode AS StatusCode, @ErrorDesc AS Message, @RecoveryCodeID AS NewRecoveryCodeID, @TransactionSeq AS TransactionSequenceNumber;
usp_TwoFactorVerificationLog_Add_S1 | DECLARE @LogID INT; DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); DECLARE @TransactionSeq BIGINT = NULL; -- Will be generated if NULL -- Example 1: Successful OTP verification (6-digit code) EXEC dbo.usp_TwoFactorVerificationLog_Add_S1 @Ai_User_ID = 1, -- User ID attempting verification @Ai_Device_ID = 3, -- Device used (NULL if recovery code) @As_CodeEntered_TEXT = '123456', -- 6-digit OTP or 8-char recovery code @Ac_Result_CODE = 'S', -- 'S'=Success, 'F'=Failure @As_IPAddress_TEXT = '192.168.1.1', -- Optional client IP @As_UserAgent_TEXT = 'Mozilla/5.0', -- Optional user agent @Ai_CreatedBy_ID = 1, -- Typically same as user ID @Ai_TransactionSeqEvent_NUMB = @TransactionSeq, -- Auto-generated if NULL @Ai_LogID = @LogID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Check results SELECT @MsgCode AS StatusCode, @ErrorDesc AS Message, @LogID AS NewLogEntryID, @TransactionSeq AS TransactionSequenceNumber; -- Example 2: Failed recovery code attempt (8-char code) EXEC dbo.usp_TwoFactorVerificationLog_Add_S1 @Ai_User_ID = 1, @Ai_Device_ID = 3, -- NULL indicates recovery code was used @As_CodeEntered_TEXT = 'ABCD1234', @Ac_Result_CODE = 'F', -- Failed attempt @As_IPAddress_TEXT = '10.0.0.1', @Ai_CreatedBy_ID = 1, @Ai_TransactionSeqEvent_NUMB = NULL, -- Will auto-generate @Ai_LogID = @LogID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT;
usp_TwoFactorRecoveryCode_Get_S1 | DECLARE @RecoveryCodeID INT = 2; -- The recovery code ID to retrieve DECLARE @UserID INT = 1; -- User ID the code belongs to DECLARE @DeviceID INT = 3; -- Device ID the code is associated with -- Output variables DECLARE @OutRecoveryCodeID INT; DECLARE @RecoveryCode NVARCHAR(100); DECLARE @IsUsed BIT; DECLARE @CreatedByID INT; DECLARE @CreatedDate DATETIME; DECLARE @UpdatedByID INT; DECLARE @UpdatedDate DATETIME; DECLARE @TransactionSeq BIGINT; DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); -- Execute the procedure EXEC dbo.usp_TwoFactorRecoveryCode_Get_S1 @Ai_Input_RecoveryCode_ID = @RecoveryCodeID, @Ai_User_ID = @UserID, @Ai_Device_ID = @DeviceID, @Ai_RecoveryCode_ID = @OutRecoveryCodeID OUTPUT, @As_RecoveryCode_TEXT = @RecoveryCode OUTPUT, @Ab_IsUsed_INDC = @IsUsed OUTPUT, @Ai_CreatedBy_ID = @CreatedByID OUTPUT, @Ad_Created_DTTM = @CreatedDate OUTPUT, @Ai_UpdatedBy_ID = @UpdatedByID OUTPUT, @Ad_Updated_DTTM = @UpdatedDate OUTPUT, @Ai_TransactionSeqEvent_NUMB = @TransactionSeq OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Display results (in production, handle securely) SELECT CASE WHEN @MsgCode = 'S' THEN 'Success' ELSE 'Failure' END AS Status, @ErrorDesc AS Message, @OutRecoveryCodeID AS RecoveryCodeID, CASE WHEN @MsgCode = 'S' THEN @RecoveryCode ELSE '***' END AS RecoveryCode, CASE WHEN @IsUsed = 1 THEN 'Used' ELSE 'Active' END AS Status, @CreatedByID AS CreatedByUserID, FORMAT(@CreatedDate, 'yyyy-MM-dd HH:mm:ss') AS CreatedDate, @UpdatedByID AS LastUpdatedByUserID, FORMAT(@UpdatedDate, 'yyyy-MM-dd HH:mm:ss') AS LastUpdatedDate, @TransactionSeq AS TransactionSequence;
usp_TwoFactorRecoveryCode_Update_S1 | DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); DECLARE @NewTransactionSeq BIGINT = NULL; -- First get the current TransactionSeqEvent_NUMB for the recovery code DECLARE @CurrentTransactionSeq BIGINT; SELECT @CurrentTransactionSeq = TransactionSeqEvent_NUMB FROM dbo.TwoFactorRecoveryCode WHERE RecoveryCode_ID = 1; -- Replace with actual recovery code ID -- Execute the update (example: marking code as used) EXEC dbo.usp_TwoFactorRecoveryCode_Update_S1 @Ai_RecoveryCode_ID = 1, -- Recovery code ID to update @Ab_IsUsed_INDC = 1, -- 1 = mark as used, 0 = mark as unused @An_OldTransactionSeqEvent_NUMB = @CurrentTransactionSeq, -- Current version @An_NewTransactionSeqEvent_NUMB = @NewTransactionSeq, -- New version (auto-generated if NULL) @Ai_UpdatedBy_ID = 1, -- User ID performing the update @Ac_Msg_CODE = @MsgCode OUTPUT, -- Returns 'S', 'L', or 'F' @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Check results SELECT CASE @MsgCode WHEN 'S' THEN 'Success' WHEN 'L' THEN 'Concurrency Conflict' ELSE 'Failure' END AS Status, @ErrorDesc AS Message, @NewTransactionSeq AS NewTransactionSequence, @CurrentTransactionSeq AS OldTransactionSequence;
usp_TwoFactorDevice_GetAll_S1 | DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_TwoFactorDevice_GetAll_S1 @Ai_User_ID = 1, -- Replace with a valid User_ID @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the output values SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
Users$Sp_Update_PersonalInfo | DECLARE @Ai_RowsAffected_NUMB INT; DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); DECLARE @An_NewTransactionSeqEvent_NUMB BIGINT; -- Replace these with actual values DECLARE @Ai_User_ID INT = 1; DECLARE @As_FirstName_TEXT VARCHAR(50) = 'John'; DECLARE @As_MiddleName_TEXT VARCHAR(50) = 'A'; DECLARE @As_LastName_TEXT VARCHAR(50) = 'Doe'; DECLARE @Ad_BirthDate_DATE DATE = '1990-01-01'; DECLARE @As_PhoneNumber_TEXT VARCHAR(20) = '(123) 456-7890'; DECLARE @Ai_UpdatedBy_ID INT = 2; DECLARE @An_OldTransactionSeqEvent_NUMB BIGINT = 1; -- get from Users table -- Execute procedure EXEC dbo.Users$Sp_Update_PersonalInfo @Ai_User_ID, @As_FirstName_TEXT, @As_MiddleName_TEXT, @As_LastName_TEXT, @Ad_BirthDate_DATE, @As_PhoneNumber_TEXT, @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- View output results SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Users$Sp_Update_Password | DECLARE @Ai_User_ID INT = 1, -- Replace with actual User_ID @As_CurrentPassword_TEXT VARCHAR(200) = 'OldPass123!', @As_NewPassword_TEXT VARCHAR(200) = 'NewPass@456', @As_ConfirmNewPassword_TEXT VARCHAR(200) = 'NewPass@456', @Ai_UpdatedBy_ID INT = 101, -- Usually same as user, or admin ID @An_OldTransactionSeqEvent_NUMB BIGINT = 10000000001, -- Get current value from Users table @An_NewTransactionSeqEvent_NUMB BIGINT = NULL, @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure EXEC dbo.Users$Sp_Update_Password @Ai_User_ID, @As_CurrentPassword_TEXT, @As_NewPassword_TEXT, @As_ConfirmNewPassword_TEXT, @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeqEvent, @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Users$Sp_Update_TwoFactorDevice | DECLARE @Ai_Device_ID INT, @An_NewTransactionSeqEvent_NUMB BIGINT = NULL, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Replace these values with actual data DECLARE @Ai_User_ID INT = 1, @Ab_TwoFactorEnabled_INDC BIT = 1, @Ac_MethodCode_CODE CHAR(2) = 'TO', -- e.g., 'TO' for TOTP @As_DeviceName_TEXT NVARCHAR(100) = 'Authenticator App', @Ai_RecoveryCodeCount_NUMB INT = 10, @Ai_UpdatedBy_ID INT = 101, @An_OldTransactionSeqEvent_NUMB BIGINT = 613; -- From current Users table -- Execute the procedure EXEC dbo.Users$Sp_Update_TwoFactorDevice @Ai_User_ID, @Ab_TwoFactorEnabled_INDC, @Ac_MethodCode_CODE, @As_DeviceName_TEXT, @Ai_RecoveryCodeCount_NUMB, @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB , @Ai_Device_ID OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ai_Device_ID AS DeviceID, @An_NewTransactionSeqEvent_NUMB AS NewTxnSeq, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
TwoFactorDevice$Sp_Get_RecoveryCodes | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Replace with a valid Device_ID DECLARE @Ai_Device_ID INT = 4, @Ai_From_NUMB INT = 1, @Ai_To_NUMB INT = 10; -- Execute the procedure EXEC dbo.TwoFactorDevice$Sp_Get_RecoveryCodes @Ai_Device_ID, @Ai_From_NUMB, @Ai_To_NUMB, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- View result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Users$Sp_Update_ProfilePicture | DECLARE @Ai_User_ID INT = 2, -- User to update @As_ProfileURL_TEXT NVARCHAR(400) = 'https://cdn.site.com/user101.jpg', @Ai_UpdatedBy_ID INT = 2, -- Usually same as User_ID @An_OldTransactionSeqEvent_NUMB BIGINT = 2, -- Current seq from dbo.Users @An_NewTransactionSeqEvent_NUMB BIGINT = NULL, -- Will be generated @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure EXEC dbo.Users$Sp_Update_ProfilePicture @Ai_User_ID, @As_ProfileURL_TEXT, @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeq, @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
UserSettings$Sp_AddOrUpdate_UserSettings | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @An_NewTransactionSeqEvent_NUMB BIGINT = NULL; -- Example JSON array for notification settings DECLARE @Json NVARCHAR(MAX) = N' [ { "NotificationType_CODE": "AC", "IsEnabled_INDC": 1, "TransactionSeqEvent_NUMB": 637 } ]'; EXEC dbo.UserSettings$Sp_AddOrUpdate_UserSettings @Ai_User_ID = 4, @Ac_Language_CODE = 'ENG', @As_TimeZone_CODE = 'UTC', @As_NotificationSettings_JSON = @Json, @Ai_UpdatedBy_ID = 123, @An_OldTransactionSeqEvent_NUMB = 636, @An_NewTransactionSeqEvent_NUMB = @An_NewTransactionSeqEvent_NUMB , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @An_NewTransactionSeqEvent_NUMB AS NewTxnSeq;
UserSettings$Sp_Get_UserSettings | DECLARE @Ai_User_ID INT = 4, -- Replace with actual user ID @Ac_Language_CODE CHAR(5), @As_LanguageName_TEXT NVARCHAR(50), @Ac_TimeZone_CODE NVARCHAR(50), @As_TimeZoneName_TEXT NVARCHAR(100), @An_TransactionSeqEvent_NUMB BIGINT, @As_NotificationSettings_JSON_TEXT NVARCHAR(MAX), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.UserSettings$Sp_Get_UserSettings @Ai_User_ID, @Ac_Language_CODE OUTPUT, @As_LanguageName_TEXT OUTPUT, @Ac_TimeZone_CODE OUTPUT, @As_TimeZoneName_TEXT OUTPUT, @An_TransactionSeqEvent_NUMB OUTPUT, @As_NotificationSettings_JSON_TEXT OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- View output SELECT @Ac_Language_CODE AS Language_CODE, @As_LanguageName_TEXT AS Language_Name, @Ac_TimeZone_CODE AS TimeZone_CODE, @As_TimeZoneName_TEXT AS TimeZone_Name, @An_TransactionSeqEvent_NUMB AS TxnSeq, @As_NotificationSettings_JSON_TEXT AS NotificationSettings_JSON, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Office$Sp_Add_Office | DECLARE @As_OrganizationName_TEXT NVARCHAR(100) = N'Example Org', @As_OfficeName_TEXT NVARCHAR(100) = N'Main Office', @As_OfficeAddress_TEXT NVARCHAR(250) = N'123 Main Street, Sample City', @Ac_County_CODE CHAR(10) = '001', -- must exist in RefCounty @Ac_OfficeType_CODE CHAR(10) = 'CC', -- must exist in RefOfficeType @As_SubOrganization_TEXT NVARCHAR(100) = N'Division A', @Ab_OverrideDuplicate_INDC BIT = 0, -- set to 1 to skip duplicate check @Ai_CreatedBy_ID INT = 1001, @An_TransactionSeqEvent_NUMB BIGINT = NULL, @Ai_Office_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Office$Sp_Add_Office @As_OrganizationName_TEXT, @As_OfficeName_TEXT, @As_OfficeAddress_TEXT, @Ac_County_CODE, @Ac_OfficeType_CODE, @As_SubOrganization_TEXT, @Ab_OverrideDuplicate_INDC, @Ai_CreatedBy_ID, @An_TransactionSeqEvent_NUMB, @Ai_Office_ID OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- View result SELECT @Ai_Office_ID AS Office_ID, @Ac_Msg_CODE AS Msg_Code, @As_DescriptionError_TEXT AS Message;
Office$Sp_Update_Office | DECLARE @Ai_Office_ID INT = 1, -- existing office ID @As_OrganizationName_TEXT NVARCHAR(100) = N'Example Organization', @As_OfficeName_TEXT NVARCHAR(100) = N'Updated Office Name', @As_OfficeAddress_TEXT NVARCHAR(250) = N'456 Updated Blvd, CityTown', @Ac_County_CODE CHAR(10) = '001', -- must exist in RefCounty @Ac_OfficeType_CODE CHAR(10) = 'CC', -- must exist in RefOfficeType @As_SubOrganization_TEXT NVARCHAR(100) = N'SubOrg Beta', @Ab_OverrideDuplicate_INDC BIT = 0, @Ai_UpdatedBy_ID INT = 1001, @An_OldTransactionSeqEvent_NUMB BIGINT = 640, -- must match current value in table @An_NewTransactionSeqEvent_NUMB BIGINT = NULL, @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Office$Sp_Update_Office @Ai_Office_ID, @As_OrganizationName_TEXT, @As_OfficeName_TEXT, @As_OfficeAddress_TEXT, @Ac_County_CODE, @Ac_OfficeType_CODE, @As_SubOrganization_TEXT, @Ab_OverrideDuplicate_INDC, @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- View output SELECT @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeqEvent, @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Office$Sp_Delete_Office | DECLARE @Ai_Office_ID INT = 1, -- Office to delete @Ai_ReplacementOffice_ID INT = NULL, -- Optional: if users exist under the old office @As_Reason_TEXT NVARCHAR(250) = N'Merging with central office due to restructuring', @Ab_Confirmation_INDC BIT = 1, -- Must confirm deletion @Ai_DeletedBy_ID INT = 1001, -- Admin performing delete @An_OldTransactionSeqEvent_NUMB BIGINT = 642, -- Current value on office record @An_NewTransactionSeqEvent_NUMB BIGINT = NULL, @Ai_ReassignedUserCount_NUMB INT, @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Office$Sp_Delete_Office @Ai_Office_ID, @Ai_ReplacementOffice_ID, @As_Reason_TEXT, @Ab_Confirmation_INDC, @Ai_DeletedBy_ID, @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB , @Ai_ReassignedUserCount_NUMB OUTPUT, @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Output the results SELECT @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeqEvent, @Ai_ReassignedUserCount_NUMB AS UsersReassigned, @Ai_RowsAffected_NUMB AS OfficeRowsDeleted, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Office$Sp_Get_Office | DECLARE @Ai_Office_ID INT = 1, -- Replace with your Office ID to retrieve @As_OrganizationName_TEXT NVARCHAR(100), @As_OfficeName_TEXT NVARCHAR(100), @As_OfficeAddress_TEXT NVARCHAR(250), @Ac_County_CODE CHAR(10), @As_CountyName_TEXT NVARCHAR(100), @Ac_OfficeType_CODE CHAR(10), @As_OfficeTypeDesc_TEXT NVARCHAR(100), @As_SubOrganization_TEXT NVARCHAR(100), @Ab_IsActive_INDC BIT, @Ai_CreatedBy_ID INT, @Ad_Created_DTTM DATETIME2, @Ai_UpdatedBy_ID INT, @Ad_Updated_DTTM DATETIME2, @An_TransactionSeqEvent_NUMB BIGINT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Office$Sp_Get_Office @Ai_Office_ID = @Ai_Office_ID, @As_OrganizationName_TEXT = @As_OrganizationName_TEXT OUTPUT, @As_OfficeName_TEXT = @As_OfficeName_TEXT OUTPUT, @As_OfficeAddress_TEXT = @As_OfficeAddress_TEXT OUTPUT, @Ac_County_CODE = @Ac_County_CODE OUTPUT, @As_CountyName_TEXT = @As_CountyName_TEXT OUTPUT, @Ac_OfficeType_CODE = @Ac_OfficeType_CODE OUTPUT, @As_OfficeTypeDesc_TEXT = @As_OfficeTypeDesc_TEXT OUTPUT, @As_SubOrganization_TEXT = @As_SubOrganization_TEXT OUTPUT, @Ab_IsActive_INDC = @Ab_IsActive_INDC OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @Ad_Created_DTTM = @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @Ad_Updated_DTTM = @Ad_Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the output results SELECT @As_OrganizationName_TEXT AS OrganizationName, @As_OfficeName_TEXT AS OfficeName, @As_OfficeAddress_TEXT AS OfficeAddress, @Ac_County_CODE AS CountyCode, @As_CountyName_TEXT AS CountyName, @Ac_OfficeType_CODE AS OfficeTypeCode, @As_OfficeTypeDesc_TEXT AS OfficeTypeDescription, @As_SubOrganization_TEXT AS SubOrganization, @Ab_IsActive_INDC AS IsActive, @Ai_CreatedBy_ID AS CreatedBy, @Ad_Created_DTTM AS CreatedDate, @Ai_UpdatedBy_ID AS UpdatedBy, @Ad_Updated_DTTM AS UpdatedDate, @An_TransactionSeqEvent_NUMB AS TransactionSeqEvent, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Users$Sp_Get_UserList | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_Get_UserList @As_Search_TEXT = NULL, -- Search for name or email containing 'john' @As_EmailAddress_TEXT = NULL, -- No specific email filter @Ai_Role_ID = NULL, -- Not using Role_ID filter @Ac_Role_CODE = NULL, -- Filter by Role_CODE (e.g., 'AD' for Admin) @Ac_Status_CODE = NULL, -- Filter by Active users only @Ai_Office_ID = NULL, -- No specific office filter @As_SortColumn_TEXT = NULL, -- Sort by full name @Ab_SortDirection_TEXT = 'ASC', -- Ascending order @Ai_From_NUMB = 1, -- Starting row @Ai_To_NUMB = 10, -- Ending row @Ai_SignOnUser_ID = 1001, -- Logged-in user ID (optional scope) @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display output message SELECT MsgCode = @Ac_Msg_CODE, Message = @As_DescriptionError_TEXT;
Office$Sp_Get_OfficeList | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Office$Sp_Get_OfficeList @Ai_SignonUser_ID = NULL, -- or a valid user ID like 101 @As_OrganizationName_TEXT = NULL, -- or partial name like 'Health' @As_OfficeName_TEXT = NULL, -- or partial name like 'Main' @Ac_County_CODE = NULL, -- or a valid county code like 'CN001' @Ac_OfficeType_CODE = NULL, -- or a valid type like 'OT01' @As_SubOrganization_TEXT = NULL, -- or partial sub-org name @Ab_IsActive_INDC = 1, -- 1 = active only, NULL = all @Ai_From_NUMB = 1, -- pagination start @Ai_To_NUMB = 10, -- pagination end @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result message SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
User$Sp_Create_User | DECLARE @Ai_User_ID INT, @As_Token_TEXT VARCHAR(50), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.User$Sp_Create_User -- Personal info @As_FirstName_TEXT = 'JohnNY', @As_MiddleName_TEXT = NULL, @As_LastName_TEXT = 'Doe', @Ad_BirthDate_DATE = '1990-05-15', @As_EmailAddress_TEXT = 'johnny.doe@example.com', @As_PhoneNumber_TEXT = '555-123-4567', @As_Gender_CODE = 'M', -- Office & role @Ai_Office_ID = 2, -- Example Office_ID @Ac_Role_CODE = 'AD', -- Example Role_CODE (e.g., 'AD' for Admin) -- Account settings @As_EmploymentStatus_CODE = 'A', -- Example: 'A' for Active @As_AccountStatus_CODE = 'P', -- Default: Pending @Ab_SendInvite_INDC = 1, -- Send invitation @Ab_ForceReset_INDC = 1, -- Force reset at first login -- Auditing @Ai_CreatedBy_ID = 1, -- Admin or current user's ID @An_TransactionSeqEvent_NUMB = NULL, -- Example transaction ID @Ai_Override_INDC = 0, -- Do not override duplicate check -- Outputs @Ai_User_ID = @Ai_User_ID OUTPUT, @As_Token_TEXT = @As_Token_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT User_ID = @Ai_User_ID, InviteToken = @As_Token_TEXT, MsgCode = @Ac_Msg_CODE, Message = @As_DescriptionError_TEXT;
User$Sp_Update_UserProfile | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @An_NewTransactionSeqEvent_NUMB BIGINT; EXEC dbo.User$Sp_Update_UserProfile @Ai_User_ID = 2134, -- Existing User_ID @As_FirstName_TEXT = 'Jane', @As_MiddleName_TEXT = 'A.', @As_LastName_TEXT = 'Smith', @Ad_BirthDate_DATE = '1990-07-01', @As_PhoneNumber_TEXT = '555-987-6543', @Ai_Office_ID = 2, -- Must exist and be active in Office table @Ac_Role_CODE = 'CM', -- Valid Role_CODE (e.g. Case Manager) @Ac_EmploymentStatus_CODE = 'A', -- 'A' for Active, etc. @Ac_AccountStatus_CODE = 'A', -- 'A' for Active, 'I' for Inactive, etc. @Ab_ForceReset_INDC = 0, -- Don’t force reset @Ai_UpdatedBy_ID = 1, -- Admin user performing the update @An_OldTransactionSeqEvent_NUMB = 655, -- The current TransactionSeqEvent_NUMB of the user @An_NewTransactionSeqEvent_NUMB = @An_NewTransactionSeqEvent_NUMB , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT MsgCode = @Ac_Msg_CODE, Message = @As_DescriptionError_TEXT, NewTransactionSeqEvent = @An_NewTransactionSeqEvent_NUMB;
UserBulkOperations$Sp_UpdateAccountStatus | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_RowsAffected_NUMB INT, @Ai_TransactionSeqEvent_NUMB BIGINT = NULL; -- Let the procedure generate it EXEC dbo.UserBulkOperations$Sp_UpdateAccountStatus @As_UserIDs_JSON = N'[2134, 2129]', -- JSON array of User_IDs to update @Ac_AccountStatus_CODE = 'A', -- 'A' = Activate users @As_Reason_TEXT = 'Mass activation after onboarding training', @Ai_UpdatedBy_ID = 1, -- Admin User_ID @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT MsgCode = @Ac_Msg_CODE, Message = @As_DescriptionError_TEXT, RowsAffected = @Ai_RowsAffected_NUMB, TransactionSeqEvent = @Ai_TransactionSeqEvent_NUMB;
UserBulkOperations$Sp_UpdateRole | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_RowsAffected_NUMB INT, @Ai_TransactionSeqEvent_NUMB BIGINT = NULL; -- Will be generated inside the proc EXEC dbo.UserBulkOperations$Sp_UpdateRole @As_UserIDs_JSON = N'[1, 2134]', -- List of User_IDs to update (must exist) @Ac_Role_CODE = 'AD', -- New role code (must exist in RefRole) @As_Reason_TEXT = 'Mass update to Case Manager role', @Ai_UpdatedBy_ID = 1, -- Admin performing the operation @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT MsgCode = @Ac_Msg_CODE, Message = @As_DescriptionError_TEXT, RowsAffected = @Ai_RowsAffected_NUMB, TransactionSeqEvent = @Ai_TransactionSeqEvent_NUMB;
EmailNotification$Sp_AddWithRecipients_S1 | DECLARE @Ai_EmailNotification_ID INT, @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT = NULL; -- Sample JSON with recipients DECLARE @As_Recipients_JSON NVARCHAR(MAX) = N' [ { "User_ID": 1, "RecipientType_CODE": "S" }, { "User_ID": 2, "RecipientType_CODE": "S" }, { "User_ID": 4, "RecipientType_CODE": "F" } ]'; EXEC dbo.EmailNotification$Sp_AddWithRecipients_S1 @As_Subject_TEXT = N'Case Review Meeting', @As_Body_HTML = N'<p>Dear all,<br/>Please attend the scheduled case review tomorrow at 10 AM.</p>', @As_Body_TEXT = N'Dear all,\nPlease attend the scheduled case review tomorrow at 10 AM.', @Ai_Template_ID = NULL, @As_Recipients_JSON = @As_Recipients_JSON, @Ai_CreatedBy_ID = 1, -- valid User_ID @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB , @Ai_EmailNotification_ID = @Ai_EmailNotification_ID OUTPUT, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT EmailNotification_ID = @Ai_EmailNotification_ID, RowsAffected = @Ai_RowsAffected_NUMB, MsgCode = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT, TransactionEvent = @An_TransactionSeqEvent_NUMB;
EmailNotification$Sp_Get_Recipients_S1 | DECLARE @Ai_EmailNotification_ID INT = 2, -- Replace 123 with the actual notification ID @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.EmailNotification$Sp_Get_Recipients_S1 @Ai_EmailNotification_ID = @Ai_EmailNotification_ID, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- To check output parameters SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Users$Sp_Get_UserDetails | DECLARE @Ai_User_ID INT = 1, -- Replace with actual User_ID @As_FirstName_TEXT VARCHAR(50), @As_MiddleName_TEXT VARCHAR(50), @As_LastName_TEXT VARCHAR(50), @Ad_BirthDate_DATE DATE, @As_EmailAddress_TEXT NVARCHAR(255), @As_PhoneNumber_TEXT NVARCHAR(20), @Ai_Role_ID INT, @Ac_Role_CODE CHAR(10), @As_RoleDesc_TEXT NVARCHAR(100), @Ai_Office_ID INT, @As_OfficeName_TEXT NVARCHAR(100), @Ac_County_CODE CHAR(10), @As_CountyName_TEXT NVARCHAR(100), @Ac_OfficeType_CODE CHAR(10), @As_OfficeTypeDesc_TEXT NVARCHAR(100), @Ac_EmploymentStatus_CODE CHAR(1), @As_EmploymentStatusDesc_TEXT NVARCHAR(100), @Ac_AccountStatus_CODE CHAR(1), @As_AccountStatusDesc_TEXT NVARCHAR(50), @Ab_ForceReset_INDC BIT, @Ab_TwoFactorEnabled_INDC BIT, @Ab_IsLocked_INDC BIT, @Ad_LastPasswordChange_DTTM DATETIME2, @Ai_LoginCount_NUMB INT, @Ad_LastLogin_DTTM DATETIME2, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_Get_UserDetails @Ai_User_ID = @Ai_User_ID, @As_FirstName_TEXT = @As_FirstName_TEXT OUTPUT, @As_MiddleName_TEXT = @As_MiddleName_TEXT OUTPUT, @As_LastName_TEXT = @As_LastName_TEXT OUTPUT, @Ad_BirthDate_DATE = @Ad_BirthDate_DATE OUTPUT, @As_EmailAddress_TEXT = @As_EmailAddress_TEXT OUTPUT, @As_PhoneNumber_TEXT = @As_PhoneNumber_TEXT OUTPUT, @Ai_Role_ID = @Ai_Role_ID OUTPUT, @Ac_Role_CODE = @Ac_Role_CODE OUTPUT, @As_RoleDesc_TEXT = @As_RoleDesc_TEXT OUTPUT, @Ai_Office_ID = @Ai_Office_ID OUTPUT, @As_OfficeName_TEXT = @As_OfficeName_TEXT OUTPUT, @Ac_County_CODE = @Ac_County_CODE OUTPUT, @As_CountyName_TEXT = @As_CountyName_TEXT OUTPUT, @Ac_OfficeType_CODE = @Ac_OfficeType_CODE OUTPUT, @As_OfficeTypeDesc_TEXT = @As_OfficeTypeDesc_TEXT OUTPUT, @Ac_EmploymentStatus_CODE = @Ac_EmploymentStatus_CODE OUTPUT, @As_EmploymentStatusDesc_TEXT = @As_EmploymentStatusDesc_TEXT OUTPUT, @Ac_AccountStatus_CODE = @Ac_AccountStatus_CODE OUTPUT, @As_AccountStatusDesc_TEXT = @As_AccountStatusDesc_TEXT OUTPUT, @Ab_ForceReset_INDC = @Ab_ForceReset_INDC OUTPUT, @Ab_TwoFactorEnabled_INDC = @Ab_TwoFactorEnabled_INDC OUTPUT, @Ab_IsLocked_INDC = @Ab_IsLocked_INDC OUTPUT, @Ad_LastPasswordChange_DTTM = @Ad_LastPasswordChange_DTTM OUTPUT, @Ai_LoginCount_NUMB = @Ai_LoginCount_NUMB OUTPUT, @Ad_LastLogin_DTTM = @Ad_LastLogin_DTTM OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- To check results: SELECT @As_FirstName_TEXT AS FirstName, @As_MiddleName_TEXT AS MiddleName, @As_LastName_TEXT AS LastName, @Ad_BirthDate_DATE AS BirthDate, @As_EmailAddress_TEXT AS Email, @As_PhoneNumber_TEXT AS Phone, @Ai_Role_ID AS RoleID, @Ac_Role_CODE AS RoleCode, @As_RoleDesc_TEXT AS RoleDesc, @Ai_Office_ID AS OfficeID, @As_OfficeName_TEXT AS OfficeName, @Ac_County_CODE AS CountyCode, @As_CountyName_TEXT AS CountyName, @Ac_OfficeType_CODE AS OfficeTypeCode, @As_OfficeTypeDesc_TEXT AS OfficeTypeDesc, @Ac_EmploymentStatus_CODE AS EmploymentStatusCode, @As_EmploymentStatusDesc_TEXT AS EmploymentStatusDesc, @Ac_AccountStatus_CODE AS AccountStatusCode, @As_AccountStatusDesc_TEXT AS AccountStatusDesc, @Ab_ForceReset_INDC AS ForceReset, @Ab_TwoFactorEnabled_INDC AS TwoFactorEnabled, @Ab_IsLocked_INDC AS IsLocked, @Ad_LastPasswordChange_DTTM AS LastPasswordChange, @Ai_LoginCount_NUMB AS LoginCount, @Ad_LastLogin_DTTM AS LastLogin, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS MessageDescription;
Users$Sp_Get_AuditLogTimeline_S1 | DECLARE @Ai_User_ID INT = 1, -- Replace with actual User_ID @Ai_From_NUMB INT = 1, -- Starting row number @Ai_To_NUMB INT = 10, -- Ending row number @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_Get_AuditLogTimeline_S1 @Ai_User_ID = @Ai_User_ID, @Ai_From_NUMB = @Ai_From_NUMB, @Ai_To_NUMB = @Ai_To_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output messages SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Users$Sp_Delete_User | DECLARE @Ai_User_ID INT = 2134, -- User ID to delete @As_Reason_TEXT NVARCHAR(1000) = 'User requested account removal', -- Optional reason @Ab_Confirmation_INDC BIT = 1, -- Confirmation flag (must be 1) @Ai_DeletedBy_ID INT = 1, -- Admin user performing deletion @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_Delete_User @Ai_User_ID = @Ai_User_ID, @As_Reason_TEXT = @As_Reason_TEXT, @Ab_Confirmation_INDC = @Ab_Confirmation_INDC, @Ai_DeletedBy_ID = @Ai_DeletedBy_ID, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ai_RowsAffected_NUMB AS RowsDeleted, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
Office$Sp_Get_UserCount | DECLARE @UserCount INT, @MsgCode CHAR(1), @DescError VARCHAR(4000); EXEC dbo.Office$Sp_Get_UserCount @Ai_Office_ID = 2, -- Replace 123 with the actual Office_ID @Ai_UserCount_NUMB = @UserCount OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @DescError OUTPUT; -- Optionally, check output values: SELECT @UserCount AS UserCount, @MsgCode AS MsgCode, @DescError AS Description;
Role$Sp_Get_UsersByRole | DECLARE @MsgCode CHAR(1), @DescError VARCHAR(4000); EXEC dbo.Role$Sp_Get_UsersByRole @Ac_Role_CODE = 'ad', -- Replace with desired role code @As_NameFilter_TEXT = NULL, -- Optional name filter (or 'John') @As_EmailFilter_TEXT = NULL, -- Optional email filter @Ai_Office_ID_Filter = NULL, -- Optional office ID filter @Ai_From_NUMB = 1, -- Starting row number @Ai_To_NUMB = 50, -- Ending row number @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @DescError OUTPUT; -- Check output messages SELECT @MsgCode AS MsgCode, @DescError AS Description;
Role$Sp_Get_RoleList | DECLARE @MsgCode CHAR(1), @DescError VARCHAR(4000); EXEC dbo.Role$Sp_Get_RoleList @Ac_Role_CODE = NULL, -- Optional filter by role code, e.g. 'Admin'. Use NULL for all roles. @Ai_From_NUMB = 1, -- Starting row number @Ai_To_NUMB = 20, -- Ending row number @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @DescError OUTPUT; -- Check output messages SELECT @MsgCode AS MsgCode, @DescError AS Description;
Role$Sp_Get_RoleDetails | DECLARE @RoleName NVARCHAR(100), @RoleDesc NVARCHAR(200), @UserCount INT, @PermissionsJSON NVARCHAR(MAX), @UpdatedDTTM DATETIME2, @TxnSeqEvent BIGINT, @MsgCode CHAR(1), @ErrorDesc VARCHAR(4000); EXEC dbo.Role$Sp_Get_RoleDetails @Ac_Role_CODE = 'AD', -- Replace with desired role code @As_RoleName_TEXT = @RoleName OUTPUT, @As_RoleDesc_TEXT = @RoleDesc OUTPUT, @Ai_UserCount_NUMB = @UserCount OUTPUT, @As_Permissions_JSON = @PermissionsJSON OUTPUT, @Ad_Updated_DTTM = @UpdatedDTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @TxnSeqEvent OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- View output SELECT @RoleName AS RoleName, @RoleDesc AS RoleDescription, @UserCount AS UserCount, @PermissionsJSON AS PermissionsJSON, @UpdatedDTTM AS UpdatedDTTM, @TxnSeqEvent AS TransactionSeqEvent, @MsgCode AS MsgCode, @ErrorDesc AS Description;
UserBulkOperations$Sp_UpdateUserOffice | DECLARE @RowsAffected INT, @MsgCode CHAR(1), @ErrorDesc VARCHAR(4000); -- Example input parameters DECLARE @UserIDs_JSON NVARCHAR(MAX) = N'[1, 2]', -- Example user IDs @Office_ID INT = 2, -- Target office ID @Reason NVARCHAR(250) = N'Consolidation of offices for efficiency.', @UpdatedBy_ID INT = 1, -- Admin user ID @TxnSeq BIGINT = 202506280001; -- Example transaction number -- Execute the procedure EXEC dbo.UserBulkOperations$Sp_UpdateUserOffice @As_UserIDs_JSON = @UserIDs_JSON, @Ai_Office_ID = @Office_ID, @As_Reason_TEXT = @Reason, @Ai_UpdatedBy_ID = @UpdatedBy_ID, @An_TransactionSeqEvent_NUMB = @TxnSeq, @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Output results SELECT @RowsAffected AS RowsAffected, @MsgCode AS MsgCode, @ErrorDesc AS Description;
dbo.User$Sp_Update_UserRole | DECLARE @RowsAffected INT, @MsgCode CHAR(1), @ErrorDesc VARCHAR(4000); -- Example input parameters DECLARE @UserID INT = 1, -- User to update @NewRoleCode CHAR(10) = 'AD', -- New role code @ReasonText NVARCHAR(500) = N'Promoted to Admin due to responsibilities.', @OldTxnSeq BIGINT = 202506280001, -- Current known transaction number @NewTxnSeq BIGINT = 202506280002, -- New transaction number to stamp @UpdatedBy INT = 1; -- Admin performing the change -- Execute the procedure EXEC dbo.User$Sp_Update_UserRole @Ai_User_ID = @UserID, @As_Role_CODE = @NewRoleCode, @As_Reason_TEXT = @ReasonText, @An_OldTransactionSeqEvent_NUMB = @OldTxnSeq, @An_NewTransactionSeqEvent_NUMB = @NewTxnSeq, @Ai_UpdatedBy_ID = @UpdatedBy, @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Output the result SELECT @RowsAffected AS RowsAffected, @MsgCode AS MsgCode, @ErrorDesc AS Description;
dbo.Users$Sp_Update_LockStatus | DECLARE @RowsAffected INT, @MsgCode CHAR(1), @ErrorText VARCHAR(4000); -- Input values DECLARE @UserID INT = 1, -- User to lock or unlock @LockFlag BIT = 0, -- 1 = Lock, 0 = Unlock @Reason NVARCHAR(500) = N'Locked due to suspicious activity.', @UpdatedBy INT = 2, -- Admin performing action @OldTxnSeq BIGINT = 202506280005, -- Existing transaction number @NewTxnSeq BIGINT = 202506280005; -- New transaction number -- Execute procedure EXEC dbo.Users$Sp_Update_LockStatus @Ai_User_ID = @UserID, @Ab_Lock_INDC = @LockFlag, @As_Reason_TEXT = @Reason, @Ai_UpdatedBy_ID = @UpdatedBy, @An_OldTransactionSeqEvent_NUMB = @OldTxnSeq, @An_NewTransactionSeqEvent_NUMB = @NewTxnSeq, @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorText OUTPUT; -- Show result SELECT @RowsAffected AS RowsAffected, @MsgCode AS MsgCode, @ErrorText AS Message;
Users$Sp_Send_InvitationEmail | DECLARE @Token VARCHAR(50), @EmailLogID INT, @MsgCode CHAR(1), @ErrorMessage VARCHAR(4000); -- Sample input values DECLARE @UserID INT = 12, -- Target user @InvitedByID INT = 1, -- Admin user ID @DomainURL NVARCHAR(200) = 'https://wioa.arkansas.gov', @ExpirationHours INT = 24; -- Execute the stored procedure EXEC dbo.Users$Sp_Send_InvitationEmail @Ai_User_ID = @UserID, @Ai_InvitedBy_ID = @InvitedByID, @As_Domain_URL = @DomainURL, @Ai_ExpirationHours = @ExpirationHours, @As_Token_TEXT = @Token OUTPUT, @Ai_EmailLog_ID = @EmailLogID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorMessage OUTPUT; -- Output results SELECT @MsgCode AS MsgCode, @ErrorMessage AS Message, @Token AS Token, @EmailLogID AS EmailLogID;
Users$Sp_Get_UserInfo | DECLARE @Ai_User_ID INT, @As_Username_TEXT NVARCHAR(100), @As_FirstName_TEXT NVARCHAR(100), @As_LastName_TEXT NVARCHAR(100), @Ad_BirthDate_DATE DATE, @As_SSN_TEXT CHAR(9), @As_PhoneNumber_TEXT NVARCHAR(20), @Ac_Gender_CODE CHAR(1), @As_GenderDesc_TEXT NVARCHAR(50), @Ac_UserType_CODE CHAR(1), @As_UserTypeDesc_TEXT NVARCHAR(50), @Ai_CreatedBy_ID INT, @Ld_Created_DTTM DATETIME2, @Ai_UpdatedBy_ID INT, @Ld_Updated_DTTM DATETIME2, @An_TransactionSeqEvent_NUMB BIGINT, @Ab_TwoFactorEnabled_INDC BIT, @Ab_IsLocked_INDC BIT, @Ad_LastPasswordChange_DTTM DATETIME2, @Ai_LoginCount_NUMB INT, @Ad_LastLogin_DTTM DATETIME2, @Ai_Role_ID INT, @Ac_Role_CODE CHAR(10), @As_RoleDesc_TEXT NVARCHAR(100), @Ai_Office_ID INT, @As_OfficeName_TEXT NVARCHAR(100), @Ac_OfficeCounty_CODE CHAR(10), @As_OfficeCountyName_TEXT NVARCHAR(100), @Ac_OfficeType_CODE CHAR(10), @As_OfficeTypeDesc_TEXT NVARCHAR(100), @Ac_EmploymentStatus_CODE CHAR(1), @As_EmploymentStatusDesc_TEXT NVARCHAR(100), @Ac_AccountStatus_CODE CHAR(1), @As_AccountStatusDesc_TEXT NVARCHAR(50), @Ab_ForceReset_INDC BIT, @As_AddressLine1_TEXT NVARCHAR(200), @As_AddressLine2_TEXT NVARCHAR(200), @As_City_TEXT NVARCHAR(100), @Ac_State_CODE CHAR(2), @As_PostalCode_TEXT NVARCHAR(20), @Ac_Country_CODE CHAR(2), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Call the procedure by User_ID EXEC dbo.Users$Sp_Get_UserInfo @Ai_InputUser_ID = 1, -- Provide a valid User_ID @As_InputEmailAddress_TEXT = NULL, -- Or NULL if using User_ID @Ai_User_ID = @Ai_User_ID OUTPUT, @As_Username_TEXT = @As_Username_TEXT OUTPUT, @As_FirstName_TEXT = @As_FirstName_TEXT OUTPUT, @As_LastName_TEXT = @As_LastName_TEXT OUTPUT, @Ad_BirthDate_DATE = @Ad_BirthDate_DATE OUTPUT, @As_SSN_TEXT = @As_SSN_TEXT OUTPUT, @As_PhoneNumber_TEXT = @As_PhoneNumber_TEXT OUTPUT, @Ac_Gender_CODE = @Ac_Gender_CODE OUTPUT, @As_GenderDesc_TEXT = @As_GenderDesc_TEXT OUTPUT, @Ac_UserType_CODE = @Ac_UserType_CODE OUTPUT, @As_UserTypeDesc_TEXT = @As_UserTypeDesc_TEXT OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @Ld_Created_DTTM = @Ld_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @Ld_Updated_DTTM = @Ld_Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ab_TwoFactorEnabled_INDC = @Ab_TwoFactorEnabled_INDC OUTPUT, @Ab_IsLocked_INDC = @Ab_IsLocked_INDC OUTPUT, @Ad_LastPasswordChange_DTTM = @Ad_LastPasswordChange_DTTM OUTPUT, @Ai_LoginCount_NUMB = @Ai_LoginCount_NUMB OUTPUT, @Ad_LastLogin_DTTM = @Ad_LastLogin_DTTM OUTPUT, @Ai_Role_ID = @Ai_Role_ID OUTPUT, @Ac_Role_CODE = @Ac_Role_CODE OUTPUT, @As_RoleDesc_TEXT = @As_RoleDesc_TEXT OUTPUT, @Ai_Office_ID = @Ai_Office_ID OUTPUT, @As_OfficeName_TEXT = @As_OfficeName_TEXT OUTPUT, @Ac_OfficeCounty_CODE = @Ac_OfficeCounty_CODE OUTPUT, @As_OfficeCountyName_TEXT = @As_OfficeCountyName_TEXT OUTPUT, @Ac_OfficeType_CODE = @Ac_OfficeType_CODE OUTPUT, @As_OfficeTypeDesc_TEXT = @As_OfficeTypeDesc_TEXT OUTPUT, @Ac_EmploymentStatus_CODE = @Ac_EmploymentStatus_CODE OUTPUT, @As_EmploymentStatusDesc_TEXT = @As_EmploymentStatusDesc_TEXT OUTPUT, @Ac_AccountStatus_CODE = @Ac_AccountStatus_CODE OUTPUT, @As_AccountStatusDesc_TEXT = @As_AccountStatusDesc_TEXT OUTPUT, @Ab_ForceReset_INDC = @Ab_ForceReset_INDC OUTPUT, @As_AddressLine1_TEXT = @As_AddressLine1_TEXT OUTPUT, @As_AddressLine2_TEXT = @As_AddressLine2_TEXT OUTPUT, @As_City_TEXT = @As_City_TEXT OUTPUT, @Ac_State_CODE = @Ac_State_CODE OUTPUT, @As_PostalCode_TEXT = @As_PostalCode_TEXT OUTPUT, @Ac_Country_CODE = @Ac_Country_CODE OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message, @As_Username_TEXT AS Username, @As_FirstName_TEXT AS FirstName, @As_LastName_TEXT AS LastName, @As_OfficeName_TEXT AS Office;
usp_Case_ProgramService_Get_S1 | DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Case_ProgramService_Get_S1 @Ai_Case_ID = 93, -- replace with actual Case_ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: Check the result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
Contract$Sp_Get_RecentTransactions | DECLARE @An_Last7DaysAmount_NUMB DECIMAL(18,2), @An_Last30DaysAmount_NUMB DECIMAL(18,2), @An_SinceStartAmount_NUMB DECIMAL(18,2), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Contract$Sp_Get_RecentTransactions @Ai_User_ID = 2, -- Replace with actual user ID @Ai_Contract_ID = 1, -- Replace with actual contract ID @Ac_Action_CODE = 'U', -- Optional: 'U' for User, 'E' for Employee @An_Last7DaysAmount_NUMB = @An_Last7DaysAmount_NUMB OUTPUT, @An_Last30DaysAmount_NUMB = @An_Last30DaysAmount_NUMB OUTPUT, @An_SinceStartAmount_NUMB = @An_SinceStartAmount_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the output SELECT @An_Last7DaysAmount_NUMB AS Last7DaysAmount, @An_Last30DaysAmount_NUMB AS Last30DaysAmount, @An_SinceStartAmount_NUMB AS SinceStartAmount, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
Timesheet$Sp_Get_ActiveNow | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Timesheet$Sp_Get_ActiveNow @Ai_Organization_ID = 1, -- Organization filter (optional, can be NULL) @As_Search_TEXT = null, -- Employee name filter (optional, can be NULL) @Ac_ViewFilter = null, -- Filter view: 'Active', 'Today', or 'All' @Ad_AsOf_DTTM = '2025-06-30', -- Snapshot timestamp (optional, can be NULL) @Ai_From_NUMB = 1, -- Start row number (1-based) @Ai_To_NUMB = 50, -- End row number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, -- Output message code ('S', 'N', 'F') @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output error description SELECT @Ac_Msg_CODE AS MSG_CODE,@As_DescriptionError_TEXT AS DescriptionError_TEXT
usp_Case_ProgramService_Update_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Case_ProgramService_Update_S1 @Ai_Case_ID = 98, -- Case ID @Js_CaseProgramService_JSON = N'[ { "Program_ID": 1, "ProgramStatus_CODE": "A", "ProgramStart_DATE": "2025-06-01", "ProgramEnd_DATE": "2025-12-31", "Service_ID": 1, "ServiceStatus_CODE": "A", "ServiceStart_DATE": "2025-06-01", "ServiceEnd_DATE": "2025-12-31" }, { "Program_ID": 2, "ProgramStatus_CODE": "A", "ProgramStart_DATE": "2025-01-01", "ProgramEnd_DATE": "2025-12-31", "Service_ID": 11, "ServiceStatus_CODE": "A", "ServiceStart_DATE": "2025-01-01", "ServiceEnd_DATE": "2025-12-31" } ]', -- JSON input for CaseProgramService details @Ai_CreatedBy_ID = 2099, -- Created by User ID @Ai_TransactionSeqEvent_NUMB = 1, -- Transaction Sequence Event Number @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, -- Output message code @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT;
IssPlan_AddFull_S1 | DECLARE @Ai_IssPlan_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.IssPlan_AddFull_S1 @Ai_Case_ID = 93, @As_PlanTitle_TEXT = 'Employment Reintegration Plan', @As_PlanDesc_TEXT = 'Comprehensive strategy to support the client in obtaining and retaining employment.', @Ad_Start_DATE = '2025-07-01', @Ad_End_DATE = '2025-12-31', @Ad_Review_DATE = '2025-08-15', @Ac_Status_CODE = 'A', -- A = Active @As_AdditionalServiceNote_TEXT = 'Additional help required with transportation.', @As_ClientSignaturePath_TEXT = '/signatures/client_98.png', @As_WorkerSignaturePath_TEXT = '/signatures/worker_2066.png', @Ai_CreatedBy_ID = 2099, @At_TransactionSeqEvent_NUMB = 1, -- JSON: Goals @As_Goals_JSON = N'[ { "Description": "Complete resume update", "TargetDate": "2025-07-15" }, { "Description": "Apply to 5 job postings", "TargetDate": "2025-07-20" } ]', -- JSON: Action Items @As_ActionItems_JSON = N'[ { "Description": "Attend resume workshop", "DueDate": "2025-07-05", "ResponsibleParty_ID": 2066 }, { "Description": "Submit job applications", "DueDate": "2025-07-20", "ResponsibleParty_ID": 2066 } ]', -- JSON: Barriers @As_Barriers_JSON = N'[ { "Barrier_CODE": "BS", "Notes": "Needs reliable transportation." }, { "Barrier_CODE": "DI", "Notes": "Has ongoing medical appointments." } ]', -- JSON: Services @As_Services_JSON = N'[ { "Service_ID": 1, "AssignedTo_ID": 2066, "DueDate": "2025-07-10" }, { "Service_ID": 2, "AssignedTo_ID": 2066, "DueDate": "2025-07-15" } ]', -- JSON: Notes @As_Notes_JSON = N'[ { "NoteType_CODE": "GENRL", "Note_TEXT": "Client is very motivated and open to feedback." }, { "NoteType_CODE": "GENRL", "Note_TEXT": "Referred to local job club for support." } ]', @Ai_IssPlan_ID = @Ai_IssPlan_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @Ai_IssPlan_ID AS New_IssPlan_ID;
usp_Applicant_Insert_S1 | DECLARE @Ai_Applicant_ID INT, @Ai_User_ID INT, @Ai_Case_ID INT, @Ai_TransactionSeqEvent_NUMB BIGINT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_Applicant_Insert_S1 @As_FirstName_TEXT = 'Final', @As_MiddleName_TEXT = 'Apps', @As_LastName_TEXT = 'tests', @Ad_DateOfBirth_DATE = '1985-10-25', @As_SocialSecurityNumber_TEXT = '123-45-6789', @As_Gender_CODE = 'M', @Ab_WorkAuthorization_INDC = 1, @As_EmploymentStatus_CODE = 'E', @Ab_LaidOffOrTerminated_INDC = 0, @Ab_ReceivingUI_INDC = 0, @Ab_VeteranOrSpouse_INDC = 0, @Ab_CriminalJustice_INDC = 0, @Ab_SeasonalAgriculturalWork_INDC = 0, @Ab_AmericanIndian_INDC = 0, @Ab_RegisteredApprenticeship_INDC = 0, @Ab_ResidentialEducation_INDC = 0, @Ab_TradeTraining_INDC = 0, @As_LowIncome_CODE = 'N', @Ab_NeedHelpTraining_INDC = 0, @As_HighSchoolDiplomaOrGED_CODE = 'Y', @As_PhoneNumber_TEXT = '5551234567', @As_EmailAddress_TEXT = 'filetestYY@example.com', @As_PublicAssistance_JSON = N'[{"Benefit_CODE":"S"}, {"Benefit_CODE":"T"}]', @As_Barriers_JSON = N'[{"Barrier_CODE":"BS"}]', @As_Documents_JSON = N'[{"DocumentType_CODE":"SS","FileName_TEXT":"social_security_card.pdf","FilePath_TEXT":"/uploads/applicant_docs/","FileSize_NUMB":20,"FileType_TEXT":"pdf"}]', @As_Res_AddressLine1_TEXT = '123 Main St', @As_Res_AddressLine2_TEXT = NULL, @As_Res_AdditionalInfo_TEXT = NULL, @Ac_Res_State_CODE = 'AL', @As_Res_CityName_TEXT = 'New York', -- You must ensure this city exists in RefCity @As_Res_Zip_TEXT = '36003', @As_Res_CountyName_TEXT = NULL, -- Match this with RefCounty @Ac_Res_Country_CODE = 'US', @As_Mail_AddressLine1_TEXT = '123 Main St', @As_Mail_AddressLine2_TEXT = NULL, @As_Mail_AdditionalInfo_TEXT = NULL, @As_Mail_CityName_TEXT = 'New York', @Ac_Mail_State_CODE = 'AL', @As_Mail_Zip_TEXT = '90001', @As_Mail_CountyName_TEXT = NULL, @Ac_Mail_Country_CODE = 'US', @Ab_ConsentConfirmed_INDC = 1, @As_Signature_TEXT = 'John DoeTY', @As_SignatureDocURL_TEXT = 'http://example.com/signature.pdf', @Ai_CreatedBy_ID = 2099, @Ai_TransactionSeqEvent_NUMB = 0, @Ai_Applicant_ID = @Ai_Applicant_ID OUTPUT, @Ai_User_ID = @Ai_User_ID OUTPUT, @Ai_Case_ID = @Ai_Case_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Final Output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @Ai_Applicant_ID AS ApplicantID, @Ai_User_ID AS UserID, @Ai_Case_ID AS CaseID;
usp_UserAddress_Update_S1 | DECLARE @Ai_Address_ID INT, @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_UserAddress_Update_S1 @Ai_UserAddress_ID = 89, @Ai_User_ID = 2167, @As_AddressLine1_TEXT = '123 Main St', @As_AddressLine2_TEXT = 'Apt 4B', @As_AdditionalInfo_TEXT = 'Near Central Park', @Ai_City_ID = NULL, @As_CityName_TEXT = 'Springfield', @As_County_CODE = NULL, @As_CountyName_TEXT = 'Clark County', @Ac_State_CODE = 'OH', @As_Zip_TEXT = '45503', @Ac_Country_CODE = 'US', @Ac_AddressType_CODE = 'R', @Ai_UpdatedBy_ID = 12, @Ai_TransactionSeqEvent_NUMB = NULL, @Ai_Address_ID = @Ai_Address_ID OUTPUT, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: Check outputs SELECT @Ai_Address_ID AS Address_ID, @Ac_Msg_Code AS Msg_Code, @As_DescriptionError_TEXT AS Error_Description;
usp_MyCaseload_Fetch_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_MyCaseload_Fetch_S1 @As_Program_CODE = null, -- or NULL @As_userName_TEXT = null, -- or NULL @Ai_Case_ID = NULL, @Ac_CaseType_CODE = NULL, @Ac_Status_CODE = NULL, @Ai_CaseWorkerUser_ID = NULL, @Ac_Priority_CODE = null, -- e.g., High @Ac_MajorActivity_CODE = NULL, @Ai_SignedOnUser_ID = 2099, -- Required @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @As_DateRangeOption_TEXT = null, -- or 'Today', 'Yesterday', NULL @Ad_StartFrom_DATE = NULL, @Ad_EndTo_DATE = NULL, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the output status SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
usp_AssessmentSubmission_Update_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_AssessmentSubmission_Update_S1 @Ai_AssessmentSubmission_ID = 17, @Ai_Old_TransactionSeqEvent_NUMB = 0, @As_CareerGoals_TEXT = N'Become a software engineer', @As_CurrentJobSearch_TEXT = N'Looking for internships', @As_SpecificCareerGoal_TEXT = N'Backend developer', @As_HighestEducation_TEXT = N'Bachelors in CS', @As_LicensesCertificates_TEXT = N'Azure, AWS Certified', @As_SkillsToImprove_TEXT = N'Cloud, Kubernetes', @As_EmploymentStatus_TEXT = N'Unemployed', @As_PastJobs_TEXT = N'Intern at TechCorp', @As_RecentLayoffs_TEXT = N'No', @As_EmploymentBarriers_TEXT = N'None', @As_HelpNeeded_TEXT = N'Resume building, mock interviews', @As_TrainingInterest_TEXT = N'Interested in cloud training', @As_OtherServicesReceive_TEXT = N'Food assistance', @As_NeedsAssessmentNotes_TEXT = N'Client highly motivated', @Atvps_ProgServ = N' [ { "Program_CODE": "AD", "Service_CODE": "SS" }, { "Program_CODE": "AD", "Service_CODE": "VR" } ]', @Ai_TransactionSeqEvent_NUMB = 1, -- Let it auto-generate @Ai_UpdatedBy_ID = 2099, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Employment$Sp_Add_UserEmployment | DECLARE @UserEmployment_ID INT, @Msg_CODE CHAR(1), @DescriptionError_TEXT NVARCHAR(4000), @TransactionSeqEvent_NUMB INT; EXEC Employment$Sp_Add_UserEmployment @Ai_User_ID = 2171 ,@As_JobTitle_TEXT = N'Software Developer' ,@As_EmployerName_TEXT = N'TechCorp Inc.' ,@An_Salary_NUMB = 85000.00 ,@Ad_StartDate_DATE = '2024-10-01' ,@As_Notes_TEXT = N'First job after graduation' ,@Ai_CreatedBy_ID = 2099 ,@An_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB ,@Ai_UserEmployment_ID = @UserEmployment_ID OUTPUT ,@Ac_Msg_CODE = @Msg_CODE OUTPUT ,@As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- To review the output SELECT @UserEmployment_ID AS UserEmployment_ID, @Msg_CODE AS Msg_CODE, @DescriptionError_TEXT AS DescriptionError;
Job$SpAddJobContract | DECLARE @Ai_Contract_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Job$SpAddJobContract @Ai_Offer_ID = 1, -- 🔁 Replace with actual Offer_ID @As_ContractType_CODE = 'H', -- 'H' for Hourly, 'F' for Fixed @Ad_Start_DATE = '2025-07-01', @Ad_End_DATE = '2025-12-31', @Ai_Salary_NUMB = 25.50, -- Hourly rate or fixed salary @As_PayPeriod_CODE = 'W', -- 'H'=Hourly, 'W'=Weekly, etc. @Ai_ExpectedHoursPerWeek_NUMB = 40, @As_PaymentType_CODE = 'AC', -- 'AC'=Account, 'CH'=Cheque, etc. @As_AdditionalInfo_TEXT = N'Includes benefits and travel reimbursement', @As_ContractTitle_TEXT = N'Job Developer Contract', @As_ContractDesc_TEXT = N'6-month contract with weekly deliverables', @Ai_CreatedBy_ID = 2099, -- 🔁 Replace with valid User_ID @Ai_TransactionSeqEvent_NUMB = NULL, -- NULL to auto-generate one @Ai_Contract_ID = @Ai_Contract_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 🔍 Check results SELECT @Ai_Contract_ID AS Contract_ID, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
usp_DetailedPlan_User_Get_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_DetailedPlan_User_Get_S1 @Ai_SignedOnUser_ID = 2099, @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @As_Search_TEXT = NULL, -- You can also try: N'John' @Ai_Case_ID = NULL, -- Use a specific ID like 123 to filter @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- To see the output message SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS MsgText;
usp_CaseMinorActivity_Insert_S1 | DECLARE @Ac_Msg_Code CHAR(5); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_CaseMinorActivity_Insert_S1 @Ai_Case_ID = 93, @Ac_MajorActivity_CODE = 'PLAN', @Ac_MinorActivity_CODE = 'RSD', @Ac_Status_CODE = 'A', @As_Notes_TEXT = N'Resume development started', @Ai_AssignedTo_ID = 2099, @Ad_DueDate_DTTM = NULL, @Ad_Started_DTTM = '2025-07-20', @Ad_Completed_DTTM = NULL, @Ac_NextMinorActivity_CODE = NULL, @Ac_Reason_CODE = NULL, @Ai_Priority_NUMB = 1, @Ai_EscalationLevel_NUMB = 1, @Ad_LastNotification_DTTM = NULL, @Ai_CaseAction_ID = NULL, @Ac_Action_CODE = 'CM001', @Ad_Action_DTTM = '2025-07-20', @Ai_CreatedBy_ID = 2099, @Ai_TransactionSeqEvent_NUMB = 1, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_CaseMinorActivity_Update_S1 | DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_CaseMinorActivity_Update_S1 @Ai_CaseMinorActivity_ID = 22, -- Existing record to update @Ac_MinorActivity_CODE = 'RSD ', -- Optional: update activity code @As_Action_CODE = null, -- Optional: MODIFY action @Ad_Action_DTTM = null, -- When action happened @As_Notes_TEXT = N'Updated with new due date.',-- Notes update @Ac_Status_CODE = 'A', -- Status: In Progress @Ai_AssignedTo_ID = 2099, -- New assignee @Ad_DueDate_DTTM = null, -- New due date @Ad_Started_DTTM = null, -- When started @Ad_Completed_DTTM = NULL, -- Still in progress @Ac_NextMinorActivity_CODE = null, -- Next in sequence @Ac_Reason_CODE = NULL, -- Optional @Ai_Priority_NUMB = 1, @Ai_EscalationLevel_NUMB = 1, @Ad_LastNotification_DTTM = NULL, @Ai_CaseAction_ID = NULL, @Ai_UpdatedBy_ID = 2099, -- Your user ID @An_TransactionSeqEvent_NUMB = NULL, -- Let proc auto-generate it @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Employment$Sp_Get_UserEmployment | DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT VARCHAR(4000); EXEC Employment$Sp_Get_UserEmployment @Ai_User_ID = 2171, -- Not required if you're using ID directly @As_JobTitle_TEXT = NULL, @Ai_UserEmployment_ID = null, -- 🎯 Specific employment record @Ai_From_NUMB = 1, @Ai_To_NUMB = 1, @Ai_SignedOnUser_ID = 1, -- Your signed-in user @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Users$Sp_PasswordReset_Confirm
Users$Sp_MailToken_Validate | DECLARE @MsgCode CHAR(5), @MsgText VARCHAR(4000); EXEC dbo.Users$Sp_MailToken_Validate @As_RawToken_TEXT = 'b23a9f6b0b036d5e1b49924', @As_EmailAddress_TEXT = 'user@example.com', @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @MsgCode AS MsgCode, @MsgText AS Message;
Employment$Sp_Delete_UserEmployment | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT = NULL; EXEC Employment$Sp_Delete_UserEmployment @Ai_UserEmployment_ID = 2, -- ID of the employment record to delete @Ai_DeletedBy_ID = 2099, -- User ID performing the delete @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @An_TransactionSeqEvent_NUMB AS TransactionSeq;
WIOA_SP_GET_REPORTS_SERVICE_DETAILS | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(MAX); EXEC dbo.WIOA_SP_GET_REPORTS_SERVICE_DETAILS @Ad_StartDate = '2025-05-01', @Ad_EndDate = '2025-05-31', @Ac_ProgramCode = NULL, -- or 'AD' @Ac_ServiceCategoryCode = NULL, -- or '01' @Ai_RowFrom_NUMB = 1, @Ai_RowTo_NUMB = 10, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
WIOA_SP_GET_REPORTS_CASELOADSUMMARY_TABLE | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); -- Execute the procedure with sample filters EXEC dbo.WIOA_SP_GET_REPORTS_CASELOADSUMMARY_TABLE @Ac_Program_CODE = 'AD', -- Or e.g., 'AD' for Adult Program @Ac_Status_CODE = 'A', -- 'A' = Active, 'I' = Inactive @Ai_RowFrom_NUMB = 1, @Ai_RowTo_NUMB = 10, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the status and result message SELECT MsgCode = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
usp_TwoFactorRecoveryCode_Update_S1 | DECLARE @MsgCode CHAR(1); DECLARE @ErrorDesc VARCHAR(4000); DECLARE @NewTransactionSeq BIGINT = NULL; -- First get the current TransactionSeqEvent_NUMB for the recovery code DECLARE @CurrentTransactionSeq BIGINT; SELECT @CurrentTransactionSeq = TransactionSeqEvent_NUMB FROM dbo.TwoFactorRecoveryCode WHERE RecoveryCode_ID = 1; -- Replace with actual recovery code ID -- Execute the update (example: marking code as used) EXEC dbo.usp_TwoFactorRecoveryCode_Update_S1 @Ai_RecoveryCode_ID = 22, -- Recovery code ID to update @Ab_IsUsed_INDC = 1, -- 1 = mark as used, 0 = mark as unused @An_OldTransactionSeqEvent_NUMB = @CurrentTransactionSeq, -- Current version @An_NewTransactionSeqEvent_NUMB = @NewTransactionSeq, -- New version (auto-generated if NULL) @Ai_UpdatedBy_ID = 1, -- User ID performing the update @Ac_Msg_CODE = @MsgCode OUTPUT, -- Returns 'S', 'L', or 'F' @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Check results SELECT CASE @MsgCode WHEN 'S' THEN 'Success' WHEN 'L' THEN 'Concurrency Conflict' ELSE 'Failure' END AS Status, @ErrorDesc AS Message, @NewTransactionSeq AS NewTransactionSequence, @CurrentTransactionSeq AS OldTransactionSequence;
Users$Sp_Regenerate_RecoveryCodes | DECLARE @Ai_Device_ID INT = NULL, -- Optional: leave NULL to auto-pick latest device @An_TransactionSeqEvent_NUMB BIGINT = NULL, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_Regenerate_RecoveryCodes @Ai_User_ID = 1, -- Replace with actual user ID @Ai_Device_ID = @Ai_Device_ID , @Ai_RecoveryCodeCount_NUMB = 10, -- Or any other number of codes you want @Ai_UpdatedBy_ID = 1, -- Typically the same as User_ID or admin ID @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description
usp_TwoFactorRecoveryCode_Update_S1 | DECLARE @Ai_RecoveryCode_ID INT = NULL, -- Optional: Pass NULL to lookup by code/email @As_RecoveryCode_TEXT NVARCHAR(256) = 'AF60E2A7C7100ACFC6FBBC20A6806FC85D28FCAD83DF29FA793F0F7A6377F056', -- Replace with actual recovery code (hashed) @As_EmailAddress_TEXT NVARCHAR(510) = NULL, -- Optional: Only if not using ID @Ai_User_ID INT = 1, -- Optional: If known, include this to speed up lookup @Ab_IsUsed_INDC BIT = 1, -- Set to 1 (used) or 0 (unused) @An_OldTransactionSeqEvent_NUMB BIGINT = NULL, -- Deprecated; just pass NULL @An_NewTransactionSeqEvent_NUMB BIGINT = NULL, -- Will be generated if NULL @Ai_UpdatedBy_ID INT = 1, -- Replace with actual updating user -- Outputs @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_TwoFactorRecoveryCode_Update_S1 @Ai_RecoveryCode_ID = @Ai_RecoveryCode_ID, @As_RecoveryCode_TEXT = @As_RecoveryCode_TEXT, @As_EmailAddress_TEXT = @As_EmailAddress_TEXT, @Ai_User_ID = @Ai_User_ID, @Ab_IsUsed_INDC = @Ab_IsUsed_INDC, @An_OldTransactionSeqEvent_NUMB = @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB = @An_NewTransactionSeqEvent_NUMB , @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the outcome SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Users$Sp_Update_TwoFactorDevice | DECLARE @Ai_User_ID INT = 2172, -- Replace with actual User_ID @Ab_TwoFactorEnabled_INDC BIT = 1, -- 1 = Enable, 0 = Disable @Ac_MethodCode_CODE CHAR(2) = 'TO', -- 'TO', 'SM', or 'EM' @As_DeviceName_TEXT NVARCHAR(100) = 'Test Device', -- Friendly name @As_SecretBase_TEXT NVARCHAR(64) = 'ABCDEF123456SECRETBASETEXT', @Ai_RecoveryCodeCount_NUMB INT = 5, -- Number of recovery codes @Ai_UpdatedBy_ID INT = 1, -- ID of the updater @An_OldTransactionSeqEvent_NUMB BIGINT = 1001, -- For concurrency @An_NewTransactionSeqEvent_NUMB BIGINT = NULL, @Ai_Device_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure EXEC dbo.Users$Sp_Update_TwoFactorDevice @Ai_User_ID, @Ab_TwoFactorEnabled_INDC, @Ac_MethodCode_CODE, @As_DeviceName_TEXT, @As_SecretBase_TEXT, @Ai_RecoveryCodeCount_NUMB, @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB , @Ai_Device_ID OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Output the results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message, @Ai_Device_ID AS Device_ID;
usp_DashboardQuickNav_GetList_S1 | DECLARE @Ac_UserType_CODE CHAR(1) = 'C', @Ac_Screen_CODE CHAR(5) = 'APP', @Ai_SignedOnUser_ID INT = 2099, -- Replace with actual user ID @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure EXEC dbo.usp_DashboardQuickNav_GetList_S1 @Ac_UserType_CODE = @Ac_UserType_CODE, @Ac_Screen_CODE = @Ac_Screen_CODE, @Ai_SignedOnUser_ID = @Ai_SignedOnUser_ID, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display output results SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Message;
usp_Get_Case_S1 | DECLARE @Ai_Case_ID INT = 98, -- Replace with actual Case_ID to fetch @As_Case_RefID NVARCHAR(50), @Ai_Applicant_ID INT, @Ad_CaseStartDate_DATE DATE, @Ac_Priority_CODE CHAR(1), @Ac_CaseType_CODE CHAR(1), @Ac_EligibilityDetermined_CODE CHAR(1), @Ac_EmploymentStatus_CODE CHAR(1), @Ac_EducationAttainment_CODE CHAR(1), @Ac_PreferredLanguage_CODE CHAR(2), @Ac_ReferralSource_CODE CHAR(1), @As_InitialNotes_TEXT NVARCHAR(1000), @Ac_ReasonForLayoff_CODE CHAR(2), @Ab_ReceivingUI_INDC BIT, @Ac_Disaster_CODE CHAR(2), @As_AffectedAreas_TEXT NVARCHAR(250), @Ai_CreatedBy_ID INT, @Ad_Created_DTTM DATETIME, @Ai_UpdatedBy_ID INT, @Ad_Updated_DTTM DATETIME, @Ai_TransactionSeqEvent_NUMB BIGINT, @Ai_user_ID INT, @Ac_CaseStatus_CODE CHAR(1), @As_FirstName_TEXT NVARCHAR(50), @As_MiddleName_TEXT NVARCHAR(50), @As_LastName_TEXT NVARCHAR(50), @Ad_DateOfBirth_DATE DATE, @As_SocialSecurityNumber_TEXT NVARCHAR(20), @As_EmailAddress_TEXT NVARCHAR(100), @As_PhoneNumber_TEXT NVARCHAR(20), @Ac_Gender_CODE CHAR(1), @As_GenderDesc_TEXT VARCHAR(150), @Ad_UserUpdated_DTTM DATETIME, @Ad_UserCreated_DTTM DATETIME, @As_Address_TEXT NVARCHAR(MAX), @Ai_Worker_ID INT, @As_WorkerName_TEXT NVARCHAR(100), @As_CasePrograms_TEXT NVARCHAR(MAX), @As_Barriers_TEXT NVARCHAR(MAX), @As_CaseDocuments_TEXT NVARCHAR(MAX), @As_CaseManagerAssignment_TEXT NVARCHAR(MAX), @As_PriorityDesc_TEXT NVARCHAR(50), @As_CaseTypeDesc_TEXT NVARCHAR(50), @As_EmploymentStatusDesc_TEXT NVARCHAR(50), @As_EducationAttainmentDesc_TEXT NVARCHAR(50), @As_LanguageDesc_TEXT NVARCHAR(50), @As_ReferralSourceDesc_TEXT NVARCHAR(100), @As_LayoffReasonDesc_TEXT NVARCHAR(100), @As_DisasterDesc_TEXT NVARCHAR(100), @Ac_CaseStatusDesc_TEXT NVARCHAR(100), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); -- Execute the procedure EXEC dbo.usp_Get_Case_S1 @Ai_Case_ID OUTPUT, @As_Case_RefID OUTPUT, @Ai_Applicant_ID OUTPUT, @Ad_CaseStartDate_DATE OUTPUT, @Ac_Priority_CODE OUTPUT, @Ac_CaseType_CODE OUTPUT, @Ac_EligibilityDetermined_CODE OUTPUT, @Ac_EmploymentStatus_CODE OUTPUT, @Ac_EducationAttainment_CODE OUTPUT, @Ac_PreferredLanguage_CODE OUTPUT, @Ac_ReferralSource_CODE OUTPUT, @As_InitialNotes_TEXT OUTPUT, @Ac_ReasonForLayoff_CODE OUTPUT, @Ab_ReceivingUI_INDC OUTPUT, @Ac_Disaster_CODE OUTPUT, @As_AffectedAreas_TEXT OUTPUT, @Ai_CreatedBy_ID OUTPUT, @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID OUTPUT, @Ad_Updated_DTTM OUTPUT, @Ai_TransactionSeqEvent_NUMB OUTPUT, @Ai_user_ID OUTPUT, @Ac_CaseStatus_CODE OUTPUT, @As_FirstName_TEXT OUTPUT, @As_MiddleName_TEXT OUTPUT, @As_LastName_TEXT OUTPUT, @Ad_DateOfBirth_DATE OUTPUT, @As_SocialSecurityNumber_TEXT OUTPUT, @As_EmailAddress_TEXT OUTPUT, @As_PhoneNumber_TEXT OUTPUT, @Ac_Gender_CODE OUTPUT, @As_GenderDesc_TEXT OUTPUT, @Ad_UserUpdated_DTTM OUTPUT, @Ad_UserCreated_DTTM OUTPUT, @As_Address_TEXT OUTPUT, @Ai_Worker_ID OUTPUT, @As_WorkerName_TEXT OUTPUT, @As_CasePrograms_TEXT OUTPUT, @As_Barriers_TEXT OUTPUT, @As_CaseDocuments_TEXT OUTPUT, @As_CaseManagerAssignment_TEXT OUTPUT, @As_PriorityDesc_TEXT OUTPUT, @As_CaseTypeDesc_TEXT OUTPUT, @As_EmploymentStatusDesc_TEXT OUTPUT, @As_EducationAttainmentDesc_TEXT OUTPUT, @As_LanguageDesc_TEXT OUTPUT, @As_ReferralSourceDesc_TEXT OUTPUT, @As_LayoffReasonDesc_TEXT OUTPUT, @As_DisasterDesc_TEXT OUTPUT, @Ac_CaseStatusDesc_TEXT OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- Review output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message, @As_Case_RefID AS CaseRef, @As_FirstName_TEXT AS FirstName, @As_LastName_TEXT AS LastName, @As_CasePrograms_TEXT AS ProgramsJSON, @As_Barriers_TEXT AS BarriersJSON, @As_CaseDocuments_TEXT AS DocumentsJSON, @As_CaseManagerAssignment_TEXT AS CaseManagersJSON;
usp_AssessmentSubmission_Update_S1 | DECLARE @Ai_AssessmentSubmission_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @Atvps_ProgServ NVARCHAR(MAX), @Ai_TransactionSeqEvent_NUMB BIGINT = 0; -- Sample JSON: Replace with real Program/Service codes SET @Atvps_ProgServ = N'[ { "Program_CODE": "AD", "Service_CODE": "JS" }, { "Program_CODE": "AD", "Service_CODE": "JT" }, {"Program_CODE": "YB"} ]'; EXEC dbo.usp_AssessmentSubmission_Add_S1 @Ai_Case_ID = 109, @Ai_SubmittedBy_ID = 2066, @As_CareerGoals_TEXT = N'Become a software developer', @As_CurrentJobSearch_TEXT = N'Applying to junior roles weekly', @As_SpecificCareerGoal_TEXT = N'.NET Full Stack Developer', @As_HighestEducation_TEXT = N'Bachelor of Science in IT', @As_LicensesCertificates_TEXT = N'Microsoft Azure Fundamentals', @As_SkillsToImprove_TEXT = N'C#, SQL Server, Communication', @As_EmploymentStatus_TEXT = N'Unemployed', @As_PastJobs_TEXT = N'Tech support, Data entry', @As_RecentLayoffs_TEXT = N'Company downsizing last quarter', @As_EmploymentBarriers_TEXT = N'Limited work experience', @As_HelpNeeded_TEXT = N'Resume building, Interview coaching', @As_TrainingInterest_TEXT = N'Yes, interested in coding bootcamp', @As_OtherServicesReceive_TEXT = N'Food assistance, housing support', @As_NeedsAssessmentNotes_TEXT = N'Motivated client with high learning potential', @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Atvps_ProgServ = @Atvps_ProgServ, @Ai_AssessmentSubmission_ID = @Ai_AssessmentSubmission_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output result SELECT AssessmentSubmission_ID = @Ai_AssessmentSubmission_ID, Msg_CODE = @Ac_Msg_CODE, Error_Description = @As_DescriptionError_TEXT; --SELECT * FROM CASES --SELECT * FROM AssessmentSubmission --SELECT * FROM CaseProgram --SELECT * FROM CASEPROGRAMSERVICE
usp_Get_Notifications_S1
usp_UserQuietHours_Save_S1 | DECLARE @An_TransactionSeqEvent_NUMB BIGINT = 0, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_UserQuietHours_Save_S1 @Ai_User_ID = 4, @Ab_IsEnabled_INDC = 1, @At_StartTime_TIME = '22:00:00', @At_EndTime_TIME = '06:00:00', @Ai_CreatedBy_ID = 4, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output check SELECT @An_TransactionSeqEvent_NUMB AS TransactionSeqEvent_NUMB, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError_TEXT;
usp_User_NotificationPreference_Update_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_User_ID INT = 2213, -- Replace with actual user ID @Ai_TransactionSeqEvent_NUMB BIGINT = 1, -- Replace with actual event number @As_NotificationPref_JSON NVARCHAR(MAX), @As_QuietHours_JSON NVARCHAR(MAX); -- Sample Notification Preferences JSON SET @As_NotificationPref_JSON = N'[ {"NotificationType_CODE": "NA", "Channel_CODE": "CWN", "IsEnabled_INDC": 0}, {"NotificationType_CODE": "AP", "Channel_CODE": "CWN", "IsEnabled_INDC": 0}, {"NotificationType_CODE": "CU", "Channel_CODE": "CWN", "IsEnabled_INDC": 0}, {"NotificationType_CODE": "RF", "Channel_CODE": "CWN", "IsEnabled_INDC": 1}, {"NotificationType_CODE": "JB", "Channel_CODE": "CWN", "IsEnabled_INDC": 1} ]'; -- Sample Quiet Hours JSON SET @As_QuietHours_JSON = N'{ "IsEnabled_INDC": 1, "StartTime_TIME": "10:00:00", "EndTime_TIME": "18:00:00" }'; EXEC usp_User_NotificationPreference_Update_S1 @Ai_User_ID = @Ai_User_ID, @As_NotificationPref_JSON = @As_NotificationPref_JSON, @As_QuietHours_JSON = @As_QuietHours_JSON, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS Description;
usp_TrainingEnrollments_Get_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_TrainingEnrollments_Get_S1 @Ai_Case_ID = 2017, -- replace with actual Case_ID @As_Search_TEXT = NULL, -- optional search filter @Ac_Status_CODE = NULL, -- optional status filter @Ai_SignedOnUser_ID = NULL, -- optional signed-on user @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output message SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Description;
IssPlan_AddFull_S1 | DECLARE @NewIssPlanID INT, @MsgCode CHAR(1), @ErrorDescription VARCHAR(4000); EXEC dbo.IssPlan_AddFull_S1 @Ai_Case_ID = 102, @Ai_Form_ID = NULL, @As_PlanTitle_TEXT = 'Career Development Plan', @As_PlanDesc_TEXT = 'Plan description here...', @Ad_Start_DATE = '2025-08-01', @Ad_End_DATE = '2025-12-31', @Ad_Review_DATE = '2025-09-01', @Ac_Status_CODE = 'A', @As_AdditionalServiceNote_TEXT = 'Additional service notes.', @As_ClientSignaturePath_TEXT = NULL, @As_WorkerSignaturePath_TEXT = NULL, @Ai_CreatedBy_ID = 2017, @At_TransactionSeqEvent_NUMB = 1001, @As_Goals_JSON = N'[ { "Title": "Complete training", "Description": "Complete training", "TargetDate": "2025-10-01", "ActionItems": [ {"Description": "Register for course", "DueDate": "2025-08-15", "AssignedToID": 2017, "Status": "A"}, {"Description": "Complete first module", "DueDate": "2025-09-15", "AssignedToID": 2017, "Status": "A"} ] }, { "Title": "Find internship", "Description": "Find internship", "TargetDate": "2025-11-01", "ActionItems": [ {"Description": "Apply to companies", "DueDate": "2025-10-10", "AssignedToID": 2017, "Status": "A"} ] } ]', @As_ActionItems_JSON = N'[]', -- Not used now @As_Barriers_JSON = N'[ {"Barrier": "B1", "Notes": "Transportation issues"} ]', @As_Services_JSON = N'[ {"ServiceID": 2, "AssignedToID": 2017, "DueDate": "2025-08-20"} ]', @As_Notes_JSON = N'[ {"NoteType": "GENRL", "Notes": "Initial plan notes here."} ]', @Ai_IssPlan_ID = @NewIssPlanID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Output results SELECT @NewIssPlanID AS NewIssPlanID, @MsgCode AS MessageCode, @ErrorDescription AS ErrorDescription;
IssPlan_UpdateFull_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.IssPlan_UpdateFull_S1 @Ai_IssPlan_ID = 115, @Ai_Case_ID = 102, @As_PlanTitle_TEXT = 'Career Development Plan 2', @As_PlanDesc_TEXT = 'This is a sample plan description', @Ad_Start_DATE = '2025-08-01', @Ad_End_DATE = '2025-12-31', @Ad_Review_DATE = '2025-10-15', @Ac_Status_CODE = 'A', @As_AdditionalServiceNote_TEXT = 'Some additional notes here', @As_ClientSignaturePath_TEXT = '/signatures/client.png', @As_WorkerSignaturePath_TEXT = '/signatures/worker.png', @Ai_UpdatedBy_ID = 2017, -- Concurrency @At_OldTransactionSeqEvent_NUMB = 1001, @At_TransactionSeqEvent_NUMB = 1001, -- JSON payloads @As_Goals_JSON = N'[{"Title": "Improve communication skills","Description": "Improve communication skills", "TargetDate": "2025-09-15"}]', @As_ActionItems_JSON = N'[{"Description": "Attend 2 workshops", "DueDate": "2025-09-01", "AssignedToID": 2017, "Status": "A"}]', @As_Barriers_JSON = N'[{"Barrier": "B1", "Notes": "Lack of transportation"}]', @As_Services_JSON = N'[{"ServiceID": 3, "AssignedToID": 2017, "DueDate": "2025-08-15"}]', @As_Notes_JSON = N'[{"NoteType": "OT", "Notes": "Initial meeting completed."}]', -- Output @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output values SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
usp_UserProgress_Milestones_Get_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(500); EXEC usp_UserProgress_Milestones_Get_S1 @Ai_Case_ID = 101, -- Replace with actual Case_ID @Ac_Program_CODE = 'AD,YT,DW', -- Or 'YT', 'AD', etc. if filtering by program @Ac_Status_CODE = NULL, -- Or 'A', 'C', etc. for Active, Completed, etc. @Ai_From_NUMB = 1, -- Paging start @Ai_To_NUMB = 10, -- Paging limit @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optional: view output message and description SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
usp_Goal_Add_S1 | DECLARE @Msg CHAR(1), @MsgText NVARCHAR(500), @GoalID INT; EXEC usp_Goal_Add_S1 @Ai_Case_ID = 98, @Ai_IssPlan_ID = 123, @As_GoalTitle_TEXT = 'Obtain Driver’s License', @As_GoalDescription_TEXT = 'Complete all steps required to receive a valid driver’s license', @Ac_Category_CODE = NULL, @Ac_Program_CODE = 'AD', @Ac_Service_CODE = null, @Ad_Due_DATE = '2025-08-01', @Ac_Status_CODE = 'N', @As_Notes_TEXT = 'Client to complete driving school first', @Ad_Completed_DTTM = NULL, @As_ActionItems_JSON = N' [ { "ActionDescription_TEXT": "Enroll in driving school", "DueDate_DATE": "2025-07-01", "ResponsibleParty_ID": 12, "Category_CODE" : "JS", "Service_ID" : 2, "Referral_TEXT": "Refer to ABC Driving School", "Notes_TEXT": "Ask for weekday classes", "Status_CODE": "A" }, { "ActionDescription_TEXT": "Schedule driving test", "DueDate_DATE": "2025-07-20", "ResponsibleParty_ID": 12, "Category_CODE" :"JS", "Service_ID" : 2, "Notes_TEXT": "After school certificate is obtained", "Status_CODE": "A" } ]', @Ai_CreatedBy_ID = 12, @An_TransactionSeqEvent_NUMB = 1, @Ai_IssGoal_ID = @GoalID OUTPUT, @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @Msg AS Msg, @MsgText AS Message, @GoalID AS NewGoalID;
usp_Duplication_Check_S1 | DECLARE @Msg_Code CHAR(5), @DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_Duplication_Check_S1 @As_FirstName_TEXT = 'John', @As_MiddleName_TEXT = NULL, @As_LastName_TEXT = 'Doe', @Ad_DateOfBirth = NULL, @As_SSN_TEXT = NULL, @As_EmailAddress_TEXT = NULL, @As_PhoneNumber_TEXT = NULL, @Ac_Gender_CODE = 'M', @Ai_SignedOnUser_ID = 2099, @Ac_Msg_Code = @Msg_Code OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- Show output parameters SELECT @Msg_Code AS Msg_Code, @DescriptionError_TEXT AS DescriptionError;
usp_ReferralResponse_Update_S1 | -- Declare variables for output DECLARE @Ac_Msg_CODE CHAR(1); DECLARE @As_DescriptionError_TEXT NVARCHAR(4000); -- Call the procedure EXEC dbo.usp_ReferralResponse_Update_S1 @Ai_Referral_ID = 1, -- Replace with your Referral ID @As_Response_CODE = 'D', -- Replace with response code (e.g., 'A', 'D', etc.) @As_DeclineReason_TEXT = 'Not qualified', -- Optional, can be NULL if not declining @Ai_UpdatedBy_ID = 2066, -- User ID performing the update @An_TransactionSeqEvent_NUMB = 1, -- Transaction number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output values SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Announcement_Add | DECLARE @Ai_Announcement_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC [dbo].[Announcement_Add] @As_Title_TEXT = N'New System Update', -- Title @As_MessageBody_TEXT = N'There will be a system maintenance on Friday night.', -- Message Body @Ac_AnnouncementType_CODE = 'I', -- Announcement Type Code @Ad_Start_DATE = '2025-08-14', -- Start Date @Ad_Expiry_DATE = '2025-08-28', -- Expiry Date (optional) @Ai_SignedOnUser_ID = 1, -- User ID @Ai_TransactionSeqEvent_NUMB = 0, -- Set to 0 to auto-generate @Ai_Announcement_ID = @Ai_Announcement_ID OUTPUT, -- OUTPUT: new announcement ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, -- OUTPUT: message code (S/F) @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- OUTPUT: error/description -- View the output SELECT @Ai_Announcement_ID AS AnnouncementID, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
User_GetPassword_S1 | DECLARE @PasswordHash NVARCHAR(MAX), @AccountStatus CHAR(1), @IsLocked BIT, @LastPasswordChange DATETIME, @MsgCode CHAR(1), @DescriptionError VARCHAR(4000); EXEC dbo.User_GetPassword_S1 @Ai_User_ID = NULL, @As_EmailAddress_TEXT = 'wioacwpadmin@gboxz.com', @As_PasswordHash_TEXT = @PasswordHash OUTPUT, @Ac_AccountStatus_CODE = @AccountStatus OUTPUT, @Ab_IsLocked_INDC = @IsLocked OUTPUT, @Ad_LastPasswordChange_DTTM = @LastPasswordChange OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @DescriptionError OUTPUT; -- Optional: View output values SELECT @PasswordHash AS PasswordHash, @AccountStatus AS AccountStatus, @IsLocked AS IsLocked, @LastPasswordChange AS LastPasswordChange, @MsgCode AS MsgCode, @DescriptionError AS Description;
Users$Sp_Login_Success_S1 | DECLARE @MsgCode CHAR(1), @DescriptionError VARCHAR(4000); EXEC dbo.Users$Sp_Login_Success_S1 @As_EmailAddress_TEXT = 'wioacwpadmin@gboxz.com', @As_IPAddress_TEXT = '192.168.1.10', @As_UserAgent_TEXT = 'Mozilla/5.0 (Windows NT 10.0; Win64; x64)', @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @DescriptionError OUTPUT; -- View output SELECT @MsgCode AS MsgCode, @DescriptionError AS Description;
Users$Sp_Password_Fails_S1 | DECLARE @MsgCode CHAR(1), @DescriptionError VARCHAR(4000); EXEC dbo.Users$Sp_Password_Fails_S1 @As_EmailAddress_TEXT = 'wioacwpadmin@gboxz.com', @As_IPAddress_TEXT = '192.168.1.10', @As_UserAgent_TEXT = 'Mozilla/5.0 (Windows NT 10.0; Win64; x64)', @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @DescriptionError OUTPUT; -- View output SELECT @MsgCode AS MsgCode, @DescriptionError AS Description;
IssGoal_Update_S1 | DECLARE @Ai_Goal_ID INT = 178, @As_GoalTitle_TEXT NVARCHAR(100) = N'Improve Reading Skills', @As_GoalDescription_TEXT NVARCHAR(500) = N'Focus on reading comprehension improvement.', @Ac_Category_CODE CHAR(10) = null, @Ac_Program_CODE CHAR(2) = 'YP', @Ac_Service_CODE CHAR(2) = NULL, @Ad_Due_DATE DATE = '2025-12-31', @Ac_Status_CODE CHAR(1) = 'N', @As_Notes_TEXT NVARCHAR(MAX) = N'Updated goal after parent meeting.', @Ai_UpdatedBy_ID INT = 12, @An_TransactionSeqEvent_NUMB BIGINT = 1, @As_ActionItems_JSON NVARCHAR(MAX) = N' [ { "ActionDescription_TEXT": "Daily reading sessions", "DueDate_DATE": "2025-10-15", "ResponsibleParty_ID": 1, "Status_CODE": "A", "Program_CODE": "ap", "Service_CODE": null, "Service_ID": 2, "Category_CODE": "CE", "Notes_TEXT": "Start with basic vocabulary.", "Referral_TEXT": "N/A" } ]', @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(500); -- Execute the stored procedure EXEC IssGoal_Update_S1 @Ai_Goal_ID, @As_GoalTitle_TEXT, @As_GoalDescription_TEXT, @Ac_Category_CODE, @Ac_Program_CODE, @Ac_Service_CODE, @Ad_Due_DATE, @Ac_Status_CODE, @As_Notes_TEXT, @Ai_UpdatedBy_ID, @An_TransactionSeqEvent_NUMB, @As_ActionItems_JSON, @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- View output SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorDescription;
usp_IssPlan_RetrieveByID_S1 | -- Declare all variables DECLARE @Ai_Case_ID INT = 98, -- Input: Replace with actual Case ID -- Output variables @Ai_IssPlan_ID INT, @As_PlanTitle_TEXT VARCHAR(100), @As_PlanDesc_TEXT VARCHAR(4000), @Ad_Start_DATE DATE, @Ad_End_DATE DATE, @Ad_Review_DATE DATE, @Ac_Status_CODE CHAR(1), @As_StatusDesc_TEXT VARCHAR(400), @As_AdditionalServiceNote_TEXT VARCHAR(400), @As_ClientSignaturePath_TEXT VARCHAR(4000), @As_WorkerSignaturePath_TEXT VARCHAR(4000), @Ai_CreatedBy_ID INT, @As_CreatedByname_TEXT VARCHAR(4000), @Ai_Participant_ID VARCHAR(200), @Ad_Created_DTTM DATETIME, @Ai_UpdatedBy_ID INT, @Ad_Updated_DTTM DATETIME, @At_TransactionSeqEvent_NUMB BIGINT, @Ai_CaseWorkerUser_ID INT, @As_Notes_Json NVARCHAR(MAX), @As_Goals_JSON NVARCHAR(MAX), @As_ServiceNeeded_JSON NVARCHAR(MAX), @As_ActionItems_JSON NVARCHAR(MAX), @As_Barriers_JSON NVARCHAR(MAX), @Ac_Msg_Code CHAR(5), @As_Error_Description VARCHAR(4000); -- Execute the procedure EXEC dbo.usp_IssPlan_RetrieveByID_S1 @Ai_Case_ID, @Ai_IssPlan_ID OUTPUT, @As_PlanTitle_TEXT OUTPUT, @As_PlanDesc_TEXT OUTPUT, @Ad_Start_DATE OUTPUT, @Ad_End_DATE OUTPUT, @Ad_Review_DATE OUTPUT, @Ac_Status_CODE OUTPUT, @As_StatusDesc_TEXT OUTPUT, @As_AdditionalServiceNote_TEXT OUTPUT, @As_ClientSignaturePath_TEXT OUTPUT, @As_WorkerSignaturePath_TEXT OUTPUT, @Ai_CreatedBy_ID OUTPUT, @As_CreatedByname_TEXT OUTPUT, @Ai_Participant_ID OUTPUT, @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID OUTPUT, @Ad_Updated_DTTM OUTPUT, @At_TransactionSeqEvent_NUMB OUTPUT, @Ai_CaseWorkerUser_ID OUTPUT, @As_Notes_Json OUTPUT, @As_Goals_JSON OUTPUT, @As_ServiceNeeded_JSON OUTPUT, @As_ActionItems_JSON OUTPUT, @As_Barriers_JSON OUTPUT, @Ac_Msg_Code OUTPUT, @As_Error_Description OUTPUT; -- View output values SELECT @Ai_IssPlan_ID AS IssPlan_ID, @As_PlanTitle_TEXT AS PlanTitle, @As_PlanDesc_TEXT AS PlanDescription, @Ad_Start_DATE AS StartDate, @Ad_End_DATE AS EndDate, @Ad_Review_DATE AS ReviewDate, @Ac_Status_CODE AS StatusCode, @As_StatusDesc_TEXT AS StatusDescription, @As_AdditionalServiceNote_TEXT AS AdditionalServiceNote, @As_ClientSignaturePath_TEXT AS ClientSignaturePath, @As_WorkerSignaturePath_TEXT AS WorkerSignaturePath, @Ai_CreatedBy_ID AS CreatedByID, @As_CreatedByname_TEXT AS CreatedByName, @Ai_Participant_ID AS ParticipantID, @Ad_Created_DTTM AS CreatedDateTime, @Ai_UpdatedBy_ID AS UpdatedByID, @Ad_Updated_DTTM AS UpdatedDateTime, @At_TransactionSeqEvent_NUMB AS TransactionSeqEvent, @Ai_CaseWorkerUser_ID AS CaseWorkerUserID, @As_Notes_Json AS NotesJson, @As_Goals_JSON AS GoalsJson, @As_ServiceNeeded_JSON AS ServicesJson, @As_ActionItems_JSON AS ActionItemsJson, @As_Barriers_JSON AS BarriersJson, @Ac_Msg_Code AS MsgCode, @As_Error_Description AS ErrorDescription;
usp_Applicant_InsertBase_S1 | DECLARE @NewApplicantID INT, @MsgCode CHAR(5), @ErrorDesc VARCHAR(4000); EXEC dbo.usp_Applicant_InsertBase_S1 @As_FirstName_TEXT = 'John', @As_MiddleName_TEXT = NULL, @As_LastName_TEXT = 'Doe', @Ad_DateOfBirth_DATE = '1990-05-15', @As_SocialSecurityNumber_TEXT = '123-45-6789', @As_Gender_CODE = 'M', @Ab_WorkAuthorization_INDC = 1, @As_EmploymentStatus_CODE = 'E', @Ab_LaidOffOrTerminated_INDC = 0, @Ab_ReceivingUI_INDC = 0, @Ab_VeteranOrSpouse_INDC = 0, @Ab_CriminalJustice_INDC = 0, @Ab_SeasonalAgriculturalWork_INDC = 0, @Ab_AmericanIndian_INDC = 0, @Ab_RegisteredApprenticeship_INDC = 0, @Ab_ResidentialEducation_INDC = 0, @Ab_TradeTraining_INDC = 0, @As_LowIncome_CODE = 'Y', @Ab_NeedHelpTraining_INDC = 1, @As_HighSchoolDiplomaOrGED_CODE = 'Y', @As_ApplicationRef_TEXT = 'APP12345', @As_ApplicantStatus_CODE = 'P', @Ad_ApplicationStatus_DATE = GETDATE(), @Ac_ApplicationType_CODE = 'O', -- ON = Online / IP = In-person @Ai_CreatedBy_ID = 101, @As_PhoneNumber_TEXT = '555-123-4567', @As_EmailAddress_TEXT = 'john.doe@email.com', @Ai_TransactionSeqEvent_NUMB = NULL, @Ai_NewApplicantID = @NewApplicantID OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- ✅ See the results SELECT @NewApplicantID AS NewApplicantID, @MsgCode AS MsgCode, @ErrorDesc AS ErrorDescription;
usp_Template_GetAll_S1 | DECLARE @MsgCode CHAR(5); DECLARE @ErrorDescription VARCHAR(4000); EXEC dbo.usp_Template_GetAll_S1 @As_ModuleCategory_TEXT = 'D', -- Replace with actual value -- D,M,R,F @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Optional: View the outputs SELECT @MsgCode AS MsgCode, @ErrorDescription AS ErrorDescription;
usp_Document_UpdateStatus_S1 | DECLARE @MsgCode CHAR(5); DECLARE @ErrorDescription NVARCHAR(4000); -- Set to 0 to trigger generation if needed EXEC dbo.usp_Document_UpdateStatus_S1 @Ai_ApplicantID = 241, -- Replace with actual Applicant_ID @Ai_Document_ID = 250, -- Replace with actual Document_ID @As_DocumentStatus_CODE = 'V', -- Replace with valid status code from RefDocumentVerificationStatus @As_Notes_TEXT = N'Approved after review.', -- Optional notes @Ai_CreatedBy_ID = 1, -- Replace with the user ID performing the action @An_TransactionSeqEvent_NUMB = 0 , @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Optional: Display output values SELECT @MsgCode AS MsgCode, @ErrorDescription AS Description;
usp_PreliminaryNote_Get_S1 | DECLARE @MsgCode CHAR(5); DECLARE @ErrorDescription VARCHAR(4000); EXEC usp_PreliminaryNote_Get_S1 @Ai_Applicant_ID = 123, -- Replace with actual Applicant_ID @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Optional: check the output messages SELECT @MsgCode AS MsgCode, @ErrorDescription AS Description;
usp_ApplicantEligibleProgram_GetAll_S8 | DECLARE @ApplicantID INT = 12, -- Replace with the actual Applicant ID @MsgCode CHAR(5), @ErrorDescription NVARCHAR(4000); EXEC dbo.usp_ApplicantEligibleProgram_GetAll_S8 @Ai_ApplicantID = @ApplicantID, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Check output messages SELECT @MsgCode AS MsgCode, @ErrorDescription AS Description;
usp_PreliminaryNote_AddUpdate_S1 | DECLARE @ApplicantID INT = 12, -- Replace with actual Applicant ID @Notes NVARCHAR(MAX) = N'Updated preliminary notes text here', @CreatedByID INT = 2099, -- Replace with actual user ID who is making the update -- @TransactionSeqEventNum BIGINT = 0, -- Set 0 to auto-generate a new transaction event number @MsgCode CHAR(5), @ErrorDescription VARCHAR(4000); EXEC dbo.usp_PreliminaryNote_AddUpdate_S1 @Ai_Applicant_ID = @ApplicantID, @As_Notes_TEXT = @Notes, @Ai_CreatedBy_ID = @CreatedByID, @An_TransactionSeqEvent_NUMB = 0, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Check the result status SELECT @MsgCode AS MsgCode, @ErrorDescription AS Description;
usp_Document_GetAll_S3 | DECLARE @ApplicantID INT = 12, -- Replace with actual Applicant ID @DocumentID INT = NULL, -- Replace with actual Document ID or NULL to get all documents @MsgCode CHAR(5), @ErrorDescription NVARCHAR(4000); EXEC dbo.usp_Document_GetAll_S3 @Ai_ApplicantID = @ApplicantID, @Ai_Document_ID = @DocumentID, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Check status and errors SELECT @MsgCode AS MsgCode, @ErrorDescription AS Description;
usp_Applicant_GetDetails_S1 | DECLARE @Applicant_ID INT = 12, -- Input Applicant ID to fetch details for @User_ID INT, @Workspace_ID INT, @FirstName NVARCHAR(50), @MiddleName NVARCHAR(50), @LastName NVARCHAR(50), @DateOfBirth DATE, @SocialSecurityNumber NVARCHAR(11), @Gender_CODE CHAR(1), @GenderDesc VARCHAR(250), @WorkAuthorization BIT, @SelectiveService BIT, @EmploymentStatus_CODE CHAR(1), @LaidOffOrTerminated BIT, @ReceivingUI BIT, @VeteranOrSpouse BIT, @CriminalJustice BIT, @SeasonalAgriculturalWork BIT, @AmericanIndian BIT, @RegisteredApprenticeship BIT, @ResidentialEducation BIT, @TradeTraining BIT, @LowIncome_CODE CHAR(1), @NeedHelpTraining BIT, @HighSchoolDiplomaOrGED_CODE CHAR(1), @PhoneNumber NVARCHAR(20), @EmailAddress NVARCHAR(100), @ConsentConfirmed BIT, @Signature NVARCHAR(100), @ConsentDate DATETIME, @SignatureDocURL NVARCHAR(250), @ApplicationRef NVARCHAR(50), @ApplicantStatus_CODE CHAR(1), @ApplicantStatusDesc VARCHAR(250), @CancelReason NVARCHAR(250), @CreatedBy_ID INT, @Created_DTTM DATETIME, @EligibilityDetermined_Date DATETIME, @UpdatedBy_ID INT, @Updated_DTTM DATETIME, @TransactionSeqEvent_NUMB BIGINT, @EmploymentStatusDesc VARCHAR(250), @HighSchoolDiplomaOrGEDDesc VARCHAR(250), @LowIncomeDesc VARCHAR(250), @Document_JSON NVARCHAR(MAX), @PublicAssistance_JSON NVARCHAR(MAX), @Barrier_JSON NVARCHAR(MAX), @EligiblePrograms_JSON NVARCHAR(MAX), @Address_JSON NVARCHAR(MAX), @LastEmployer NVARCHAR(MAX), @JobPosition NVARCHAR(MAX), @EndDate DATETIME, @CurrentEmployed VARCHAR(10), @HighestEducation NVARCHAR(MAX), @School NVARCHAR(MAX), @GraduationYear NVARCHAR(MAX), @ReasonForLeaving NVARCHAR(MAX), @MsgCode CHAR(5), @Description NVARCHAR(4000); EXEC dbo.usp_Applicant_GetDetails_S1 @Ai_Applicant_ID = @Applicant_ID OUTPUT, @Ai_user_ID = @User_ID OUTPUT, @Ai_Workspace_ID = @Workspace_ID OUTPUT, @As_FirstName_TEXT = @FirstName OUTPUT, @As_MiddleName_TEXT = @MiddleName OUTPUT, @As_LastName_TEXT = @LastName OUTPUT, @Ad_DateOfBirth_DATE = @DateOfBirth OUTPUT, @As_SocialSecurityNumber_TEXT = @SocialSecurityNumber OUTPUT, @As_Gender_CODE = @Gender_CODE OUTPUT, @As_GenderDesc_TEXT = @GenderDesc OUTPUT, @Ab_WorkAuthorization_INDC = @WorkAuthorization OUTPUT, @Ab_SelectiveService_INDC = @SelectiveService OUTPUT, @As_EmploymentStatus_CODE = @EmploymentStatus_CODE OUTPUT, @Ab_LaidOffOrTerminated_INDC = @LaidOffOrTerminated OUTPUT, @Ab_ReceivingUI_INDC = @ReceivingUI OUTPUT, @Ab_VeteranOrSpouse_INDC = @VeteranOrSpouse OUTPUT, @Ab_CriminalJustice_INDC = @CriminalJustice OUTPUT, @Ab_SeasonalAgriculturalWork_INDC = @SeasonalAgriculturalWork OUTPUT, @Ab_AmericanIndian_INDC = @AmericanIndian OUTPUT, @Ab_RegisteredApprenticeship_INDC = @RegisteredApprenticeship OUTPUT, @Ab_ResidentialEducation_INDC = @ResidentialEducation OUTPUT, @Ab_TradeTraining_INDC = @TradeTraining OUTPUT, @As_LowIncome_CODE = @LowIncome_CODE OUTPUT, @Ab_NeedHelpTraining_INDC = @NeedHelpTraining OUTPUT, @As_HighSchoolDiplomaOrGED_CODE = @HighSchoolDiplomaOrGED_CODE OUTPUT, @As_PhoneNumber_TEXT = @PhoneNumber OUTPUT, @As_EmailAddress_TEXT = @EmailAddress OUTPUT, @Ab_ConsentConfirmed_INDC = @ConsentConfirmed OUTPUT, @As_Signature_TEXT = @Signature OUTPUT, @Ad_ConsentDate_DTTM = @ConsentDate OUTPUT, @As_SignatureDocURL_TEXT = @SignatureDocURL OUTPUT, @As_ApplicationRef_TEXT = @ApplicationRef OUTPUT, @As_ApplicantStatus_CODE = @ApplicantStatus_CODE OUTPUT, @As_ApplicantStatusDesc_TEXT = @ApplicantStatusDesc OUTPUT, @As_CancelReason_TEXT = @CancelReason OUTPUT, @Ai_CreatedBy_ID = @CreatedBy_ID OUTPUT, @Ad_Created_DTTM = @Created_DTTM OUTPUT, @Ad_EligibilityDetermined_Date = @EligibilityDetermined_Date OUTPUT, @Ai_UpdatedBy_ID = @UpdatedBy_ID OUTPUT, @Ad_Updated_DTTM = @Updated_DTTM OUTPUT, @Ai_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB OUTPUT, @As_EmploymentStatusDesc_TEXT = @EmploymentStatusDesc OUTPUT, @As_HighSchoolDiplomaOrGEDDesc_TEXT = @HighSchoolDiplomaOrGEDDesc OUTPUT, @As_LowIncomeDesc_TEXT = @LowIncomeDesc OUTPUT, @As_Document_TEXT = @Document_JSON OUTPUT, @As_PublicAssistance_TEXT = @PublicAssistance_JSON OUTPUT, @As_Barrier_TEXT = @Barrier_JSON OUTPUT, @As_EligiblePrograms_TEXT = @EligiblePrograms_JSON OUTPUT, @As_Address_TEXT = @Address_JSON OUTPUT, @As_Lastemployer_TEXT = @LastEmployer OUTPUT, @As_jobposition_TEXT = @JobPosition OUTPUT, @Ad_enddate_DTTM = @EndDate OUTPUT, @As_currentemployed_TEXT = @CurrentEmployed OUTPUT, @As_Highesteducation_TEXT = @HighestEducation OUTPUT, @As_School_TEXT = @School OUTPUT, @As_graduationyear_TEXT = @GraduationYear OUTPUT, @As_Reasonforleaving_TEXT = @ReasonForLeaving OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @Description OUTPUT; SELECT @MsgCode AS MsgCode, @Description AS Description, @Applicant_ID AS Applicant_ID, @User_ID AS User_ID, @Workspace_ID AS Workspace_ID, @FirstName AS FirstName, @MiddleName AS MiddleName, @LastName AS LastName, @DateOfBirth AS DateOfBirth, @SocialSecurityNumber AS SocialSecurityNumber, @Gender_CODE AS Gender_CODE, @GenderDesc AS GenderDesc, @WorkAuthorization AS WorkAuthorization, @SelectiveService AS SelectiveService, @EmploymentStatus_CODE AS EmploymentStatus_CODE, @EmploymentStatusDesc AS EmploymentStatusDesc, @LaidOffOrTerminated AS LaidOffOrTerminated, @ReceivingUI AS ReceivingUI, @VeteranOrSpouse AS VeteranOrSpouse, @CriminalJustice AS CriminalJustice, @SeasonalAgriculturalWork AS SeasonalAgriculturalWork, @AmericanIndian AS AmericanIndian, @RegisteredApprenticeship AS RegisteredApprenticeship, @ResidentialEducation AS ResidentialEducation, @TradeTraining AS TradeTraining, @LowIncome_CODE AS LowIncome_CODE, @LowIncomeDesc AS LowIncomeDesc, @NeedHelpTraining AS NeedHelpTraining, @HighSchoolDiplomaOrGED_CODE AS HighSchoolDiplomaOrGED_CODE, @HighSchoolDiplomaOrGEDDesc AS HighSchoolDiplomaOrGEDDesc, @PhoneNumber AS PhoneNumber, @EmailAddress AS EmailAddress, @ConsentConfirmed AS ConsentConfirmed, @Signature AS Signature, @ConsentDate AS ConsentDate, @SignatureDocURL AS SignatureDocURL, @ApplicationRef AS ApplicationRef, @ApplicantStatus_CODE AS ApplicantStatus_CODE, @ApplicantStatusDesc AS ApplicantStatusDesc, @CancelReason AS CancelReason, @CreatedBy_ID AS CreatedBy_ID, @Created_DTTM AS CreatedDate, @EligibilityDetermined_Date AS EligibilityDeterminedDate, @UpdatedBy_ID AS UpdatedBy_ID, @Updated_DTTM AS UpdatedDate, @TransactionSeqEvent_NUMB AS TransactionSeqEvent, @LastEmployer AS LastEmployer, @JobPosition AS JobPosition, @EndDate AS EndDate, @CurrentEmployed AS CurrentEmployed, @HighestEducation AS HighestEducation, @School AS School, @GraduationYear AS GraduationYear, @ReasonForLeaving AS ReasonForLeaving, @Document_JSON AS DocumentsJson, @PublicAssistance_JSON AS PublicAssistanceJson, @Barrier_JSON AS BarrierJson, @EligiblePrograms_JSON AS EligibleProgramsJson, @Address_JSON AS AddressJson;
usp_Case_ProgramService_Add_S1 | DECLARE @Msg CHAR(5), @Desc VARCHAR(4000); EXEC usp_Case_ProgramService_Add_S1 @Ai_Case_ID = 19, @As_CaseProgramService_JSON = N'[{"Program_ID":1,"ProgramStatus_CODE":"A","ProgramStart_DATE":"2024-01-01","ProgramEnd_DATE":"2024-12-31","Service_ID":3,"ServiceStatus_CODE":"A","ServiceStart_DATE":"2024-02-01","ServiceEnd_DATE":"2024-11-30"}]', @Ai_CreatedBy_ID = 12, @Ai_TransactionSeqEvent_NUMB = 1, @Ac_Msg_Code = @Msg OUTPUT, @As_DescriptionError_TEXT = @Desc OUTPUT; SELECT @Msg AS MsgCode, @Desc AS Message;
usp_Document_Insert_S3 | DECLARE @ApplicantID INT = 235, @CreatedByID INT = 1, @TransactionSeqEvent_NUMB BIGINT = 0, -- or an existing number if known @DocumentsJson NVARCHAR(MAX), @NewDocumentsJson NVARCHAR(MAX), @MsgCode CHAR(5), @DescriptionError VARCHAR(4000); -- Sample JSON array of documents to insert SET @DocumentsJson = N' [ { "DocumentType_CODE": "SS", "FileName_TEXT": "id_card.pdf", "FilePath_TEXT": "/uploads/docs/id_card.pdf", "FileSize_NUMB": 205000 }, { "DocumentType_CODE": "VR", "FileName_TEXT": "proof_of_residence.pdf", "FilePath_TEXT": "/uploads/docs/proof_of_residence.pdf", "FileSize_NUMB": 153000 } ]'; -- Call the stored procedure EXEC dbo.usp_Document_Insert_S3 @Ai_ApplicantID = @ApplicantID, @Js_Documents = @DocumentsJson, @Ai_CreatedBy_ID = @CreatedByID, @An_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB, @As_NewDocuments = @NewDocumentsJson OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @DescriptionError OUTPUT; -- Output the results SELECT @MsgCode AS MsgCode, @DescriptionError AS Description, @NewDocumentsJson AS InsertedDocumentsJson;
WORKINGHOURS_Save_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.WORKINGHOURS_Save_S1 @Ai_User_ID = 2, @Ai_TransactionSeqEvent_NUMB = 0, @As_WeeklySchedule_JSON = '[ { "DayOfWeek_CODE": "MON", "Available_INDC": 1, "TimeSegments": [ { "StartDate_DTTM": "09:00:00", "EndDate_DTTM": "11:00:00" },{ "StartDate_DTTM": "13:00:00", "EndDate_DTTM": "17:00:00" } ] }, { "DayOfWeek_CODE": "TUE", "Available_INDC": 1, "TimeSegments": [ { "StartDate_DTTM": "09:00:00", "EndDate_DTTM": "17:00:00" } ] }, { "DayOfWeek_CODE": "WED", "Available_INDC": 1, "TimeSegments": [ { "StartDate_DTTM": "09:00:00", "EndDate_DTTM": "17:00:00" } ] }, { "DayOfWeek_CODE": "THU", "Available_INDC": 1, "TimeSegments": [ { "StartDate_DTTM": "09:00:00", "EndDate_DTTM": "17:00:00" } ] }, { "DayOfWeek_CODE": "FRI", "Available_INDC": 1, "TimeSegments": [ { "StartDate_DTTM": "09:00:00", "EndDate_DTTM": "17:00:00" } ] }, { "DayOfWeek_CODE": "SAT", "Available_INDC": 0, "TimeSegments": [] }, { "DayOfWeek_CODE": "SUN", "Available_INDC": 0, "TimeSegments": [] } ]', @As_OverrideSchedule_JSON = '[ { "OverrideDate_DATE": "2025-06-20", "Available_INDC": 1, "TimeSegments": [ { "StartDate_DTTM": "09:00:00", "EndDate_DTTM": "11:00:00" },{ "StartDate_DTTM": "13:00:00", "EndDate_DTTM": "17:00:00" } ] }, { "OverrideDate_DATE": "2025-06-21", "Available_INDC": 0, "TimeSegments": [] } ]', @Ad_OverrideFrom_DATE = '2025-06-20', @Ad_OverrideTo_DATE = '2025-06-21', @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT;
UNIT_RetrieveAll_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure EXEC dbo.UNIT_RetrieveAll_S1 @Ai_Workspace_ID = 3, -- Optional: specify a single Workspace ID @As_Workspaces_TEXT = N'101,102,103', -- Optional: comma-separated Workspace_IDs @As_User_TEXT = N'2001,2002', -- Optional: comma-separated User_IDs (must be members) @As_WorkspaceName_TEXT = N'Finance', -- Optional: partial match for workspace name @As_Unit_TEXT = N'3,1', -- Optional: comma-separated Unit_IDs @As_UnitName_TEXT = N'HR', -- Optional: partial match for unit name @Ac_Status_CODE = 'A', -- Optional: filter by unit status (e.g., 'A', 'I') @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Review the output status SELECT MsgCode = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
CALENDAR_Add_S1 | DECLARE @lc_Calendar_ID INT, @lc_Msg_CODE CHAR(5), @ls_DescriptionError_TEXT VARCHAR(4000); EXEC CALENDAR_Add_S1 @Ai_Workspace_ID = 3, @As_CalendarName_TEXT = 'Calendar12', @As_CalendarDesc_TEXT = 'Team meeting schedule for Q3', @As_CalendarURL_TEXT = 'https://company.com/calendars/q3', @Ac_Security_CODE = 'U', @Ab_Internal_INDC = 0, @Ad_StartDate = '2025-06-01', @Ad_EndDate = '2025-09-30', @Ab_MeetingInperson_INDC = 1, @Ab_MeetingOnline_INDC = 0, @Ab_MeetingTelephone_INDC = 0, @Ai_AppointmentDuration_NUMB = 30, @Ai_TimeBetweenAppointments_NUMB = 10, @Ai_AppointmentPerSlot_NUMB = 1, @As_Form_TEXT = NULL, @Ab_ShowOrganizerName_INDC = 1, @Ab_AllowAttendeeChooseOrganizer_INDC = 0, @Ab_AllowInviteGuests_INDC = 1, @Ai_Unit_ID = 1, @Ac_AssignmentMethod_CODE = 'R', @Ac_AssignmentCriteria_CODE = 'E', @Ai_CreatedBy_ID = 3, @Ai_TransactionSeqEvent_NUMB = NULL, @Ac_Status_CODE = 'A', @As_Location_TEXT = 'kenya,HG,US', @Ac_Color_CODE = NULL, @Ai_Calendar_ID = @lc_Calendar_ID output, @Ac_Msg_CODE = @lc_Msg_CODE output, @As_DescriptionError_TEXT = @ls_DescriptionError_TEXT output; SELECT @lc_Calendar_ID AS Calendar_ID,@lc_Msg_CODE AS Msg_Code,@ls_DescriptionError_TEXT AS Error_Description;
Calendar$Sp_Update_Calendar | DECLARE @Li_RowsAffected_NUMB INT , @Lc_Msg_CODE CHAR(1) , @Ls_DescriptionError_TEXT NVARCHAR(500); EXEC Calendar$Sp_Update_Calendar @Ai_Workspace_ID = 3, @Ai_Calendar_ID = 2, @As_CalendarName_TEXT = 'Calendar for events', @As_CalendarDesc_TEXT= 'new calendar for workspace to maintain events related meetings', @Ac_Security_CODE = 'P', @Ab_Internal_INDC =0, @Ad_Start_DATE = '2025-05-15', @Ad_End_DATE = '2025-06-12' , @Ai_UpdatedBy_ID = 3, @Ab_MeetingInperson_INDC = 0, @Ab_MeetingOnline_INDC = 1, @Ab_MeetingTelephone_INDC = 1, @Ai_AppointmentDuration_NUMB = 20, @Ai_TimeBetweenAppointments_NUMB = 15, @Ai_AppointmentPerSlot_NUMB = 5, @As_Form_TEXT = null, @Ab_ShowOrganizerName_INDC = 0, @Ab_AllowAttendeeChooseOrganizer_INDC = 1, @Ab_AllowInviteGuests_INDC = 1, @Ai_Unit_ID = 1, @Ac_AssignmentMethod_CODE = 'C', @Ac_AssignmentCriteria_CODE = NULL, @An_OldTransactionSeqEvent_NUMB = 336, @An_NewTransactionSeqEvent_NUMB = 0, @As_Location_TEXT = NULL, --- NEW @As_CalendarURL_TEXT = null, @Ai_RowsAffected_NUMB = @Li_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; SELECT @Li_RowsAffected_NUMB AS eff_row , @Lc_Msg_CODE as msg, @Ls_DescriptionError_TEXT as err ;
CALENDAR_RetrieveByID_S1 | DECLARE @Ai_Workspace_ID INT, @As_WorkspaceName_TEXT NVARCHAR(100), @As_CalendarName_TEXT NVARCHAR(100), @As_CalendarDesc_TEXT NVARCHAR(500), @As_CalendarURL_TEXT NVARCHAR(250), @Ac_Security_CODE CHAR(1), @Ab_Internal_INDC BIT, @Ad_StartDate DATE, @Ad_EndDate DATE, @Ab_MeetingInperson_INDC BIT, @Ab_MeetingOnline_INDC BIT, @Ab_MeetingTelephone_INDC BIT, @Ai_AppointmentDuration_NUMB INT, @Ai_TimeBetweenAppointments_NUMB INT, @Ai_AppointmentPerSlot_NUMB INT, @As_Form_TEXT NVARCHAR(MAX), @Ab_ShowOrganizerName_INDC BIT, @Ab_AllowAttendeeChooseOrganizer_INDC BIT, @Ab_AllowInviteGuests_INDC BIT, @Ai_Unit_ID INT, @As_UnitName_TEXT NVARCHAR(100), @Ac_AssignmentMethod_CODE CHAR(1), @Ac_AssignmentCriteria_CODE CHAR(1), @Ac_Status_CODE CHAR(1), @As_StatusDesc_TEXT NVARCHAR(50), @As_SecurityDesc_TEXT NVARCHAR(100), @As_AssignmentMethodDesc_TEXT NVARCHAR(100), @As_AssignmentCriteriaDesc_TEXT NVARCHAR(100), @Ai_CreatedBy_ID INT, @Ad_Created_DTTM DATETIME, @Ai_UpdatedBy_ID INT, @Ad_Updated_DTTM DATETIME, @Ai_TransactionSeqEvent_NUMB BIGINT, @As_Location_TEXT VARCHAR(500), @Ac_Color_CODE CHAR(3), @Ac_ColorDesc_TEXT VARCHAR(100) , @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.CALENDAR_RetrieveByID_S1 @Ai_Calendar_ID = 2, @Ai_Workspace_ID = @Ai_Workspace_ID OUTPUT, @As_WorkspaceName_TEXT = @As_WorkspaceName_TEXT OUTPUT, @As_CalendarName_TEXT = @As_CalendarName_TEXT OUTPUT, @As_CalendarDesc_TEXT = @As_CalendarDesc_TEXT OUTPUT, @As_CalendarURL_TEXT = @As_CalendarURL_TEXT OUTPUT, @Ac_Security_CODE = @Ac_Security_CODE OUTPUT, @Ab_Internal_INDC = @Ab_Internal_INDC OUTPUT, @Ad_StartDate = @Ad_StartDate OUTPUT, @Ad_EndDate = @Ad_EndDate OUTPUT, @Ab_MeetingInperson_INDC = @Ab_MeetingInperson_INDC OUTPUT, @Ab_MeetingOnline_INDC = @Ab_MeetingOnline_INDC OUTPUT, @Ab_MeetingTelephone_INDC = @Ab_MeetingTelephone_INDC OUTPUT, @Ai_AppointmentDuration_NUMB = @Ai_AppointmentDuration_NUMB OUTPUT, @Ai_TimeBetweenAppointments_NUMB = @Ai_TimeBetweenAppointments_NUMB OUTPUT, @Ai_AppointmentPerSlot_NUMB = @Ai_AppointmentPerSlot_NUMB OUTPUT, @As_Form_TEXT = @As_Form_TEXT OUTPUT, @Ab_ShowOrganizerName_INDC = @Ab_ShowOrganizerName_INDC OUTPUT, @Ab_AllowAttendeeChooseOrganizer_INDC = @Ab_AllowAttendeeChooseOrganizer_INDC OUTPUT, @Ab_AllowInviteGuests_INDC = @Ab_AllowInviteGuests_INDC OUTPUT, @Ai_Unit_ID = @Ai_Unit_ID OUTPUT, @As_UnitName_TEXT = @As_UnitName_TEXT OUTPUT, @Ac_AssignmentMethod_CODE = @Ac_AssignmentMethod_CODE OUTPUT, @Ac_AssignmentCriteria_CODE = @Ac_AssignmentCriteria_CODE OUTPUT, @Ac_Status_CODE = @Ac_Status_CODE OUTPUT, @As_StatusDesc_TEXT = @As_StatusDesc_TEXT OUTPUT, @As_SecurityDesc_TEXT = @As_SecurityDesc_TEXT OUTPUT, @As_AssignmentMethodDesc_TEXT = @As_AssignmentMethodDesc_TEXT OUTPUT, @As_AssignmentCriteriaDesc_TEXT = @As_AssignmentCriteriaDesc_TEXT OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @Ad_Created_DTTM = @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @Ad_Updated_DTTM = @Ad_Updated_DTTM OUTPUT, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB OUTPUT, @As_Location_TEXT = @As_Location_TEXT OUTPUT, @Ac_Color_CODE = @Ac_Color_CODE OUTPUT, @Ac_ColorDesc_TEXT = @Ac_ColorDesc_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS msg, @As_DescriptionError_TEXT AS err, @Ai_Workspace_ID AS workspace_id, @As_WorkspaceName_TEXT AS workspace_name, @As_CalendarName_TEXT AS calendar_name, @Ac_Status_CODE AS status_code, @As_StatusDesc_TEXT AS status_desc, @Ai_TransactionSeqEvent_NUMB AS txn_seq, -- Basic Info @As_CalendarDesc_TEXT AS calendar_desc, @As_CalendarURL_TEXT AS calendar_url, @Ac_Security_CODE AS security_code, @Ab_Internal_INDC AS is_internal, @Ad_StartDate AS start_date, @Ad_EndDate AS end_date, -- Meeting Options @Ab_MeetingInperson_INDC AS in_person, @Ab_MeetingOnline_INDC AS online, @Ab_MeetingTelephone_INDC AS telephone, @Ai_AppointmentDuration_NUMB AS appointment_duration, @Ai_TimeBetweenAppointments_NUMB AS time_between_appointments, @Ai_AppointmentPerSlot_NUMB AS appointments_per_slot, @As_Form_TEXT AS form_text, -- Attendee & Organizer Settings @Ab_ShowOrganizerName_INDC AS show_organizer, @Ab_AllowAttendeeChooseOrganizer_INDC AS allow_attendee_choose_organizer, @Ab_AllowInviteGuests_INDC AS allow_invite_guests, -- Assignment & Unit Info @Ai_Unit_ID AS unit_id, @As_UnitName_TEXT AS unit_name, @Ac_AssignmentMethod_CODE AS assignment_method_code, @Ac_AssignmentCriteria_CODE AS assignment_criteria_code, @As_AssignmentMethodDesc_TEXT AS assignment_method_desc, @As_AssignmentCriteriaDesc_TEXT AS assignment_criteria_desc, -- Security & Status Descriptions @As_SecurityDesc_TEXT AS security_desc, @Ac_Status_CODE AS status_code_repeat, @As_StatusDesc_TEXT AS status_desc_repeat, -- Audit @Ai_CreatedBy_ID AS created_by, @Ad_Created_DTTM AS created_dttm, @Ai_UpdatedBy_ID AS updated_by, @Ad_Updated_DTTM AS updated_dttm, @Ai_TransactionSeqEvent_NUMB AS transaction_seq, @As_Location_TEXT AS Location_TEXT, @Ac_Color_CODE as color, @Ac_ColorDesc_TEXT as colordesc;
UNIT_InsertWithMembers_S1 | DECLARE @Ai_Unit_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Procedure Execution EXEC dbo.UNIT_InsertWithMembers_S1 @Ai_Workspace_ID = 3, @As_UnitName_TEXT = 'My Unit2', @Ac_Status_CODE = 'A', @Ai_CreatedBy_ID = 1, @Ai_TransactionSeqEvent_NUMB = 0, @As_Members_JSON = ' [ { "User_ID": 1, "Start_DATE": "2025-05-01", "End_DATE": null, "Permissions": [ { "PermissionCat_CODE": "A", "CanView_INDC": 1, "CanEdit_INDC": 1 }, { "PermissionCat_CODE": "C", "CanView_INDC": 1, "CanEdit_INDC": 0 } ] }, { "User_ID": 2, "Start_DATE": "2025-05-01", "End_DATE": "2025-12-31", "Permissions": [ { "PermissionCat_CODE": "A", "CanView_INDC": 1, "CanEdit_INDC": 0 } ] } ] ', @As_MemberPerms_JSON = null, @Ai_Unit_ID = @Ai_Unit_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output results SELECT @Ai_Unit_ID AS Unit_ID, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
UNIT_UpdateWithMembers_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.UNIT_UpdateWithMembers_S1 @Ai_Unit_ID = 11, @Ai_Workspace_ID = 3, @As_UnitName_TEXT = N'Technical Team', @Ac_Status_CODE = 'A', @Ai_UpdatedBy_ID = 1, @An_OldTransactionSeqEvent_NUMB = 853, @An_NewTransactionSeqEvent_NUMB = 0, @As_Members_JSON = '[ { "User_ID": 1, "Start_DATE": "2025-05-01", "End_DATE": null, "Permissions": [ { "PermissionCat_CODE": "C", "CanView_INDC": 1, "CanEdit_INDC": 0 } ] }, { "User_ID": 2, "Start_DATE": "2025-05-01", "End_DATE": "2025-12-31", "Permissions": [ { "PermissionCat_CODE": "A", "CanView_INDC": 1, "CanEdit_INDC": 0 }, { "PermissionCat_CODE": "C", "CanView_INDC": 1, "CanEdit_INDC": 0 } ] } ]', @As_MemberPerms_JSON = NULL, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorText;
UNIT_UpdateStatus_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.UNIT_UpdateStatus_S1 @Ai_Unit_ID = 8, -- Replace with actual Unit ID to update @Ac_Status_CODE = 'I', -- Replace with new status code (e.g., 'A', 'I', etc.) @Ai_UpdatedBy_ID = 2, -- Replace with the user ID performing the update @An_OldTransactionSeqEvent_NUMB = 366, -- Replace with appropriate transaction sequence number @An_NewTransactionSeqEvent_NUMB = 0, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the output parameters to confirm success or understand errors SELECT MsgCode = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
CALENDAR_RetrieveAll_S1 | DECLARE @Lc_Msg_CODE CHAR(1), @Ls_DescriptionError_TEXT NVARCHAR(500); EXEC dbo.CALENDAR_RetrieveAll_S1 @Ai_Workspace_ID = 3, @As_Workspaces_TEXT = NULL, @As_Units_TEXT = NULL, @As_CalendarName_TEXT = NULL, @As_Status_CODE = NULL, @As_MeetingType_CODE = NULL, @As_UnitMembers_TEXT = '1,2', @As_Security_CODE = NULL, @Ai_SignedOnUser_ID = NULL, @Ai_From_NUMB = 1, @Ai_To_NUMB = 100, @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; SELECT @Lc_Msg_CODE AS msg, @Ls_DescriptionError_TEXT AS err;
Calendar$Sp_Delete_Calendar | DECLARE @Li_RowsAffected_NUMB INT, @Lc_Msg_CODE CHAR(1), @Ls_DescriptionError_TEXT NVARCHAR(500); EXEC Calendar$Sp_Delete_Calendar @Ai_Calendar_ID = 4, -- Replace with actual Calendar ID @Ai_UpdatedBy_ID = 3, -- Replace with actual User ID performing the delete @An_OldTransactionSeqEvent_NUMB = 202505140001, -- Replace with old transaction sequence @An_NewTransactionSeqEvent_NUMB = 2, -- Replace with new transaction sequence @Ai_RowsAffected_NUMB = @Li_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; SELECT @Li_RowsAffected_NUMB AS eff_row, @Lc_Msg_CODE AS msg, @Ls_DescriptionError_TEXT AS err;
Calendar$SpUpdateCalendarAvailability | DECLARE @Lc_Msg_CODE CHAR(5), @Ls_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Calendar$SpUpdateCalendarAvailability @Ai_Calendar_ID = 22, -- Replace with actual calendar ID @Ad_From_DATE = '2025-08-01', -- Starting date for availability range @Ad_To_DATE = '2025-08-31', -- Ending date for availability range @Ai_TimeZone_ID = NULL, -- Replace with actual timezone ID @As_WorkingHours_TEXT = '[ { "Type_CODE": "W", "DayOfWeek_CODE": "MON", "Available_INDC": 1, "Timings": [ {"StartDate_DTTM": "2025-07-23T15:00:00", "EndDate_DTTM": "2025-07-23T23:00:00","Memberjson" : [1,2]}, {"StartDate_DTTM": "2025-07-23T08:00:00", "EndDate_DTTM": "2025-07-23T10:00:00","Memberjson" : [1,2]} ] }, { "Type_CODE": "O", "OverrideDate_DATE": "2025-05-22", "Available_INDC": 0, "Timings": [{"StartTime": "2025-07-18T09:00:00", "EndTime": "2025-07-18T17:00:00","Memberjson" : [1,2]}] } ]', -- Replace with actual JSON string (keep well-formed) @Ai_UserWorkspace_ID = NULL, -- Optional; specify if applicable @Ai_UpdatedBy_ID = 2, -- ID of the user updating the calendar @Ai_OldTransactionEventSeq_NUMB = 1153, -- Last known transaction seq (for concurrency) @Ai_NewTransactionEventSeq_NUMB = 0, -- New transaction seq @Ai_SignedOnUser_ID = 2, -- Signed-in user (typically same as UpdatedBy_ID) @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; -- Output response SELECT @Lc_Msg_CODE AS msg, @Ls_DescriptionError_TEXT AS err; --SELECT * FROM Calendar
Calendar$SpGetCalendarAvailability | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$SpGetCalendarAvailability @Ai_Calendar_ID = 1, -- Example Calendar ID @Ai_SignedOnUser_ID = 2, -- Example signed-on user ID @Ad_From_DATE = '2025-05-20', -- Example from date @Ad_To_DATE = '2025-05-26', -- Example to date @Ai_TimeZone_ID = NULL, -- Or specific time zone ID @Ai_UnitMember_ID = 2, -- Default (0 = all members or self) @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optionally view the output SELECT Msg_CODE = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
USER_CreateDefaultWorkingHours_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.USER_CreateDefaultWorkingHours_S1 @Ai_User_ID = 2, @Ai_TransactionSeqEvent_NUMB = 1, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optionally view the output SELECT Msg_CODE = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
UNIT_RetrieveByID_S1 | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.UNIT_RetrieveByID_S1 @Ai_Unit_ID = 3, -- Replace with actual Unit ID to update @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the output parameters to confirm success or understand errors SELECT MsgCode = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
MeetingRooms$Sp_Add_MeetingRoom | DECLARE @Ai_NewMeetingRoom_ID INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @Tvp_Users VARCHAR(MAX); -- Sample JSON with Admin and Guests SET @Tvp_Users = ' [ { "User_ID":1, "Role_CODE": "A" }, { "User_ID": 2, "Role_CODE": "G" }, { "User_ID": 4, "Role_CODE": "G" } ]'; EXEC dbo.MeetingRooms$Sp_Add_MeetingRoom @As_MeetingRoomName_TEXT = N'Product Strategy Room', @As_Description_TEXT = N'Room used for product roadmap discussions', @Ai_Workspace_ID = 3, @Ac_Security_CODE = 'O', -- P = Private, for example @As_MeetingUrl_TEXT ='GFFHGHSFHJ.COM', @As_Session_TEXT ='gfdgvhb', @As_MeetingLogoUrl_TEXT =null, @Tvp_Users = @Tvp_Users, @Ai_NewMeetingRoom_ID = @Ai_NewMeetingRoom_ID OUTPUT, @Ai_TransactionSeqEvent_NUMB = 10, @Ai_CreatedBy_ID = 2, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output Results SELECT NewMeetingRoom_ID = @Ai_NewMeetingRoom_ID, Status_Code = @Ac_Msg_CODE, Error_Description = @As_DescriptionError_TEXT;
MeetingRooms$Sp_Update_MeetingRoom | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @As_Tvp_Users VARCHAR(MAX); -- Sample JSON input for users (Admin and Guests) SET @As_Tvp_Users = ' [ { "User_ID": 1, "Role_CODE": "A" }, { "User_ID": 2, "Role_CODE": "G" }, { "User_ID": 4, "Role_CODE": "G" } ]'; -- Execute the procedure EXEC dbo.MeetingRooms$Sp_Update_MeetingRoom @Ai_MeetingRoom_ID = 13, -- Replace with actual MeetingRoom_ID to update @As_MeetingRoomName_TEXT = N'Tech Leadership Room', @As_Description_TEXT = N'Discussions for tech strategy and leadership sessions', @Ai_Workspace_ID = 3, @Ac_Security_CODE = 'O', @As_MeetingUrl_TEXT = 'https://meet.example.com/techlead', @As_Session_TEXT = 'spnjfhs', @As_MeetingLogoUrl_TEXT = 'https://cdn.example.com/logos/techroom.png', @Tvp_Users = @As_Tvp_Users, @Ai_UpdatedBy_ID = 2, @Ai_TransactionSeqEvent_NUMB = 3, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output Result SELECT Status_Code = @Ac_Msg_CODE, Error_Description = @As_DescriptionError_TEXT;
MeetingRooms$Sp_Get_MeetingRoomInfo | DECLARE @As_MeetingRoomName_TEXT NVARCHAR(100), @As_Description_TEXT NVARCHAR(500), @Ai_Workspace_ID INT, @Ac_Security_CODE CHAR(1), @As_SecurityDesc_TEXT NVARCHAR(100), @As_MeetingUrl_TEXT VARCHAR(250), @As_Session_TEXT VARCHAR(10), @As_MeetingLogoUrl_TEXT VARCHAR(400), @Ai_CreatedBy_ID INT, @As_CreatedByName NVARCHAR(100), @Ad_Created_DTTM DATETIME, @Ai_UpdatedBy_ID INT, @As_UpdatedByName NVARCHAR(100), @Ad_Updated_DTTM DATETIME, @Ai_TransactionSeqEvent_NUMB BIGINT, @As_MeetingRoomUsers_JSON NVARCHAR(MAX), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.MeetingRooms$Sp_Get_MeetingRoomInfo @Ai_MeetingRoom_ID = 13, -- Sample ID @As_MeetingRoomName_TEXT = @As_MeetingRoomName_TEXT OUTPUT, @As_Description_TEXT = @As_Description_TEXT OUTPUT, @Ai_Workspace_ID = @Ai_Workspace_ID OUTPUT, @Ac_Security_CODE = @Ac_Security_CODE OUTPUT, @As_SecurityDesc_TEXT = @As_SecurityDesc_TEXT OUTPUT, @As_MeetingUrl_TEXT = @As_MeetingUrl_TEXT OUTPUT, @As_Session_TEXT = @As_Session_TEXT OUTPUT, @As_MeetingLogoUrl_TEXT = @As_MeetingLogoUrl_TEXT OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @As_CreatedByName = @As_CreatedByName OUTPUT, @Ad_Created_DTTM = @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @As_UpdatedByName = @As_UpdatedByName OUTPUT, @Ad_Updated_DTTM = @Ad_Updated_DTTM OUTPUT, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB OUTPUT, @As_MeetingRoomUsers_JSON = @As_MeetingRoomUsers_JSON OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @As_MeetingRoomName_TEXT AS meetingroom_name, @As_Description_TEXT AS description, @Ai_Workspace_ID AS workspace_id, @Ac_Security_CODE AS security_code, @As_SecurityDesc_TEXT AS security_description, @Ai_CreatedBy_ID AS created_by_id, @As_CreatedByName AS created_by_name, @Ad_Created_DTTM AS created_datetime, @Ai_UpdatedBy_ID AS updated_by_id, @As_UpdatedByName AS updated_by_name, @Ad_Updated_DTTM AS updated_datetime, @Ai_TransactionSeqEvent_NUMB AS txn_seq_event, @As_MeetingRoomUsers_JSON AS meetingroom_users_json, @As_MeetingUrl_TEXT AS url_text, @As_Session_TEXT AS session_text, @As_MeetingLogoUrl_TEXT AS logourl, @Ac_Msg_CODE AS msg, @As_DescriptionError_TEXT AS err;
MeetingRooms$Sp_Get_MeetingRooms | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.MeetingRooms$Sp_Get_MeetingRooms @Ai_Workspace_ID = 3, -- Sample workspace ID @Ac_Security_CODE = 'O', -- 'O' for Open, 'L' for Locked @As_Search_TEXT = null, -- Sample search keyword @Ai_RowFrom = 1, @Ai_RowTo = 10, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS msg, @As_DescriptionError_TEXT AS err;
MeetingRooms$Sp_Delete_MeetingRoom | DECLARE @Lc_Msg_CODE CHAR(1), @Ls_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.MeetingRooms$Sp_Delete_MeetingRoom @Ai_MeetingRoom_ID = 4, @Ai_DeletedBy_ID = 2, @Ai_TransactionSeqEvent_NUMB = 2, @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; SELECT @Lc_Msg_CODE AS msg, @Ls_DescriptionError_TEXT AS err;
Calendar$SpDeleteAppointment | DECLARE @Li_RowsAffected_NUMB INT, @Lc_Msg_CODE CHAR(5), @Ls_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$SpDeleteAppointment @Ai_Appointment_ID = 21, @An_OldTransactionSeqEvent_NUMB = 1, @An_NewTransactionSeqEvent_NUMB = 2, @Ai_UpdatedBy_ID = 2, @Ac_RepeatChangeType_CODE = 'S', -- 'A' = All, 'S' = Single, 'F' = Future @Ad_RepeatChange_DATE = '2025-06-02 11:00:00.000', @Ai_RowsAffected_NUMB = @Li_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; SELECT @Li_RowsAffected_NUMB AS eff_row, @Lc_Msg_CODE AS msg, @Ls_DescriptionError_TEXT AS err;
Calendar$SpGetUserWorkingHours | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); -- ╔═ Execute Procedure ═╗ EXEC dbo.Calendar$SpGetUserWorkingHours @Ai_SignedOnUser_ID = 4, -- Example User ID @Ad_From_DATE = '2025-06-01', -- Start date of working hour range @Ad_To_DATE = '2025-06-07', -- End date of working hour range @Ai_TimeZone_ID = null, -- Optional Time Zone ID (e.g., 5 = EST) @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- ╔═ Output the Result ═╗ SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage; select * from UserAvailability
Calendar$SpAddAppointment | DECLARE @Ai_Appointment_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000), @Ab_SendEmail_INDC BIT, @Ab_SendUserPhone_INDC BIT ; EXEC dbo.Calendar$SpAddAppointment @Ai_Calendar_ID = 1, @As_AppointmentName_TEXT = N'Mock Interview Session', @Ac_AppointmentType_CODE = N'VIRTUAL', @Ai_Job_ID = NULL, @Ad_Start_DTTM = '2025-06-22T10:00:00', @Ad_End_DTTM = '2025-06-22T11:00:00', @Ab_AllDay_INDC = 0, @Ac_MeetingType_CODE = 'O', @As_Location_TEXT = N'Zoom Meeting Room 3A', @As_Notes_TEXT = N'Candidate mock interview for Software Engineer position.', @As_RepeatRule_TEXT = N'FREQ=WEEKLY;BYDAY=MO', @As_Participants_JSON = N'[{"User_ID": 2, "ParticipantType_CODE": "O", "FirstName": "John", "LastName": "Doe", "EmailAddress": "john@example.com"}]', @As_Forms_JSON = N'[{"Form_ID": 2, "Data": "Sample answers"}]', @As_MeetingRooms_JSON = N'[{"RoomName": "Zoom Room", "Description": "Virtual Zoom Room", "RoomSecurity": "O", "SessionCode": "ABC123", "MeetingURL": "https://zoom.us/abc", "MeetingViewURL": "https://zoom.us/view/abc"}]', @As_MeetingTelephones_JSON = N'[{"TelephoneConferenceName": "Dial-In", "PhoneNumber": "+18005551234", "PhoneExtension": "101", "PhonePin": "4567"}]', @As_ExceptionDates_JSON = N'["2025-06-08", "2025-06-15"]', @As_CalendarShareLink_TEXT = 'share-calendar-link', @Ai_TimeZone_ID = 3, @Ai_CreatedBy_ID = 2, @Ai_UpdatedBy_ID = 2, @An_TransactionSeqEvent_NUMB = 1, @Ab_ModifyEvent_INDC = 1, @Ab_InviteOthers_INDC = 1, @Ab_SeeGuest_INDC = 1, @Ab_SendEmail_INDC = @Ab_SendEmail_INDC OUTPUT, @Ab_SendUserPhone_INDC = @Ab_SendUserPhone_INDC OUTPUT, @Ai_Appointment_ID = @Ai_Appointment_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ab_SendEmail_INDC as sendmail, @Ab_SendUserPhone_INDC as sendsms, @Ai_Appointment_ID AS appointment_id, @Ac_Msg_CODE AS msg, @As_DescriptionError_TEXT AS err;
Calendar$SpUpdateAppointment | DECLARE @Li_RowsAffected_NUMB INT, @Li_NewAppointment_ID INT, @Lc_Msg_CODE CHAR(5), @Ls_DescriptionError_TEXT NVARCHAR(4000) , @Ab_SendEmail_INDC BIT , @Ab_SendUserPhone_INDC BIT; EXEC dbo.Calendar$SpUpdateAppointment @Ai_Appointment_ID = 46 ,@An_OldTransactionSeqEvent_NUMB = 1 ,@An_NewTransactionSeqEvent_NUMB = 0 ,@Ai_UpdatedBy_ID = 2 -- Core Fields to Change ,@As_AppointmentName_TEXT = N'Updated Career Counseling Session' ,@Ac_AppointmentType_CODE = 'Virtual' ,@Ai_Job_ID = null ,@Ad_Start_DTTM = '2025-06-01 10:00:00' ,@Ad_End_DTTM = '2025-06-01 11:00:00' ,@Ab_AllDay_INDC = 0 ,@Ac_MeetingType_CODE = 'O' ,@As_Location_TEXT = N'Virtual Zoom Room' ,@As_Notes_TEXT = N'Discuss job placement opportunities.' ,@As_RepeatRule_TEXT = N'FREQ=WEEKLY;COUNT=5' -- JSON Inputs ,@As_Participants_JSON = N'[{"User_ID":4,"ParticipantType_CODE":"G"}]' ,@As_Forms_JSON = N'[{"Form_ID":2,"Data":"{}"}]' ,@As_MeetingRooms_JSON = N'[{"RoomName":"Room A","RoomSecurity":"O"}]' ,@As_MeetingTelephones_JSON = N'[{"TelephoneConferenceName":"TeamLine","PhoneNumber":"555-1234","PhoneExtension":NULL,"PhonePin":"546646"}]' -- Recurrence Info ,@Ac_RepeatChangeType_CODE = 'A' ,@Ad_RepeatChange_DATE = '2025-06-01' ,@As_ExceptionDates_JSON = N'["2025-06-15"]' ,@Ac_Rsvp_CODE = 'A' ,@Ai_TimeZone_ID = 1 , @Ab_ModifyEvent_INDC = 1 , @Ab_InviteOthers_INDC = 0 , @Ab_SeeGuest_INDC = 1 -- Outputs ,@Ab_SendEmail_INDC = @Ab_SendEmail_INDC OUTPUT ,@Ab_SendUserPhone_INDC = @Ab_SendUserPhone_INDC OUTPUT ,@Ai_RowsAffected_NUMB = @Li_RowsAffected_NUMB OUTPUT ,@Ai_NewAppointment_ID = @Li_NewAppointment_ID OUTPUT ,@Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT ,@As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; SELECT @Ab_SendEmail_INDC as mail, @Ab_SendUserPhone_INDC as sms, @Lc_Msg_CODE AS msg, @Ls_DescriptionError_TEXT AS err, @Li_RowsAffected_NUMB AS rows_affected, @Li_NewAppointment_ID AS new_appointment_id; -- select * from Appointments
Calendar$SpShareAppointmentViaEmail | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Calendar$SpShareAppointmentViaEmail @Ai_SignedOnUser_ID = 2, @Ai_Appointment_ID = 43, @As_GuestEmails_TEXT = 'guest1@gmail.com,guest2@gmail.com', @An_TransactionSeqEvent_NUMB = 0, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
Calendar$SpUpdateAppointmentRsvpStatus | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$SpUpdateAppointmentRsvpStatus @Ai_SignedOnUser_ID = 2, @Ai_Appointment_ID = 43, @As_EmailAddress_TEXT = NULL ,--'guest1@gmail.com', @As_RepeatRule_TEXT = null, --'FREQ=WEEKLY;BYDAY=TU;COUNT=5', @Ac_RepeatChangeType_CODE = null ,--'A - ALL , S -single , F- Future', @Ad_RepeatChange_DATE = null , --'2025-06-25', @As_NewRsvpStatus_CODE = 'N', -- e.g., N - NO , M - may be, Y -yes @An_TransactionSeqEvent_NUMB = 0, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError;
Calendar$GetCalendarUnAvailabilitySlots | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Calendar$SPGetCalendarUnAvailabilitySlots @Ai_Calendar_ID = 1, @As_CounselorWorkspace_TEXT = null, -- N'[1, 2]', -- Example: list of User_IDs (or pass NULL for all) @Ad_Start_DTTM = '2025-07-23T09:00:00', @Ad_End_DTTM = '2025-07-23T10:00:00', @As_RepeatRule_TEXT = 'FREQ=DAILY;INTERVAL=1;UNTIL=20250801', @Ai_TimeZone_ID = NULL, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT MsgCode = @Ac_Msg_CODE, ErrorDescription = @As_DescriptionError_TEXT;
Calendar$Sp_Update_Calendar_Status | DECLARE @lc_RowsAffected INT, @lc_Msg CHAR(1), @lc_Error NVARCHAR(500); EXEC dbo.Calendar$Sp_Update_Calendar_Status @Ai_Calendar_ID = 51, -- Example Calendar ID @Ac_Status_CODE = 'I', -- New status (e.g., 'I' for Inactive) @Ai_UpdatedBy_ID = 1, -- User performing the update @An_OldTransactionSeqEvent_NUMB = 1351, -- Old Seq # (must match record’s current seq) @An_NewTransactionSeqEvent_NUMB = 0, -- New Seq # (next transaction ID) @Ai_RowsAffected_NUMB = @lc_RowsAffected OUTPUT, @Ac_Msg_CODE = @lc_Msg OUTPUT, @As_DescriptionError_TEXT = @lc_Error OUTPUT; -- View results SELECT @lc_RowsAffected AS RowsAffected, @lc_Msg AS MsgCode, @lc_Error AS ErrorDescription;
WorkDiary$Sp_Get_Summary | DECLARE @An_TotalHours_NUMB DECIMAL(8,2), @An_BillableHours_NUMB DECIMAL(8,2), @An_AvgDaily_NUMB DECIMAL(8,2), @An_OverTime_NUMB DECIMAL(8,2), @An_ActivityPct_NUMB DECIMAL(5,2), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.WorkDiary$Sp_Get_Summary @Ai_User_ID = 2, -- Replace with actual User_ID @Ai_Contract_ID = 3, -- Replace with actual Contract_ID @As_ViewType_CODE = 'D', -- 'D' = Daily, 'C' = Consolidated, 'W' = Weekly, 'M' = Monthly @Ad_From_DATE = '2025-06-10', -- Start of date range @Ac_Action_CODE = 'W', -- Optional: 'U' or 'E' @Ad_To_DATE = '2025-07-03', -- End of date range @An_TotalHours_NUMB = @An_TotalHours_NUMB OUTPUT, @An_BillableHours_NUMB = @An_BillableHours_NUMB OUTPUT, @An_AvgDaily_NUMB = @An_AvgDaily_NUMB OUTPUT, @An_OverTime_NUMB = @An_OverTime_NUMB OUTPUT, @An_ActivityPct_NUMB = @An_ActivityPct_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError, @An_TotalHours_NUMB AS TotalHours, @An_BillableHours_NUMB AS BillableHours, @An_AvgDaily_NUMB AS AverageDailyHours, @An_OverTime_NUMB AS OvertimeHours, @An_ActivityPct_NUMB AS ActivityPercentage;
WorkDiary$Sp_Get_SummaryMetrics | DECLARE @An_TotalTargetHours_NUMB DECIMAL(9,2), @An_TotalProgressHours_NUMB DECIMAL(9,2), @An_AvgActivityPct_NUMB DECIMAL(5,2), @An_TotalOvertimeHours_NUMB DECIMAL(9,2), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.WorkDiary$Sp_Get_SummaryMetrics @Ai_User_ID = 2, -- Replace with actual User_ID @Ai_Contract_ID = 3, -- Replace with actual Contract_ID @Ac_Action_CODE = 'W', -- Optional: 'T' for Timesheet, 'W' for WorkDiary, or NULL @Ad_From_DATE = '2025-06-10', -- Start date of range @Ad_To_DATE = '2025-07-03', -- End date of range @An_TotalTargetHours_NUMB = @An_TotalTargetHours_NUMB OUTPUT, @An_TotalProgressHours_NUMB = @An_TotalProgressHours_NUMB OUTPUT, @An_AvgActivityPct_NUMB = @An_AvgActivityPct_NUMB OUTPUT, @An_TotalOvertimeHours_NUMB = @An_TotalOvertimeHours_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the results SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError, @An_TotalTargetHours_NUMB AS TotalTargetHours, @An_TotalProgressHours_NUMB AS TotalProgressHours, @An_AvgActivityPct_NUMB AS AvgActivityPercent, @An_TotalOvertimeHours_NUMB AS TotalOvertimeHours;
WorkDiary$Sp_Get_UserContractProjects | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.WorkDiary$Sp_Get_UserContractProjects @Ai_User_ID = 2065, -- Replace with actual User_ID @Ai_Contract_ID = 7, -- Optional: NULL or specific Contract_ID @Ac_Action_CODE = 'W', -- 'T' = Timesheet, 'W' = WorkDiary @Ad_From_DATE = '2025-07-01', -- From date @Ad_To_DATE = '2025-07-08', -- To date @Ai_From_NUMB = 1, -- Pagination start @Ai_To_NUMB = 50, -- Pagination end @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output Message SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
WorkDiary$Sp_GetActivityTimeline | DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.WorkDiary$Sp_GetActivityTimeline @Ai_User_ID = 1, -- Replace with actual user ID @Ad_From_DATE = '2025-06-01', -- Start date of timeline @Ad_To_DATE = '2025-07-03', -- End date of timeline @Ac_Action_CODE = 'A', -- Optional: 'U' or 'E' (or NULL for all) @Ai_From_NUMB = 1, @Ai_To_NUMB = 100, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
WorkDiary$Sp_StopTracking | DECLARE @Ad_End_DTTM DATETIME2, @Ab_Duration_NUMB DECIMAL(5,2), @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.WorkDiary$Sp_StopTracking @Ai_Entry_ID = 8, -- Replace with actual TimesheetEntry ID @Ai_UpdatedBy_ID = 1, -- User stopping the session @An_OldTransactionSeqEvent_NUMB = 860, -- Last known TX event number @An_NewTransactionSeqEvent_NUMB = 1, -- Let SP generate if NULL @Ad_End_DTTM = @Ad_End_DTTM OUTPUT, @Ab_Duration_NUMB = @Ab_Duration_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the outputs SELECT @Ad_End_DTTM AS EndTime, @Ab_Duration_NUMB AS DurationHours, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
WorkDiary$Sp_StartTracking | DECLARE @Ai_Entry_ID INT, @Ad_Start_DTTM DATETIME2, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.WorkDiary$Sp_StartTracking @Ai_User_ID = 2065, -- Replace with actual user ID @Ai_Contract_ID = 7, -- Replace with actual contract ID @As_ProjectName_TEXT = 'Quarterly Report Automation', -- Example project name @As_Description_TEXT = 'Initial setup and data mapping tasks', -- Description @Ai_CreatedBy_ID = 2065, -- Usually same as Ai_User_ID @An_TransactionSeqEvent_NUMB = 1, -- Let SP generate if applicable @Ai_Entry_ID = @Ai_Entry_ID OUTPUT, @Ad_Start_DTTM = @Ad_Start_DTTM OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the results SELECT @Ai_Entry_ID AS EntryID, @Ad_Start_DTTM AS StartTime, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError;
usp_AssessmentSubmission_RetrieveByID_S1 | DECLARE @Case_ID INT = 109, -- Replace with actual Case ID @AssessmentSubmission_ID INT, @SubmittedBy_ID INT, @Submitted_DTTM DATETIME, @CareerGoals_TEXT NVARCHAR(500), @CurrentJobSearch_TEXT NVARCHAR(500), @SpecificCareerGoal_TEXT NVARCHAR(500), @HighestEducation_TEXT NVARCHAR(500), @LicensesCertificates_TEXT NVARCHAR(500), @SkillsToImprove_TEXT NVARCHAR(500), @EmploymentStatus_TEXT NVARCHAR(500), @PastJobs_TEXT NVARCHAR(500), @RecentLayoffs_TEXT NVARCHAR(500), @EmploymentBarriers_TEXT NVARCHAR(500), @HelpNeeded_TEXT NVARCHAR(500), @TrainingInterest_TEXT NVARCHAR(500), @OtherServicesReceive_TEXT NVARCHAR(500), @NeedsAssessmentNotes_TEXT NVARCHAR(1000), @TransactionSeqEvent_NUMB BIGINT, @ProgServ_JSON NVARCHAR(MAX), @Msg_CODE CHAR(1), @DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure EXEC dbo.usp_AssessmentSubmission_RetrieveByID_S1 @Ai_Case_ID = @Case_ID, @Ai_AssessmentSubmission_ID = @AssessmentSubmission_ID OUTPUT, @Ai_SubmittedBy_ID = @SubmittedBy_ID OUTPUT, @Ad_Submitted_DTTM = @Submitted_DTTM OUTPUT, @As_CareerGoals_TEXT = @CareerGoals_TEXT OUTPUT, @As_CurrentJobSearch_TEXT = @CurrentJobSearch_TEXT OUTPUT, @As_SpecificCareerGoal_TEXT = @SpecificCareerGoal_TEXT OUTPUT, @As_HighestEducation_TEXT = @HighestEducation_TEXT OUTPUT, @As_LicensesCertificates_TEXT = @LicensesCertificates_TEXT OUTPUT, @As_SkillsToImprove_TEXT = @SkillsToImprove_TEXT OUTPUT, @As_EmploymentStatus_TEXT = @EmploymentStatus_TEXT OUTPUT, @As_PastJobs_TEXT = @PastJobs_TEXT OUTPUT, @As_RecentLayoffs_TEXT = @RecentLayoffs_TEXT OUTPUT, @As_EmploymentBarriers_TEXT = @EmploymentBarriers_TEXT OUTPUT, @As_HelpNeeded_TEXT = @HelpNeeded_TEXT OUTPUT, @As_TrainingInterest_TEXT = @TrainingInterest_TEXT OUTPUT, @As_OtherServicesReceive_TEXT = @OtherServicesReceive_TEXT OUTPUT, @As_NeedsAssessmentNotes_TEXT = @NeedsAssessmentNotes_TEXT OUTPUT, @At_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB OUTPUT, @As_ProgServ_JSON = @ProgServ_JSON OUTPUT, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- Output result SELECT AssessmentSubmission_ID = @AssessmentSubmission_ID, SubmittedBy_ID = @SubmittedBy_ID, Submitted_DTTM = @Submitted_DTTM, CareerGoals = @CareerGoals_TEXT, CurrentJobSearch = @CurrentJobSearch_TEXT, SpecificCareerGoal = @SpecificCareerGoal_TEXT, HighestEducation = @HighestEducation_TEXT, LicensesCertificates = @LicensesCertificates_TEXT, SkillsToImprove = @SkillsToImprove_TEXT, EmploymentStatus = @EmploymentStatus_TEXT, PastJobs = @PastJobs_TEXT, RecentLayoffs = @RecentLayoffs_TEXT, EmploymentBarriers = @EmploymentBarriers_TEXT, HelpNeeded = @HelpNeeded_TEXT, TrainingInterest = @TrainingInterest_TEXT, OtherServicesReceive = @OtherServicesReceive_TEXT, NeedsAssessmentNotes = @NeedsAssessmentNotes_TEXT, TransactionSeqEvent = @TransactionSeqEvent_NUMB, ProgramServices_JSON = @ProgServ_JSON, Msg_CODE = @Msg_CODE, DescriptionError = @DescriptionError_TEXT;
usp_ApplicantDocument_AddBatch_S1 | DECLARE @Applicant_ID INT = 13; DECLARE @CreatedBy_ID INT = 1; DECLARE @TransactionSeq BIGINT = 1000001; DECLARE @RowsAffected INT; DECLARE @MsgCode CHAR(5); DECLARE @ErrorDesc VARCHAR(4000); --select * from RefDocumentType -- Sample JSON document list with 3 documents DECLARE @DocumentList_JSON NVARCHAR(MAX) = N' [ { "DocumentType_CODE": "AW", "FileName_TEXT": "passport_john_doe.pdf", "FileType_TEXT": "PDF", "FilePath_TEXT": "/docs/1001/passport.pdf", "FileSize_NUMB": "1024000" }, { "DocumentType_CODE": "EC", "FileName_TEXT": "resume_john_doe.docx", "FileType_TEXT": "DOCX", "FilePath_TEXT": "/docs/1001/resume.docx", "FileSize_NUMB": "512000" }, { "DocumentType_CODE": "MR", "FileName_TEXT": "drivers_license.jpg", "FileType_TEXT": "JPG", "FilePath_TEXT": "/docs/1001/license.jpg", "FileSize_NUMB": "786432" } ]'; -- Execute the stored procedure EXEC usp_ApplicantDocument_AddBatch_S1 @Ai_Applicant_ID = @Applicant_ID, @Ai_ParentDocument_ID = NULL, @Ai_Folder_ID = 1, -- Main Documents folder @As_Description_TEXT = 'Initial document upload', @Ai_CreatedBy_ID = @CreatedBy_ID, @An_TransactionSeqEvent_NUMB = @TransactionSeq, @Js_DocumentList_JSON = @DocumentList_JSON, @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; -- Check the results SELECT @RowsAffected AS 'Documents Inserted', @MsgCode AS 'Status', @ErrorDesc AS 'Message';
usp_CaseMinorActivity_Get_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_CaseMinorActivity_Get_S1 @Ai_SignedOnUser_ID = 2099, -- Required @Ai_User_ID = 2110, -- Optional filters @Ai_Case_ID = NULL, @Ac_Status_CODE = NULL, @Ac_MinorActivity_CODE = NULL, @Ac_MajorActivity_CODE = NULL, @Ai_AssignedTo_ID = NULL, @Ac_Reason_CODE = NULL, @Ad_StartDate_DTTM = NULL, @Ad_EndDate_DTTM = NULL, @Ai_CaseMinorActivity_ID = NULL, @Ai_CaseMajorActivity_ID = NULL, @As_Search_TEXT = NULL, @Ac_Type_CODE = NULL, @Ai_From_NUMB = 1, @Ai_To_NUMB = 10, @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check result SELECT @Ac_Msg_Code AS MsgCode, @As_DescriptionError_TEXT AS Description;
Employment$Sp_Update_UserEmployment | DECLARE @MsgCode CHAR(1); DECLARE @Description NVARCHAR(4000); EXEC Employment$Sp_Update_UserEmployment @Ai_UserEmployment_ID = 3, -- The UserEmployment record ID to update @Ai_User_ID = 2170, -- The User ID owner of the employment record @As_JobTitle_TEXT = N'Senior Developer', -- Job title (must not be empty) @As_EmployerName_TEXT = N'Acme Corp', -- Employer name (must not be empty) @An_Salary_NUMB = 85000.00, -- Salary, or NULL if not applicable @Ad_StartDate_DATE = '2020-01-15', -- Start date (must not be NULL) @As_Notes_TEXT = N'Promoted recently', -- Optional notes (can be NULL) @Ai_UpdatedBy_ID = 2099, -- The user who is performing the update (must exist) @An_TransactionSeqEvent_NUMB = NULL, -- Pass NULL to auto-generate transaction sequence @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @Description OUTPUT; -- Check results SELECT @MsgCode AS MsgCode, @Description AS Description;
usp_CasePrimaryNeeds_Get_S1 | DECLARE @MsgCode CHAR(5); DECLARE @ErrorDescription VARCHAR(4000); EXEC dbo.usp_CasePrimaryNeeds_Get_S1 @Ai_Case_ID = 19, -- Replace with actual Case_ID @Ai_SignedonWorker_ID = 2099, -- Replace with actual SignedOnWorker_ID @Ac_Msg_Code = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- If you want to capture the result set returned by the SELECT, just run this as is -- The output parameters will tell you the status -- View output parameters SELECT @MsgCode AS MsgCode, @ErrorDescription AS Description;
usp_ReferralNote_Update_S1 | DECLARE @ReferralNote_ID INT = 10, -- Existing ReferralNote_ID to be updated @NoteText NVARCHAR(1000) = N'This is the updated referral note.', @UpdatedBy_ID INT = 2099, -- Existing valid User_ID @TransactionSeqEvent_NUMB BIGINT = 20250923123456, -- Or NULL if auto-generated elsewhere @RowsAffected INT, @Msg_CODE CHAR(1), @DescriptionError_TEXT NVARCHAR(4000); EXEC [usp_ReferralNote_Update_S1] @Ai_ReferralNote_ID = @ReferralNote_ID, @As_Note_TEXT = @NoteText, @Ai_UpdatedBy_ID = @UpdatedBy_ID, @An_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB, @Ai_RowsAffected = @RowsAffected OUTPUT, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- Optional: View output SELECT @RowsAffected AS RowsAffected, @Msg_CODE AS MsgCode, @DescriptionError_TEXT AS ErrorMessage;
usp_Add_CaseNote_s1 | DECLARE @Ai_CaseNote_ID BIGINT, @Ac_Msg_CODE VARCHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_TransactionSeqEvent_NUMB BIGINT = NULL; EXEC dbo.usp_Add_CaseNote_s1 @Ai_Case_ID = 101, -- Replace with actual Case_ID @Ai_CaseMinorActivity_ID = NULL, -- Or provide a valid ID if applicable @Ac_NoteType_CODE = 'AS', -- Replace with a valid NoteType_CODE from RefCaseNoteType @As_Note_TEXT = N'This is a test case note.', @Ai_CreatedBy_ID = 1, -- Replace with a valid User_ID @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB, -- NULL to auto-generate @At_Attachments = N'[ { "FileName": "test.pdf", "FileType": "application/pdf", "FileSize": 12345, "FilePath": "/uploads/test.pdf", "Checksum": "ABC123XYZ" } ]', -- Optional; set to NULL if no attachments @Ai_CaseNote_ID = @Ai_CaseNote_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check result SELECT Ai_CaseNote_ID = @Ai_CaseNote_ID, Msg_CODE = @Ac_Msg_CODE, DescriptionError_TEXT = @As_DescriptionError_TEXT;
usp_User_ConversationSummary_GetList_S2 | DECLARE @MsgCode CHAR(5); DECLARE @ErrorDescription VARCHAR(4000); EXEC usp_User_ConversationSummary_GetList_S2 @Ai_SignedOnUser_ID = 2066, -- Replace with a valid User_ID @As_Search_TEXT = NULL, -- Or provide a search keyword like 'John' @Ab_UnreadOnly_INDC = 0, -- 1 = Unread only, 0 = All @Ai_From_NUMB = 1, -- Pagination: From record number @Ai_To_NUMB = 10, -- Pagination: To record number @Ac_Msg_CODE = @MsgCode OUTPUT, -- Output: Status Code (e.g., 'S', 'F', 'E0001', etc.) @As_DescriptionError_TEXT = @ErrorDescription OUTPUT; -- Output: Message/Description -- Optionally print or check the output values PRINT 'Status Code: ' + @MsgCode; PRINT 'Message: ' + @ErrorDescription;
usp_Case_ProgramService_Status_Update_S1 | DECLARE @Ac_Msg_Code CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_Case_ProgramService_Status_Update_S1 @Ai_CaseProgram_ID = 18, -- Provide valid CaseProgram_ID or set to 0 @Ac_ProgramStatus_CODE = 'C', -- Example status: 'A', 'C', 'P', etc. from RefCaseProgramStatus @Ai_CaseProgramService_ID = 11, -- Provide valid CaseProgramService_ID or set to 0 @Ac_ServiceStatus_CODE = 'C', -- Example service status code @Ai_UpdatedBy_ID = 2099, -- Valid user ID @Ai_TransactionSeqEvent_NUMB = 123456, -- Valid transaction number @Ac_Msg_Code = @Ac_Msg_Code OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT MsgCode = @Ac_Msg_Code, Description = @As_DescriptionError_TEXT;
usp_ReferralNote_Delete_S1 | DECLARE @Ai_RowsAffected INT, @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_ReferralNote_Delete_S1 @Ai_ReferralNote_ID = 101, -- Replace with actual ReferralNote_ID @Ai_DeletedBy_ID = 2099, -- Replace with the ID of the user performing the delete @An_TransactionSeqEvent_NUMB = 12345, -- Replace with valid transaction sequence number @Ai_RowsAffected = @Ai_RowsAffected OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Output the result SELECT RowsAffected = @Ai_RowsAffected, MsgCode = @Ac_Msg_CODE, Description = @As_DescriptionError_TEXT;
usp_Update_CaseNote_s1 | DECLARE @Ai_CaseNote_ID BIGINT = 13, -- Existing CaseNote ID to update @Ai_Case_ID INT = 98, -- Valid Case ID @Ai_CaseMinorActivity_ID INT = NULL, -- Optional @Ac_NoteType_CODE CHAR(5) = 'AS', -- Valid Note Type Code @As_NotesName_TEXT VARCHAR(255) = 'Updated Contact Note', @As_Note_TEXT NVARCHAR(2000) = N'This is an updated case note.', @Ai_UpdatedBy_ID INT = 2, -- Valid User ID @Ai_TransactionSeqEvent_NUMB BIGINT = 0, -- Valid Transaction Sequence Number @At_Attachments NVARCHAR(MAX) = null, @Ac_Msg_CODE VARCHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_Update_CaseNote_s1 @Ai_CaseNote_ID, @Ai_Case_ID, @Ai_CaseMinorActivity_ID, @Ac_NoteType_CODE, @As_NotesName_TEXT, @As_Note_TEXT, @Ai_UpdatedBy_ID, @Ai_TransactionSeqEvent_NUMB, @At_Attachments, @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT OUTPUT; -- View the result SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS MsgText;
usp_CaseMinorActivity_Insert_S1 | DECLARE @CaseMinorActivity_ID INT; DECLARE @Msg_Code CHAR(5); DECLARE @DescriptionError_TEXT VARCHAR(4000); DECLARE @TransactionSeqEvent_NUMB BIGINT = NULL; EXEC dbo.usp_CaseMinorActivity_Insert_S1 @Ai_Case_ID = 101, -- Replace with valid Case_ID @Ac_MajorActivity_CODE = null, @Ac_MinorActivity_CODE = 'OTH ', -- Replace with valid MinorActivity_CODE @Ac_Status_CODE = null, @As_Notes_TEXT = N'Initial planning activity note', @Ai_AssignedTo_ID = NULL, @Ad_DueDate_DTTM = NULL, @Ad_Started_DTTM = '2025-10-08 10:00:00', -- Replace with your actual date @Ad_Completed_DTTM = NULL, @Ac_NextMinorActivity_CODE = NULL, @Ac_Reason_CODE = NULL, @Ai_Priority_NUMB = 1, @Ai_EscalationLevel_NUMB = 0, @Ad_LastNotification_DTTM = NULL, @Ai_CaseAction_ID = NULL, @Ac_Action_CODE = NULL, @Ad_Action_DTTM = NULL, @Ai_CreatedBy_ID = 2099, -- Replace with valid User_ID @Ai_TransactionSeqEvent_NUMB = null, @Ai_CaseMinorActivity_ID = @CaseMinorActivity_ID OUTPUT, @Ac_Msg_Code = @Msg_Code OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- View outputs SELECT @Msg_Code AS Msg_Code, @DescriptionError_TEXT AS Description, @CaseMinorActivity_ID AS CaseMinorActivity_ID
usp_UserFollowUp_GetCompleted_S1 | DECLARE @MsgCode CHAR(5), @MsgText VARCHAR(4000); EXEC dbo.usp_UserFollowUp_GetCompleted_S1 @Ai_FollowUp_ID = 101, @Ac_Msg_Code = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @MsgText OUTPUT; SELECT @MsgCode AS MsgCode, @MsgText AS Message;
usp_ApplicantDocument_AddBatch_S1 | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT = 0, -- 0 to auto-generate @Ai_Applicant_ID INT = 303, @Ai_ParentDocument_ID INT = NULL, -- NULL if no parent document @Ai_Folder_ID INT = NULL, -- NULL to auto-check/create folder @Ai_CreatedBy_ID INT = 1, -- Replace with valid user ID @As_Description_TEXT NVARCHAR(250) = 'Initial upload', @Js_DocumentList_JSON NVARCHAR(MAX); -- Sample JSON input with 2 documents SET @Js_DocumentList_JSON = '[ { "DocumentType_CODE": "AT", "FileName_TEXT": "Resume.pdf", "FileType_TEXT": "PDF", "FilePath_TEXT": "/uploads/resume.pdf", "FileSize_NUMB": 500000 }, { "DocumentType_CODE": "AW", "FileName_TEXT": "Passport.jpg", "FileType_TEXT": "JPG", "FilePath_TEXT": "/uploads/passport.jpg", "FileSize_NUMB": 200000, "VersionNumber_NUMB": 1.0 } ]'; -- Execute procedure EXEC dbo.usp_ApplicantDocument_AddBatch_S1 @Ai_Applicant_ID = @Ai_Applicant_ID, @Ai_ParentDocument_ID = @Ai_ParentDocument_ID, @Ai_Folder_ID = @Ai_Folder_ID, @As_Description_TEXT = @As_Description_TEXT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB , @Js_DocumentList_JSON = @Js_DocumentList_JSON, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check results SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @An_TransactionSeqEvent_NUMB AS TransactionSeqEvent;
usp_ApplicantFolder_GetManage_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_RowFrom_NUMB INT = 1, -- Start row @Ai_RowTo_NUMB INT = 11, -- End row @Ai_Applicant_ID INT = 1; -- Replace with your applicant ID -- Execute the procedure EXEC dbo.usp_ApplicantFolder_GetManage_S1 @Ai_Applicant_ID = @Ai_Applicant_ID, @Ai_RowFrom_NUMB = @Ai_RowFrom_NUMB, @Ai_RowTo_NUMB = @Ai_RowTo_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Applicant_Get_With_Documents_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_RowFrom_NUMB INT = 0, -- 0 means default start row @Ai_RowTo_NUMB INT = 0, -- 0 means default end row @Ai_SignedOnWorker_ID INT = 1, -- Replace with your worker ID @As_SearchName_TEXT NVARCHAR(200) = NULL; -- Replace with search text if needed -- Example 1: No search text, default pagination EXEC dbo.Applicant_Get_With_Documents_S1 @Ai_SignedOnWorker_ID = @Ai_SignedOnWorker_ID, @As_SearchName_TEXT = @As_SearchName_TEXT, @Ai_RowFrom_NUMB = @Ai_RowFrom_NUMB, @Ai_RowTo_NUMB = @Ai_RowTo_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_GetLatestVersions_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_RowFrom_NUMB INT = 1, @Ai_RowTo_NUMB INT = 50; -- ================================ -- Example 1: Only Applicant_ID, no folder, no search, all document types -- ================================ EXEC dbo.usp_ApplicantDocument_GetLatestVersions_S1 @Ai_Applicant_ID = 1, @Ai_Folder_ID = NULL, @As_SearchName_TEXT = NULL, @Ac_DocumentType_CODE = NULL, @Ai_RowFrom_NUMB = @Ai_RowFrom_NUMB, @Ai_RowTo_NUMB = @Ai_RowTo_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_UpdateMetadata_S1 | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantDocument_UpdateMetadata_S1 @Ai_ApplicantDocument_ID = 326, -- Replace with actual Document ID @As_FileName_TEXT = N'UpdatedDocumentName.pdf', -- New file name @Ac_DocumentType_CODE = 'AW', -- Replace with actual document type code @Ai_UpdatedBy_ID = 1, -- User ID performing the update @An_OldTransactionSeqEvent_NUMB = 1945, -- Existing transaction sequence number @An_TransactionSeqEvent_NUMB = 0, -- 0 to auto-generate new transaction sequence @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Optionally, view output results SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_GetDeleteDescription_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantDocument_GetDeleteDescription_S1 @Ai_ApplicantDocument_ID = 326, -- Replace with actual Document ID @Ai_Applicant_ID = 303, -- Replace with actual Applicant ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT= @As_DescriptionError_TEXT OUTPUT; -- Check the output SELECT @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_Delete_S1 | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantDocument_Delete_S1 @Ai_ApplicantDocument_ID = 327, -- Replace with actual Document ID @Ai_Applicant_ID = 303, -- Replace with actual Applicant ID @Ai_DeletedBy_ID = 1, -- User performing the deletion @An_TransactionSeqEvent_NUMB = 1945, -- Existing transaction sequence number @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ai_RowsAffected_NUMB AS RowsDeleted, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_UpdateVerificationStatus_S1 | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantDocument_UpdateVerificationStatus_S1 @Ai_ApplicantDocument_ID = 326, -- Replace with actual Document ID @Ac_VerificationStatus_CODE = 'V', -- 'V', 'N', 'R', etc. @An_OldTransactionSeqEvent_NUMB = 1947, -- Previous transaction sequence number @As_VerificationComment_TEXT = N'Verified by reviewer', -- Optional comment @Ai_UpdatedBy_ID = 1, -- User performing update @An_TransactionSeqEvent_NUMB = 0, -- 0 to auto-generate new transaction sequence @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ai_RowsAffected_NUMB AS RowsUpdated, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_AddNewVersion_S1 | DECLARE @Ai_NewDocument_ID INT, @Ai_NewVersionNumber_NUMB DECIMAL(5,2), @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantDocument_AddNewVersion_S1 @Ai_ApplicantDocument_ID = 326, -- Existing Document ID @As_FileName_TEXT = N'NewVersion.pdf', -- New file name @As_FileType_TEXT = 'PDF', -- File type (PDF, DOC, DOCX, JPG, PNG) @As_FilePath_TEXT = N'/docs/NewVersion.pdf', -- File path or URL @Ai_FileSize_NUMB = 1048576, -- File size in bytes (example: 1 MB) @As_VersionNotes_TEXT = N'Updated version with corrections', -- Optional notes @Ai_UpdatedBy_ID = 1, -- User uploading the version @An_TransactionSeqEvent_NUMB = 0, -- 0 to auto-generate transaction sequence @Ai_NewDocument_ID = @Ai_NewDocument_ID OUTPUT, @Ai_NewVersionNumber_NUMB = @Ai_NewVersionNumber_NUMB OUTPUT, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ai_NewDocument_ID AS NewDocumentID, @Ai_NewVersionNumber_NUMB AS NewVersionNumber, @Ai_RowsAffected_NUMB AS RowsInserted, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_GetVersionHistoryByDocument_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Example: Get version history for Document ID 123, rows 1 to 10 EXEC usp_ApplicantDocument_GetVersionHistoryByDocument_S1 @Ai_ApplicantDocument_ID = 326, -- Replace with actual Document ID @Ai_RowFrom_NUMB = 1, -- Pagination start row @Ai_RowTo_NUMB = 10, -- Pagination end row @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output messages SELECT @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_GetDeleteDescription_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantDocument_GetDeleteDescription_S1 @Ai_ApplicantDocument_ID = 326, -- Replace with actual Document ID @Ai_Applicant_ID = 303, -- Replace with actual Applicant ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT= @As_DescriptionError_TEXT OUTPUT; -- Check the output SELECT @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_Delete_S1 | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC usp_ApplicantDocument_Delete_S1 @Ai_ApplicantDocument_ID = 327, -- Replace with actual Document ID @Ai_Applicant_ID = 303, -- Replace with actual Applicant ID @Ai_DeletedBy_ID = 1, -- User performing the deletion @An_TransactionSeqEvent_NUMB = 1945, -- Existing transaction sequence number @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the results SELECT @Ai_RowsAffected_NUMB AS RowsDeleted, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantFolder_GetManage_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_RowFrom_NUMB INT = 1, -- Start row @Ai_RowTo_NUMB INT = 11, -- End row @Ai_Applicant_ID INT = 1; -- Replace with your applicant ID -- Execute the procedure EXEC dbo.usp_ApplicantFolder_GetManage_S1 @Ai_Applicant_ID = @Ai_Applicant_ID, @Ai_RowFrom_NUMB = @Ai_RowFrom_NUMB, @Ai_RowTo_NUMB = @Ai_RowTo_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantDocument_MoveFolder_S1 | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the procedure for a specific document and folder EXEC dbo.usp_ApplicantDocument_MoveFolder_S1 @Ai_ApplicantDocument_ID = 326, -- Replace with actual Document ID @Ai_NewFolder_ID = 117, -- Replace with the target Folder ID @Ai_UpdatedBy_ID = 1, -- Replace with the User ID performing the move @An_OldTransactionSeqEvent_NUMB = 1956, -- Replace with the old transaction sequence @An_TransactionSeqEvent_NUMB = 0, -- Use 0 to auto-generate a new transaction sequence @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check the outputs SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantFolder_GetFolderList_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_RowFrom_NUMB INT = 1, -- Start row @Ai_RowTo_NUMB INT = 11, -- End row @Ai_Applicant_ID INT = 303; -- Replace with your applicant ID -- Execute the procedure EXEC dbo.usp_ApplicantFolder_GetFolderList_S1 @Ai_Applicant_ID = @Ai_Applicant_ID, @Ai_RowFrom_NUMB = @Ai_RowFrom_NUMB, @Ai_RowTo_NUMB = @Ai_RowTo_NUMB, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_ApplicantFolder_Add_S1 | DECLARE @Ai_Folder_ID INT, @An_TransactionSeqEvent_NUMB BIGINT = 0, -- Pass 0 to auto-generate new transaction number @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the stored procedure EXEC dbo.usp_ApplicantFolder_Add_S1 @Ai_Applicant_ID = 303, -- Replace with valid Applicant_ID @Ai_ParentFolder_ID = 117, -- Replace with valid Parent Folder_ID (NULL or 0 for top-level) @As_FolderName_TEXT = N'New Documents', -- Folder name to create @Ai_CreatedBy_ID = 1, -- Replace with valid User_ID @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB , @Ai_Folder_ID = @Ai_Folder_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display results SELECT @Ai_Folder_ID AS NewFolderID, @An_TransactionSeqEvent_NUMB AS TransactionSeqEventNumber, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS DescriptionMessage;
ApplicantFolder$Sp_Get_ApplicantFolder | DECLARE @Ai_Applicant_ID INT, @Ai_ParentFolder_ID INT, @As_FolderName_TEXT NVARCHAR(100), @Ai_CreatedBy_ID INT, @Ai_UpdatedBy_ID INT, @Ad_Created_DTTM DATETIME, @Ad_Updated_DTTM DATETIME, @An_TransactionSeqEvent_NUMB BIGINT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the stored procedure EXEC dbo.ApplicantFolder$Sp_Get_ApplicantFolder @Ai_Folder_ID = 117, -- Replace with valid Folder_ID @Ai_Applicant_ID = @Ai_Applicant_ID OUTPUT, @Ai_ParentFolder_ID = @Ai_ParentFolder_ID OUTPUT, @As_FolderName_TEXT = @As_FolderName_TEXT OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @Ad_Created_DTTM = @Ad_Created_DTTM OUTPUT, @Ad_Updated_DTTM = @Ad_Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display the output values SELECT @Ai_Applicant_ID AS Applicant_ID, @Ai_ParentFolder_ID AS ParentFolder_ID, @As_FolderName_TEXT AS FolderName, @Ai_CreatedBy_ID AS CreatedBy_ID, @Ai_UpdatedBy_ID AS UpdatedBy_ID, CONVERT(VARCHAR(10), @Ad_Created_DTTM, 101) AS CreatedDate, -- MM/DD/YYYY format CONVERT(VARCHAR(10), @Ad_Updated_DTTM, 101) AS UpdatedDate, -- MM/DD/YYYY format @An_TransactionSeqEvent_NUMB AS TransactionSeqEventNumber, @Ac_Msg_CODE AS MessageCode, @As_DescriptionError_TEXT AS DescriptionMessage;
usp_ApplicantFolder_Update_S1 | -- Declare variables for OUTPUT parameters DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT; -- Execute the procedure EXEC usp_ApplicantFolder_Update_S1 @Ai_Folder_ID = 121, -- Existing folder ID @Ai_Applicant_ID = 303, -- Applicant linked to the folder @Ai_ParentFolder_ID = null, -- Parent folder ID (cannot be NULL) @As_FolderName_TEXT = 'Krishnan A Doe (WIOA-2025-000303303)', -- New folder name @Ai_UpdatedBy_ID = 1, -- User performing update @An_OldTransactionSeqEvent_NUMB = 1981, -- Existing transaction number from folder record @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Show results SELECT @Ai_RowsAffected_NUMB AS RowsAffected, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS DescriptionError, @An_TransactionSeqEvent_NUMB AS NewTransactionSeqEvent_NUMB;
ApplicantFolder$Sp_Get_DeleteConfirmation | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC ApplicantFolder$Sp_Get_DeleteConfirmation @Ai_Folder_ID = 118, @Ai_Applicant_ID = 303, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
ApplicantFolder$Sp_Delete_ApplicantFolder | DECLARE @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT; -- Suppose you already have a transaction sequence number, otherwise set 0 SET @An_TransactionSeqEvent_NUMB = 0; EXEC ApplicantFolder$Sp_Delete_ApplicantFolder @Ai_Folder_ID = 123, -- Folder to delete @Ai_Applicant_ID = 303, -- Applicant owning the folder @Ai_DeletedBy_ID = 1, -- User performing deletion @An_TransactionSeqEvent_NUMB = 1, @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check results SELECT @Ai_RowsAffected_NUMB AS RowsDeleted, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
usp_ApplicantFolder_GetTree_S1 | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Example: Get first 10 top-level folders for applicant ID 2001 EXEC usp_ApplicantFolder_GetTree_S1 @Ai_Applicant_ID = 303, @Ai_ParentFolder_ID = null, -- NULL for top-level folders @Ai_RowFrom_NUMB = 1, @Ai_RowTo_NUMB = 10, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output status SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Announcement_RetrieveAll | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC [dbo].[Announcement_RetrieveAll] @As_Search_TEXT = NULL, @Ac_Type_CODE = NULL, @Ac_Status_CODE = NULL, @Ad_From_DATE = '08-01-2025', @Ad_To_DATE = '09-01-2025', @Ai_RowFrom_NUMB = 1, @Ai_RowTo_NUMB = 10, @As_SortColumn_TEXT = NULL, @Ac_SortDirection_CODE = NULL, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Announcement_Add | DECLARE @Ai_Announcement_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC [dbo].[Announcement_Add] @As_Title_TEXT = N'Upcoming Maintenance Notice', -- Announcement title @As_MessageBody_TEXT = N'The system will be under maintenance on Oct 20 from 10 PM to 12 AM.', -- Message body @Ac_AnnouncementType_CODE = 'I', -- Announcement type (e.g., 'G' for General, adjust as per RefAnnouncementType) @Ad_Start_DATE = '2025-10-15', -- Start date @Ad_Expiry_DATE = '2025-10-25', -- Optional expiry date (can be NULL) @Ai_SignedOnUser_ID = 1, -- User ID creating the announcement @Ai_TransactionSeqEvent_NUMB = 0, -- 0 to auto-generate @Ai_Announcement_ID = @Ai_Announcement_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ai_Announcement_ID AS Announcement_ID, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Announcement_Update | DECLARE @RowsAffected_NUMB INT, @Msg_CODE CHAR(5), @DescriptionError_TEXT VARCHAR(4000); EXEC [dbo].[Announcement_Update] @Ai_Announcement_ID = 16, -- 🔹 Existing announcement ID to update @As_Title_TEXT = N'System Maintenance - Updated', @As_MessageBody_TEXT = N'The scheduled maintenance has been rescheduled to Saturday 11 PM.', @Ac_AnnouncementType_CODE = 'W', -- 🔹 Must exist in RefAnnouncementType @Ad_Start_DATE = '2025-10-10', @Ad_Expiry_DATE = '2025-10-15', @Ai_SignedOnUser_ID = 1, -- 🔹 Must exist in Users table @An_OldTransactionSeqEvent_NUMB = 1452, -- 🔹 Current TransactionSeqEvent_NUMB from Announcement table @Ai_TransactionSeqEvent_NUMB = 0, -- Auto-generate new one if 0 @Ai_RowsAffected_NUMB = @RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- View results SELECT @RowsAffected_NUMB AS RowsAffected, @Msg_CODE AS Msg_CODE, @DescriptionError_TEXT AS DescriptionError;
Announcement_Delete | DECLARE @RowsAffected_NUMB INT, @Msg_CODE CHAR(5), @DescriptionError_TEXT VARCHAR(4000); EXEC [dbo].[Announcement_Delete] @Ai_Announcement_ID = 16, -- 🔹 Existing announcement ID to delete @Ai_SignedOnUser_ID = 1, -- 🔹 Must exist in Users table @An_OldTransactionSeqEvent_NUMB = 1997, -- 🔹 Current TransactionSeqEvent_NUMB from Announcement table @Ai_TransactionSeqEvent_NUMB = 0, -- Auto-generate new one if 0 @Ai_RowsAffected_NUMB = @RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- View results SELECT @RowsAffected_NUMB AS RowsAffected, @Msg_CODE AS Msg_CODE, @DescriptionError_TEXT AS DescriptionError;
Announcement_GetDetails | DECLARE @Msg_CODE CHAR(5), @DescriptionError_TEXT VARCHAR(4000); EXEC [dbo].[Announcement_GetDetails] @Ai_Announcement_ID = 18, @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; SELECT @Msg_CODE AS Msg_CODE, @DescriptionError_TEXT AS Description;
Users$Sp_Get_UserList | DECLARE @Msg_CODE CHAR(5), @DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Users$Sp_Get_UserList @As_Search_TEXT = NULL, -- Search by name or email (optional) @As_EmailAddress_TEXT = NULL, -- Filter by specific email (optional) @Ai_Role_ID = NULL, -- Filter by role ID (optional) @Ac_Role_CODE = NULL, -- Filter by role code (optional) @Ac_Status_CODE =NULL, -- Active users only (example) @Ai_Office_ID = NULL, -- Filter by office ID (optional) @As_SortColumn_TEXT = NULL, -- Sort by Full Name @Ab_SortDirection_TEXT = 'ASC', -- Sort direction @Ai_From_NUMB = 1, -- Pagination start row @Ai_To_NUMB = 50, -- Pagination end row @Ai_SignOnUser_ID = 2198, -- Logged-in user ID @Ac_Msg_CODE = @Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- View output message SELECT @Msg_CODE AS Msg_CODE, @DescriptionError_TEXT AS Description;
User$Sp_Create_User | DECLARE @Ai_User_ID INT, @As_Token_TEXT VARCHAR(50), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT = 0; -- optional input, if not already generated EXEC dbo.User$Sp_Create_User @As_FirstName_TEXT = 'Lakshmi', @As_MiddleName_TEXT = 'A', -- optional @As_LastName_TEXT = 'John', @Ad_BirthDate_DATE = '2005-07-16', @As_EmailAddress_TEXT = 'lakshmijohn1@example.com', @As_PhoneNumber_TEXT = '(123) 456-7890', @As_Gender_CODE = NULL, -- optional @Ai_Office_ID = 2, @Ac_Role_CODE = 'CM', @As_EmploymentStatus_CODE = 'EM', @As_AccountStatus_CODE = 'P', -- optional, default 'P'Failed to Add Calendar: Appointment Duration must be 15-180 minutes. @Ab_SendInvite_INDC = 1, -- optional, default 1 @Ab_ForceReset_INDC = 1, -- optional, default 1 @Ai_CreatedBy_ID = 1, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB, @Ai_Override_INDC = 0, -- optional @Ai_User_ID = @Ai_User_ID OUTPUT, @As_Token_TEXT = @As_Token_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check results SELECT @Ai_User_ID AS UserID, @As_Token_TEXT AS InvitationToken, @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS Message;
Users$Sp_Get_UserDetails | DECLARE @As_FirstName_TEXT VARCHAR(50), @As_MiddleName_TEXT VARCHAR(50), @As_LastName_TEXT VARCHAR(50), @Ad_BirthDate_DATE DATE, @As_EmailAddress_TEXT NVARCHAR(255), @As_PhoneNumber_TEXT NVARCHAR(20), @As_ProfileURL_TEXT NVARCHAR(400), @Ai_Role_ID INT, @Ac_Role_CODE CHAR(10), @As_RoleDesc_TEXT NVARCHAR(100), @Ai_Office_ID INT, @As_OfficeName_TEXT NVARCHAR(100), @Ac_County_CODE CHAR(10), @As_CountyName_TEXT NVARCHAR(100), @Ac_OfficeType_CODE CHAR(10), @As_OfficeTypeDesc_TEXT NVARCHAR(100), @An_TransactionSeqEvent_NUMB BIGINT, @Ac_EmploymentStatus_CODE CHAR(2), @As_EmploymentStatusDesc_TEXT NVARCHAR(100), @Ac_AccountStatus_CODE CHAR(1), @As_AccountStatusDesc_TEXT NVARCHAR(50), @Ab_ForceReset_INDC BIT, @Ab_TwoFactorEnabled_INDC BIT, @Ab_IsLocked_INDC BIT, @Ad_LastPasswordChange_DTTM DATETIME2, @Ai_LoginCount_NUMB INT, @Ad_LastLogin_DTTM DATETIME2, @As_PendingEmailInfo_TEXT NVARCHAR(4000), @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- Replace 123 with the User_ID you want to fetch EXEC dbo.Users$Sp_Get_UserDetails @Ai_User_ID = 2266, @As_FirstName_TEXT = @As_FirstName_TEXT OUTPUT, @As_MiddleName_TEXT = @As_MiddleName_TEXT OUTPUT, @As_LastName_TEXT = @As_LastName_TEXT OUTPUT, @Ad_BirthDate_DATE = @Ad_BirthDate_DATE OUTPUT, @As_EmailAddress_TEXT = @As_EmailAddress_TEXT OUTPUT, @As_PhoneNumber_TEXT = @As_PhoneNumber_TEXT OUTPUT, @As_ProfileURL_TEXT = @As_ProfileURL_TEXT OUTPUT, @Ai_Role_ID = @Ai_Role_ID OUTPUT, @Ac_Role_CODE = @Ac_Role_CODE OUTPUT, @As_RoleDesc_TEXT = @As_RoleDesc_TEXT OUTPUT, @Ai_Office_ID = @Ai_Office_ID OUTPUT, @As_OfficeName_TEXT = @As_OfficeName_TEXT OUTPUT, @Ac_County_CODE = @Ac_County_CODE OUTPUT, @As_CountyName_TEXT = @As_CountyName_TEXT OUTPUT, @Ac_OfficeType_CODE = @Ac_OfficeType_CODE OUTPUT, @As_OfficeTypeDesc_TEXT = @As_OfficeTypeDesc_TEXT OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ac_EmploymentStatus_CODE = @Ac_EmploymentStatus_CODE OUTPUT, @As_EmploymentStatusDesc_TEXT = @As_EmploymentStatusDesc_TEXT OUTPUT, @Ac_AccountStatus_CODE = @Ac_AccountStatus_CODE OUTPUT, @As_AccountStatusDesc_TEXT = @As_AccountStatusDesc_TEXT OUTPUT, @Ab_ForceReset_INDC = @Ab_ForceReset_INDC OUTPUT, @Ab_TwoFactorEnabled_INDC = @Ab_TwoFactorEnabled_INDC OUTPUT, @Ab_IsLocked_INDC = @Ab_IsLocked_INDC OUTPUT, @Ad_LastPasswordChange_DTTM = @Ad_LastPasswordChange_DTTM OUTPUT, @Ai_LoginCount_NUMB = @Ai_LoginCount_NUMB OUTPUT, @Ad_LastLogin_DTTM = @Ad_LastLogin_DTTM OUTPUT, @As_PendingEmailInfo_TEXT = @As_PendingEmailInfo_TEXT OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output SELECT @As_FirstName_TEXT AS FirstName, @As_MiddleName_TEXT AS MiddleName, @As_LastName_TEXT AS LastName, @Ad_BirthDate_DATE AS BirthDate, @As_EmailAddress_TEXT AS Email, @As_PhoneNumber_TEXT AS Phone, @As_ProfileURL_TEXT AS ProfileURL, @Ac_Role_CODE AS RoleCode, @As_RoleDesc_TEXT AS RoleDesc, @As_OfficeName_TEXT AS OfficeName, @As_CountyName_TEXT AS County, @As_OfficeTypeDesc_TEXT AS OfficeType, @Ac_AccountStatus_CODE AS AccountStatus, @As_AccountStatusDesc_TEXT AS AccountStatusDesc, @Ab_ForceReset_INDC AS ForceReset, @Ab_TwoFactorEnabled_INDC AS TwoFactorEnabled, @Ab_IsLocked_INDC AS IsLocked, @Ad_LastPasswordChange_DTTM AS LastPasswordChange, @Ai_LoginCount_NUMB AS LoginCount, @Ad_LastLogin_DTTM AS LastLogin, @As_PendingEmailInfo_TEXT AS PendingEmailInfo, @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS Message;
User$Sp_Update_UserProfile | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @An_NewTransactionSeqEvent_NUMB BIGINT; -- 2️⃣ Execute the stored procedure EXEC dbo.User$Sp_Update_UserProfile @Ai_User_ID = 2266, -- Replace with actual User_ID @As_FirstName_TEXT = 'Lakshmi', @As_MiddleName_TEXT = 'A', -- Optional, can be NULL @As_LastName_TEXT = 'John', @Ad_BirthDate_DATE = '2005-05-15', @As_PhoneNumber_TEXT = '(123) 456-7890', @As_Email_TEXT = 'lakshmijohn2@example.com', @Ai_Office_ID = 2, -- Replace with actual Office_ID @Ac_Role_CODE = 'AD', -- Replace with actual Role_CODE @Ac_EmploymentStatus_CODE = 'EM', -- Replace with actual EmploymentStatus_CODE @Ac_AccountStatus_CODE = 'A', -- Replace with actual AccountStatus_CODE @Ab_ForceReset_INDC = 0, -- Optional, can be NULL @Ai_UpdatedBy_ID = 1, -- Replace with the User_ID who updates @An_OldTransactionSeqEvent_NUMB = 2020,-- Replace with actual old transaction sequence @An_NewTransactionSeqEvent_NUMB = @An_NewTransactionSeqEvent_NUMB , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 3️⃣ View the result SELECT @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS Message, @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeqID; select * from users where user_id = 2266
User$Sp_GetEmailChangeAudit | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- 2️⃣ Execute the procedure EXEC dbo.User$Sp_GetEmailChangeAudit @Ai_User_ID = 2266, -- Replace with the actual User_ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 3️⃣ Check the output SELECT @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS Message;
.User$Sp_ApproveEmailChange | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); -- 2️⃣ Execute the procedure EXEC dbo.User$Sp_ApproveEmailChange @Ai_User_ID = 2266, -- Replace with actual User_ID @As_OldEmail_TEXT = 'old@example.com', -- Replace with the old email @As_NewEmail_TEXT = 'new@example.com', -- Replace with the new email @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- 3️⃣ Check the output SELECT @Ac_Msg_CODE AS StatusCode, @As_DescriptionError_TEXT AS Message;
Users$Sp_Update_LockStatus | DECLARE @Li_RowsAffected_NUMB INT, @Lc_Msg_CODE CHAR(5), @Ls_DescriptionError_TEXT VARCHAR(4000), @Ln_NewTransactionSeqEvent_NUMB BIGINT; -- 🔹 Execute the stored procedure EXEC dbo.Users$Sp_Update_LockStatus @Ai_User_ID = 2053, -- ✅ Target user ID to lock/unlock @Ab_Lock_INDC = 0, -- ✅ 1 = Lock, 0 = Unlock @As_Reason_TEXT = N'Locking due to policy violation', -- Optional reason @Ai_UpdatedBy_ID = 1, -- ✅ Admin performing the action @An_OldTransactionSeqEvent_NUMB = 2033,-- ✅ Current transaction sequence number @An_NewTransactionSeqEvent_NUMB = @Ln_NewTransactionSeqEvent_NUMB , -- new txn seq @Ai_RowsAffected_NUMB = @Li_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Lc_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Ls_DescriptionError_TEXT OUTPUT; -- 🔹 Display output values SELECT @Li_RowsAffected_NUMB AS RowsAffected, @Lc_Msg_CODE AS MsgCode, @Ls_DescriptionError_TEXT AS DescriptionError, @Ln_NewTransactionSeqEvent_NUMB AS NewTransactionSeqEvent;
Users$Sp_UpdateAccountStatus | DECLARE @v_RowsAffected_NUMB INT, @v_Msg_CODE CHAR(5), @v_DescriptionError_TEXT VARCHAR(4000), @v_NewTransactionSeqEvent_NUMB BIGINT = NULL; EXEC dbo.Users$Sp_UpdateAccountStatus @Ai_User_ID = 2211, -- 🔹 The user to activate/deactivate @Ac_AccountStatus_CODE = 'A', -- 🔹 'A' = Activate, 'I' = Deactivate @As_Reason_TEXT = null, @Ai_UpdatedBy_ID = 1, -- 🔹 Admin or updater’s user ID @An_OldTransactionSeqEvent_NUMB = 2037, -- 🔹 From current user record @Ai_TransactionSeqEvent_NUMB = @v_NewTransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB = @v_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @v_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @v_DescriptionError_TEXT OUTPUT; -- 🔹 Display results SELECT @v_Msg_CODE AS Msg_CODE, @v_DescriptionError_TEXT AS DescriptionError, @v_RowsAffected_NUMB AS RowsAffected, @v_NewTransactionSeqEvent_NUMB AS NewTransactionSeqEvent;
Users$Sp_UpdateTwoFactorAuth | DECLARE @RowsAffected INT, @MsgCode CHAR(5), @ErrorDesc VARCHAR(4000); EXEC dbo.Users$Sp_UpdateTwoFactorAuth @Ai_User_ID = 2198, -- 🔹 Target user ID @Ab_EnableTwoFactor_INDC = 0, -- 🔹 1 = Enable, 0 = Disable @Ai_UpdatedBy_ID = 1, -- 🔹 Admin or user performing update @An_OldTransactionSeqEvent_NUMB = 1145, -- 🔹 Existing transaction number from Users table @Ai_TransactionSeqEvent_NUMB = 2, -- 🔹 Let procedure auto-generate @Ai_RowsAffected_NUMB = @RowsAffected OUTPUT, @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; SELECT @RowsAffected AS RowsAffected, @MsgCode AS MsgCode, @ErrorDesc AS Description;
Role$Sp_Get_RoleAccessList | DECLARE @Msg CHAR(5), @Desc VARCHAR(4000); EXEC dbo.Role$Sp_Get_RoleAccessList @Ai_SignOnUser_ID = 2198, @Ac_Role_CODE = NULL, -- All roles @Ai_From_NUMB = 1, @Ai_To_NUMB = 50, @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @Desc OUTPUT; SELECT @Msg AS MsgCode, @Desc AS Message;
Role$Sp_Update_MultipleRolePermissions | DECLARE @Msg CHAR(5), @Desc VARCHAR(4000); EXEC dbo.Role$Sp_Update_MultipleRolePermissions @Ac_Role_CODE = 'CM', @As_ScreenList_JSON = '["EVNT","MSG","FORM","DASH","CARE"]', @Ab_EnablePermissions_INDC = 1, @Ai_UpdatedBy_ID = 1, @Ac_Msg_CODE = @Msg OUTPUT, @As_DescriptionError_TEXT = @Desc OUTPUT; SELECT @Msg AS MsgCode, @Desc AS Message;
Office$Sp_Get_OfficeList | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Office$Sp_Get_OfficeList @Ai_SignonUser_ID = 1, -- Example: signed-in user ID @As_OrganizationName_TEXT = NULL, -- Optional filter @As_OfficeName_TEXT = NULL, -- Optional filter @Ac_County_CODE = NULL, -- Optional county filter (e.g., 'C001') @Ac_OfficeType_CODE = NULL, -- Optional office type filter (e.g., 'OT01') @As_SubOrganization_TEXT = NULL, -- Optional filter @As_SearchName_TEXT = NULL, -- Optional keyword search @Ab_IsActive_INDC = 1, -- 1 = Active, 0 = Inactive, NULL = All @Ai_From_NUMB = 1, -- Start row number @Ai_To_NUMB = 50, -- End row number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Office$Sp_Add_Office | DECLARE @Ai_Office_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT = NULL; -- optional, will be auto-generated if NULL EXEC dbo.Office$Sp_Add_Office @As_OrganizationName_TEXT = N'Central Health Organization', -- Organization name (3–100 chars) @As_OfficeName_TEXT = N'North Branch Office', -- Office name (unique per county) @As_OfficeAddress_TEXT = N'123 North Avenue, Springfield', -- Office address (required) @Ac_County_CODE = '001', -- Must exist in RefCounty @Ac_OfficeType_CODE = 'MB', -- Must exist in RefOfficeType @As_SubOrganization_TEXT = N'Health Division', -- Optional @Ab_OverrideDuplicate_INDC = 0, -- 1 = allow duplicate name @Ai_CreatedBy_ID = 1, -- Must exist in Users table @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB , -- Transaction sequence @Ai_Office_ID = @Ai_Office_ID OUTPUT, -- Newly created Office ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, -- Message code @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Description or error -- Display output results SELECT @Ai_Office_ID AS Office_ID, @An_TransactionSeqEvent_NUMB AS TransactionSeqEvent_NUMB, @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS Description;
Office$Sp_Update_Office | DECLARE @Ai_Office_ID INT = 2, -- Replace with target office ID @As_OfficeName_TEXT NVARCHAR(100) = 'Main Office', @As_OfficeAddress_TEXT NVARCHAR(250) = '123 Main Street, Sample City', @Ac_County_CODE CHAR(10) = 'AR', @Ac_OfficeType_CODE CHAR(10) = 'MB', @As_SubOrganization_TEXT NVARCHAR(100) = 'Sub Org', @Ab_OverrideDuplicate_INDC BIT = 0, @Ai_UpdatedBy_ID INT = 1, -- Admin or user performing update @An_OldTransactionSeqEvent_NUMB BIGINT = 2042, -- Replace with last transaction number @An_NewTransactionSeqEvent_NUMB BIGINT = 2042, @Ai_RowsAffected_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000); EXEC dbo.Office$Sp_Update_Office @Ai_Office_ID = @Ai_Office_ID, @As_OfficeName_TEXT = @As_OfficeName_TEXT, @As_OfficeAddress_TEXT = @As_OfficeAddress_TEXT, @Ac_County_CODE = @Ac_County_CODE, @Ac_OfficeType_CODE = @Ac_OfficeType_CODE, @As_SubOrganization_TEXT = @As_SubOrganization_TEXT, @Ab_OverrideDuplicate_INDC = @Ab_OverrideDuplicate_INDC, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID, @An_OldTransactionSeqEvent_NUMB = @An_OldTransactionSeqEvent_NUMB, @An_NewTransactionSeqEvent_NUMB = @An_NewTransactionSeqEvent_NUMB , @Ai_RowsAffected_NUMB = @Ai_RowsAffected_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Check output SELECT @Ai_RowsAffected_NUMB AS RowsUpdated, @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
usp_Insert_Organization_Details_S1 | DECLARE @Ai_Organization_ID INT, @Ai_OrganizationAddress_ID INT, @Ai_OrganizationMember_ID INT, @Ai_User_ID INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT VARCHAR(4000), @Ai_TransactionSeqEvent_NUMB BIGINT = 0; EXEC dbo.usp_Insert_Organization_Details_S1 @As_OrganizationName_TEXT = N'erg Technologies Pvt Ltd', @As_EmailAddress_TEXT = 'erg@abctech.com', @Ac_OrganizationType_CODE = 'AG', -- Must exist in RefOrganizationType @Ac_Status_CODE = 'A', @As_AddressLine1_TEXT = N'123 Tech Park, Phase 1', @As_AddressLine2_TEXT = N'Near Metro Station', @Ai_City_ID = 1, -- Optional (if city already exists) @As_CityName_TEXT = 'Chennai', @Ac_State_CODE = 'TN', @As_PostalCode_TEXT = '600042', @Ac_County_CODE = 'AR', @As_CountyName_TEXT = 'Chennai District', @Ac_Country_CODE = 'IN', @As_UserName_TEXT = NULL, -- Auto-generated inside SP @As_FirstName_TEXT = 'Nivetha', @As_LastName_TEXT = 'Ragupathi', @As_MiddleName_TEXT = NULL, @As_Passwordhash_TEXT = N'hashedpasswordsample', @As_PasswordSalt_TEXT = N'saltsample', @Ai_CreatedBy_ID = 1, @Ai_TransactionSeqEvent_NUMB = @Ai_TransactionSeqEvent_NUMB , @Ai_Organization_ID = @Ai_Organization_ID OUTPUT, @Ai_OrganizationAddress_ID = @Ai_OrganizationAddress_ID OUTPUT, @Ai_OrganizationMember_ID = @Ai_OrganizationMember_ID OUTPUT, @Ai_User_ID = @Ai_User_ID OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- ✅ View Results SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError_TEXT, @Ai_Organization_ID AS Organization_ID, @Ai_OrganizationAddress_ID AS OrganizationAddress_ID, @Ai_OrganizationMember_ID AS OrganizationMember_ID, @Ai_User_ID AS User_ID, @Ai_TransactionSeqEvent_NUMB AS TransactionSeqEvent_NUMB;
Organization$SpGetOrganizationDetails | DECLARE @As_OrganizationName_TEXT NVARCHAR(200), @As_OrganizationDesc_TEXT NVARCHAR(1000), @As_WebsiteUrl_TEXT NVARCHAR(255), @Ac_OrganizationType_CODE CHAR(2), @As_OrganizationTypeDesc_TEXT NVARCHAR(50), @Ac_RecruitmentStatus_CODE CHAR(1), @As_RecruitmentStatusDesc_TEXT NVARCHAR(20), @Ac_Status_CODE CHAR(1), @As_StatusDesc_TEXT NVARCHAR(50), @As_LogoURL_TEXT NVARCHAR(1500), @As_Size_TEXT NVARCHAR(255), @As_EmailAddress_TEXT NVARCHAR(255), @As_PrimaryPhone_TEXT NVARCHAR(50), @Ai_CreatedBy_ID INT, @As_CreatedByName_TEXT NVARCHAR(200), @Ad_Created_DTTM DATETIME, @Ai_UpdatedBy_ID INT, @As_UpdatedByName_TEXT NVARCHAR(200), @Ad_Updated_DTTM DATETIME, @An_TransactionSeqEvent_NUMB BIGINT, @Ai_ActiveContractsCount_NUMB INT, @An_AvgDaysToFillPosition_NUMB INT, @An_OverallRating_NUMB DECIMAL(3, 2), @As_Ratings_TEXT NVARCHAR(50), @An_ReviewCount_NUMB INT, @As_AddressesJSON_TEXT NVARCHAR(MAX), @As_ContactsJSON_TEXT NVARCHAR(MAX), @As_CertificationsJSON_TEXT NVARCHAR(MAX), @As_ProfileCompletionJSON_TEXT NVARCHAR(MAX), @An_JobCount_NUMB INT, @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC dbo.Organization$SpGetOrganizationDetails @Ai_Organization_ID = 40, -- 🔹 Change to the Organization_ID you want to test @As_OrganizationName_TEXT = @As_OrganizationName_TEXT OUTPUT, @As_OrganizationDesc_TEXT = @As_OrganizationDesc_TEXT OUTPUT, @As_WebsiteUrl_TEXT = @As_WebsiteUrl_TEXT OUTPUT, @Ac_OrganizationType_CODE = @Ac_OrganizationType_CODE OUTPUT, @As_OrganizationTypeDesc_TEXT = @As_OrganizationTypeDesc_TEXT OUTPUT, @Ac_RecruitmentStatus_CODE = @Ac_RecruitmentStatus_CODE OUTPUT, @As_RecruitmentStatusDesc_TEXT = @As_RecruitmentStatusDesc_TEXT OUTPUT, @Ac_Status_CODE = @Ac_Status_CODE OUTPUT, @As_StatusDesc_TEXT = @As_StatusDesc_TEXT OUTPUT, @As_LogoURL_TEXT = @As_LogoURL_TEXT OUTPUT, @As_Size_TEXT = @As_Size_TEXT OUTPUT, @As_EmailAddress_TEXT = @As_EmailAddress_TEXT OUTPUT, @As_PrimaryPhone_TEXT = @As_PrimaryPhone_TEXT OUTPUT, @Ai_CreatedBy_ID = @Ai_CreatedBy_ID OUTPUT, @As_CreatedByName_TEXT = @As_CreatedByName_TEXT OUTPUT, @Ad_Created_DTTM = @Ad_Created_DTTM OUTPUT, @Ai_UpdatedBy_ID = @Ai_UpdatedBy_ID OUTPUT, @As_UpdatedByName_TEXT = @As_UpdatedByName_TEXT OUTPUT, @Ad_Updated_DTTM = @Ad_Updated_DTTM OUTPUT, @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB OUTPUT, @Ai_ActiveContractsCount_NUMB = @Ai_ActiveContractsCount_NUMB OUTPUT, @An_AvgDaysToFillPosition_NUMB = @An_AvgDaysToFillPosition_NUMB OUTPUT, @An_OverallRating_NUMB = @An_OverallRating_NUMB OUTPUT, @As_Ratings_TEXT = @As_Ratings_TEXT OUTPUT, @An_ReviewCount_NUMB = @An_ReviewCount_NUMB OUTPUT, @As_AddressesJSON_TEXT = @As_AddressesJSON_TEXT OUTPUT, @As_ContactsJSON_TEXT = @As_ContactsJSON_TEXT OUTPUT, @As_CertificationsJSON_TEXT = @As_CertificationsJSON_TEXT OUTPUT, @As_ProfileCompletionJSON_TEXT = @As_ProfileCompletionJSON_TEXT OUTPUT, @An_JobCount_NUMB = @An_JobCount_NUMB OUTPUT, @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- ✅ View the outputs SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError, @As_OrganizationName_TEXT AS OrganizationName, @As_OrganizationDesc_TEXT AS Description, @As_WebsiteUrl_TEXT AS WebsiteURL, @Ac_OrganizationType_CODE AS OrgTypeCode, @As_OrganizationTypeDesc_TEXT AS OrgTypeDesc, @Ac_Status_CODE AS StatusCode, @As_StatusDesc_TEXT AS StatusDesc, @As_EmailAddress_TEXT AS Email, @As_PrimaryPhone_TEXT AS PrimaryPhone, @As_Size_TEXT AS OrganizationSize, @As_Ratings_TEXT AS Ratings, @An_OverallRating_NUMB AS RatingValue, @An_ReviewCount_NUMB AS ReviewCount, @Ai_ActiveContractsCount_NUMB AS ActiveContracts, @An_JobCount_NUMB AS JobCount, @As_AddressesJSON_TEXT AS AddressesJSON, @As_ContactsJSON_TEXT AS ContactsJSON, @As_CertificationsJSON_TEXT AS CertificationsJSON, @As_ProfileCompletionJSON_TEXT AS ProfileCompletionJSON, @An_TransactionSeqEvent_NUMB as t;
Organization$SpUpdateOrganizationDetails | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000), @An_NewTransactionSeqEvent_NUMB BIGINT; EXEC dbo.Organization$SpUpdateOrganizationDetails1 @Ai_Organization_ID = 41, -- 🔹 Replace with valid Organization_ID @As_OrganizationName_TEXT = N'Protech Solutions', @As_OrganizationDesc_TEXT = N'Research & Development.', @As_WebsiteUrl_TEXT = N'https://www.futuretech.com', @Ac_OrganizationType_CODE = 'AG', -- 🔹 Must exist in RefOrganizationType @As_Size_TEXT = N'100 Employees', @As_EmailAddress_TEXT = N'info@futuretech.com', @As_LogoURL_TEXT = N'https://cdn.futuretech.com/logo.png', @An_OldTransactionSeqEvent_NUMB = 2135, -- 🔹 Replace with latest sequence number from Organization table @An_NewTransactionSeqEvent_NUMB = @An_NewTransactionSeqEvent_NUMB , @Ai_UpdatedBy_ID = 2273, -- 🔹 Must exist in Users table @As_PrimaryPhone_TEXT = N'+1-555-789-1234', -- Certifications JSON @As_CertificationsJSON_TEXT = N'[ { "CertificationTitle_TEXT": "ISO 27001", "CertificationDesc_TEXT": "Information Security Management System", "CertificationYear_NUMB": 2023 }, { "CertificationTitle_TEXT": "AWS Partner Certification", "CertificationDesc_TEXT": "Cloud Partner Certification", "CertificationYear_NUMB": 2024 } ]', -- Addresses JSON @As_AddressesJSON_TEXT = '[{"OrganizationAddress_ID":45, "Address_ID":433, "AddressType_CODE":"H", "AddressLine1_TEXT":"OMR Road", "AddressLine2_TEXT":"Near Ags", "CityName_TEXT":"London", "State_CODE":"TN", "Zip_TEXT":"", "County_CODE":null, "Country_CODE":"IN", "CountyName_TEXT":"niki", "IsPrimary_INDC":true}]', @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeqEvent;
Profile$Sp_GetEmployerDetails | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(200); EXEC dbo.[Profile$Sp_GetEmployerDetails] @Ai_SignedOnUser_ID = 2273, -- Replace with actual signed-on user ID @Ai_Organization_ID = 41, -- Replace with actual organization ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output values SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
Profile$Sp_UpdateEmployerProfile | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(200), @An_NewTransactionSeqEvent_NUMB BIGINT; -- Example execution EXEC dbo.[Profile$Sp_UpdateEmployerProfile] @Ai_SignedOnUser_ID = 2273, -- Replace with actual signed-on user ID @Ai_Organization_ID = 41, -- Replace with actual organization ID @As_FullName_TEXT = 'John Doe', -- Optional @As_CompanyName_TEXT = 'Example Company', -- Optional @Ac_Type_CODE = 'AG', -- Optional organization type code @Ac_AddressType_CODE = 'R', -- Optional address type @As_LocationAddressLine1_TEXT = '123 Garden', -- Optional @As_LocationAddressLine2_TEXT = 'Suite 200', -- Optional @As_AdditionalInfo_TEXT = 'Near Park', -- Optional @Ai_City_ID = 10, -- Optional city ID @Ac_State_CODE = 'CA', -- Optional state code @As_Zip_TEXT = '90001', -- Optional @As_County_CODE = '001', -- Optional @Ac_Country_CODE = 'US', -- Optional @An_OldTransactionSeqEvent_NUMB = 2126, -- Replace with old transaction number @An_NewTransactionSeqEvent_NUMB = @An_NewTransactionSeqEvent_NUMB , -- Will be generated if 0 @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output values SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description, @An_NewTransactionSeqEvent_NUMB AS NewTransactionSeqEvent;
Reports$Sp_Export_MyPerformance_Enrollments | DECLARE @Enroll_Msg_CODE CHAR(5), @Enroll_Desc_TEXT NVARCHAR(4000); EXEC Reports$Sp_Export_MyPerformance_Enrollments @Ac_FilterType_TEXT = 'CT', -- CUSTOM @Ad_Start_DATE = '2025-01-28', @Ad_End_DATE = '2025-07-28', @Ac_Program_CODE = NULL, -- all programs @Ai_SignedOnUser_ID = 42, -- your worker ID @Ac_Msg_CODE = @Enroll_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @Enroll_Desc_TEXT OUTPUT; -- Return status SELECT @Enroll_Msg_CODE AS Msg_CODE, @Enroll_Desc_TEXT AS Description;
Reports$Sp_Export_MyPerformance_Placements | DECLARE @MsgCode CHAR(5), @ErrorDesc NVARCHAR(4000); EXEC Reports$Sp_Export_MyPerformance_Placements @Ac_FilterType_TEXT = 'CT', @Ad_Start_DATE = '2025-01-28', @Ad_End_DATE = '2025-07-28', @Ac_Program_CODE = NULL, -- Example program code @Ai_SignedOnUser_ID = 456, -- Replace with actual user ID @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorDesc OUTPUT; SELECT @MsgCode AS MessageCode, @ErrorDesc AS ErrorDescription;
Reports$Sp_Export_CaseSummary | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC Reports$Sp_Export_CaseSummary @Ac_FilterType_TEXT = 'CT', -- 'LT', 'LN', 'LY', 'YT', or 'CT' @Ad_Start_DATE = '2025-01-01', -- Only required for 'CT' @Ad_End_DATE = '2025-10-06', -- Only required for 'CT' @Ac_Program_CODE = NULL, -- e.g., '01' or NULL for all programs @Ac_Status_CODE = NULL, -- e.g., 'A', 'C', etc. or NULL for all @Ai_SignedOnUser_ID = 1, -- Replace with a valid User_ID @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the output message SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Message;
Reports$Sp_Export_PlacementRate_ByProgram | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC Reports$Sp_Export_PlacementRate_ByProgram @Ai_SignedOnUser_ID = 1, -- replace with valid user ID @Ac_FilterType_TEXT = 'CT', -- 'LT', 'LN', 'LY', 'YT', or 'CT' @Ad_Start_DATE = '2025-01-01', -- only needed if FilterType is 'CT' @Ad_End_DATE = '2025-10-01', -- only needed if FilterType is 'CT' @Ac_Program_CODE = NULL, -- optional filter, e.g., 'PR' @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output messages SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError_TEXT;
Reports$Sp_Export_AverageWage_ByProgram | DECLARE @Ac_Msg_CODE CHAR(5), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC Reports$Sp_Export_AverageWage_ByProgram @Ai_SignedOnUser_ID = 1, -- Replace with a valid User_ID @Ac_FilterType_TEXT = 'CT', -- One of: 'LT', 'LN', 'LY', 'YT', 'CT' @Ad_Start_DATE = '2025-01-01', -- Only needed for 'CT' @Ad_End_DATE = '2025-10-01', -- Only needed for 'CT' @Ac_Program_CODE = NULL, -- Optional: e.g., 'PR' @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display the output SELECT @Ac_Msg_CODE AS Msg_CODE, @As_DescriptionError_TEXT AS DescriptionError_TEXT;
Reports$Sp_Export_SupportiveServiceDetails | DECLARE @MsgCode CHAR(5), @ErrorMessage VARCHAR(4000); EXEC Reports$Sp_Export_SupportiveServiceDetails @Ac_FilterType_TEXT = 'CT', -- 'LT', 'LN', 'LY', 'YT', 'CT' @Ad_Start_DATE = '2025-06-17', -- required only if 'CT' @Ad_End_DATE = '2025-09-29', -- required only if 'CT' @As_ServiceName_TEXT = 'Workforce Coaching', -- or use 'Transportation Assistance', etc. @Ai_SignedOnUser_ID = 12, -- replace with valid User_ID @Ac_Msg_CODE = @MsgCode OUTPUT, @As_DescriptionError_TEXT = @ErrorMessage OUTPUT; SELECT @MsgCode AS MsgCode, @ErrorMessage AS ErrorMessage;
DECLARE @UserEmployment_ID INT, @Msg_CODE CHAR(1), @DescriptionError_TEXT NVARCHAR(4000), @TransactionSeqEvent_NUMB INT; EXEC Employment$Sp_Add_UserEmployment @Ai_User_ID = 2171 ,@As_JobTitle_TEXT = N'Software Developer' ,@As_EmployerName_TEXT = N'TechCorp Inc.' ,@An_Salary_NUMB = 85000.00 ,@Ac_SalaryFrequency_CODE = 'HR' ,@Ad_StartDate_DATE = '2024-10-01' ,@As_Notes_TEXT = N'First job after graduation' ,@Ai_CreatedBy_ID = 2099 ,@An_TransactionSeqEvent_NUMB = @TransactionSeqEvent_NUMB ,@Ai_UserEmployment_ID = @UserEmployment_ID OUTPUT ,@Ac_Msg_CODE = @Msg_CODE OUTPUT ,@As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- To review the output SELECT @UserEmployment_ID AS UserEmployment_ID, @Msg_CODE AS Msg_CODE, @DescriptionError_TEXT AS DescriptionError;
DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT NVARCHAR(4000); EXEC usp_ReferralOutcome_Update_S1 @Ai_Referral_ID = 1, -- Replace with actual Referral_ID @As_ReferralOutcome_CODE = 'sp', -- Example: 'AC' for Accepted @As_ReferralOutcome_TEXT = 'service alreadshgidsfrg', -- Example outcome description @Ai_UpdatedBy_ID = 2066, -- Caseworker ID who is updating @An_TransactionSeqEvent_NUMB = 1, -- Transaction sequence event number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS Description;
DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000); -- Execute the stored procedure EXEC dbo.usp_CaseProgressNote_Update_S1 @Ai_ProgressNote_ID = 1, -- Replace with actual ProgressNote_ID @Ac_NoteType_CODE = 'GN', -- Replace with valid NoteType_CODE @Ac_Priority_CODE = 'H', -- Optional: 'H' for High, or NULL @As_Title_TEXT = N'My Updated Note Title', @As_Content_TEXT = N'This is the updated content of the note.', @As_Tags_TEXT = N'task,followup', -- Optional or NULL @Ab_PrivateNote_INDC = 0, -- 0 = public, 1 = private @Ai_UpdatedBy_ID = 1, -- Replace with valid User_ID @An_TransactionSeqEvent_NUMB = 1, -- Replace with actual sequence number @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- View the output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
DECLARE @Ac_Msg_CODE CHAR(1), @As_DescriptionError_TEXT VARCHAR(4000), @An_TransactionSeqEvent_NUMB BIGINT; -- Initialize @An_TransactionSeqEvent_NUMB to 0 if no prior transaction exists SET @An_TransactionSeqEvent_NUMB = 0; -- Execute the stored procedure EXEC dbo.usp_CaseProgressNote_Delete_S1 @Ai_ProgressNote_ID = 1, -- Replace with actual ProgressNote_ID @Ai_DeletedBy_ID = 1, -- Replace with valid User_ID of deleter @An_TransactionSeqEvent_NUMB = @An_TransactionSeqEvent_NUMB , @Ac_Msg_CODE = @Ac_Msg_CODE OUTPUT, @As_DescriptionError_TEXT = @As_DescriptionError_TEXT OUTPUT; -- Display the output SELECT @Ac_Msg_CODE AS MsgCode, @As_DescriptionError_TEXT AS ErrorMessage;
DECLARE @User_ID INT; DECLARE @Msg_Code CHAR(5); DECLARE @DescriptionError_TEXT VARCHAR(4000); EXEC dbo.usp_User_Add_S1 @Ai_Applicant_ID = 324, @As_Username_TEXT = 'FYJTYUU', -- Will be auto-generated if NULL @As_FirstName_TEXT = 'John', @As_MiddleName_TEXT = NULL, @As_LastName_TEXT = 'Doe', @Ad_BirthDate_DATE = '1990-01-01', @Ac_SSN_TEXT = '103-45-6719', @Ac_Gender_CODE = 'M', -- Must exist in dbo.RefGender @As_EmailAddress_TEXT = 'john.doe234578@example.com', @As_PhoneNumber_TEXT = '(121) 456-7890', @As_Passwordhash_TEXT = NULL, @As_PasswordSalt_TEXT = NULL, @As_Reference_ID = 'REF123456', @Ac_UserType_CODE = 'U', -- Must exist in dbo.RefUserType @Ai_CreatedBy_ID = 1, -- ID of the user performing the action @Ai_TransactionSeqEvent_NUMB = NULL, -- Will be auto-generated if NULL @Ai_User_ID = @User_ID OUTPUT, @Ac_Msg_Code = @Msg_Code OUTPUT, @As_DescriptionError_TEXT = @DescriptionError_TEXT OUTPUT; -- Optional: Print output values SELECT @User_ID AS Created_User_ID, @Msg_Code AS Message_Code, @DescriptionError_TEXT AS Message_Text;

## Parameter Changes
Procedure Name | Parameters | Datatype | Posistion | IN or OUT
usp_ReviewApplication_GetList_S1 | @Ai_SignedOnUser_ID | INT | 8 | IN
usp_Applicant_GetDetails_S1 | @Ai_Applicant_ID | INT | 1 | OUT
| @Ai_user_ID | INT | 2 | OUT
| @Ai_Workspace_ID | INT | 2 | OUT
| @As_EmploymentStatusDesc_TEXT | Varchar | 42 | OUT
| @As_HighSchoolDiplomaOrGEDDesc_TEXT | Varchar | 43 | OUT
| @As_LowIncomeDesc_TEXT | Varchar | 44 | OUT
usp_Applicant_UpdateBase_S1 | @Ab_SelectiveService_INDC | BIT | 25 | IN
| @Ab_TwoFactorEnabled_INDC | BIT | 26 | IN
| @As_LogoURL_TEXT | NVARCHAR | 27 | IN
| @As_PublicAssistance_JSON | NVARCHAR | 28 | IN
| @As_Barriers_JSON | NVARCHAR | 29 | IN
usp_ApplicantEligibleProgram_GetAll_S8 | EligibilityReason_TEXT | Varchar | 12 | CursorOut
dbo.Organization$SpGetOrganizationDetails | @As_PrimaryPhone_TEXT | NVARCHAR | 14 | OUT
| @Ai_ActiveContractsCount_NUMB | INT | 22 | OUT
| @An_AvgDaysToFillPosition_NUMB | INT | 23 | OUT
| @An_OverallRating_NUMB | DECIMAL(3, 2) | 24 | OUT
| @As_Ratings_TEXT | NVARCHAR | 25 | OUT
| @An_ReviewCount_NUMB | INT | 26 | OUT
| @As_CertificationsJSON_TEXT | NVARCHAR | 29 | OUT
| @As_ProfileCompletionJSON_TEXT | NVARCHAR | 30 | OUT
usp_MessageHistory_Fetch_S1 | @Ai_User_ID | INT | 2 | IN
| @Ai_Conversation_ID | INT | 1 | IN
| @As_Search_TEXT | Varchar | 3 | IN
| @Ai_SignedOnUser_ID | INT | 6 | IN
| @Ai_From_NUMB | INT | 7 | IN
| @Ai_To_NUMB | INT | 8 | IN
| @As_DescriptionError_TEXT | Varchar | 10 | IN
| Conversation_ID | INT | 1 | CursorOut
| Message_ID | INT | 2 | CursorOut
| Sender_ID | INT | 3 | CursorOut
| SenderUserName_TEXT | Varchar | 4 | CursorOut
| Receiver_ID | INT | 5 | CursorOut
| ReceiverUserName_TEXT | Varchar | 6 | CursorOut
| Message_TEXT | Varchar | 7 | CursorOut
| Active_INDC | bit | 8 | CursorOut
| HasAttachment_INDC | bit | 9 | CursorOut
| ConversationCreatedBy_ID | INT | 10 | CursorOut
| ConversationCreated_DTTM | Date | 11 | CursorOut
| Entity_ID | INT | 12 | CursorOut
| EntityType_CODE | char | 13 | CursorOut
| EntityType_Desc_TEXT | Varchar | 14 | CursorOut
| Topic_CODE | char | 15 | CursorOut
| Topic_Desc_TEXT | Varchar | 16 | CursorOut
| Read_DTTM | Date | 17 | CursorOut
| Edited_DTTM | Date | 18 | CursorOut
| Read_INDC | bit | 19 | CursorOut
| Attachments_JSON | Varchar | 20 | CursorOut
| MessageCreatedBy_ID | INT | 21 | CursorOut
| MessageCreated_DTTM | Date | 22 | CursorOut
| UpdatedBy_ID | INT | 23 | CursorOut
| Updated_DTTM | Date | 24 | CursorOut
| TransactionSeqEvent_NUMB | INT | 25 | CursorOut
| Row_NUMB | INT | 26 | CursorOut
| RowCount_NUMB | INT | 27 | CursorOut
usp_Conversation_CreateAndInsertMessage_S1 | Ai_Sender_ID | INT | 3 | IN
| Ac_SenderType_CODE | Char | 4 | IN
| Ai_Receiver_ID | INT | 5 | IN
| Ac_ReceiverType_CODE | Char | 6 | IN
Resume$Sp_Get_ResumeFullByID | @As_notableprojects_TEXT | NVARCHAR(200) | 12 | OUT
| @Ac_resumevisibility_CODE | CHAR(1) | 13 | OUT
Resume$Sp_update_ResumeSkill | @As_TechnicalSkills_TEXT | NVARCHAR(MAX) | 4 | IN
| @As_SoftSkills_TEXT | NVARCHAR(MAX), | 5 | IN
Resume$Sp_GetAll_ResumeWorkExperienceByResume | @Ai_From_NUMB | INT | 3 | IN
| @Ai_To_NUMB | INT | 4 | IN
| Ac_Msg_CODE | INT->CHAR(1) | 7 | OUT
Resume$Sp_Get_ResumeWorkExperience | @Ab_Delete_INDC | BIT | 11 | IN
Resume$Sp_GetAll_ResumeEducationByResume | @Ai_From_NUMB | INT | 3 | IN
| @Ai_To_NUMB | INT | 4 | IN
| @Ac_Msg_CODE | CHAR(1) | 7 | OUT
Resume$Sp_Update_ResumeEducation | @Ab_Delete_INDC | BIT | 9 | IN
Resume$Sp_GetAll_ResumeCertificationByResume | @Ai_From_NUMB | INT | 3 | IN
| @Ai_To_NUMB | INT | 4 | IN
| @Ac_Msg_CODE | INT-> CHAR | 7 | OUT
Resume$Sp_Update_ResumeAward | @Ab_Delete_INDC | BIT | 8 | IN
Resume$Sp_GetAll_ResumeReferenceByResume | @Ai_From_NUMB | INT | 3 | IN
| @Ai_To_NUMB | INT | 4 | IN
| Ac_Msg_CODE | INT-> CHAR | 6 | OUT
Resume$Sp_Update_ResumeReference | @Ab_Delete_INDC | BIT | 9 | IN
Resume$Sp_GetAll_ResumesByUser | @Ai_From_NUMB | INT | 5 | IN
| @Ai_To_NUMB | INT | 6 | IN
| Ac_Msg_CODE | INT-> CHAR | 9 | OUT
Resume$Sp_Add_ResumeFull | @AS_notableprojects_TEXT | NVARCHAR(200) | 12 | IN
| @Ac_resumevisibility_CODE | CHAR(1) | 13 | IN
| @jsTechnicalSkills_JSON | NVARCHAR(MAX) | 23 | IN
| @jsSoftSkills_JSON | NVARCHAR(MAX) | 24 | IN
|  | BIT | 29 | cursor out
| IsSaved_INDC | DATE | 31 | cursor out
| Deadline_DATE | VARCHAR(30) | 33 | cursor out
Job$SpSearchJobs | SavedUserTag_TEXT
|  | NVARCHAR(MAX) | 36 | IN
@As_SpecificNationality_JSON
|  | INT | 2 | IN
Job$SpSaveJob | @Ai_SignedOnUser_ID | NVARCHAR(MAX) | 34 | OUT
| @As_PreferredCountry_NAME | BIT | 55 | OUT
Job$SpGetJobDetails | @Ab_Save_INDC | VARCHAR(100) | 56 | OUT
data type length change | @As_PreferredNationalityDesc_TEXT
|  | VARCHAR(400) | 14 | cursor out
| Location_TEXT | INT | 27 | cursor out
Contract_ID
Job$SpGetJobOffers |  | VARCHAR(30) | 22 | cursor out
| ContractId_TEXT | VARCHAR(30) | 23 | cursor out
ContractStatusDesc_TEXT
Job$SpGetJobContracts |  | INT | 1 | IN and OUT
| @Ai_Contract_ID | NVARCHAR(100) | 2 | OUT
| @As_Contractid_TEXT | CHAR(1) | 7 | OUT
Job$SpGetJobContractDetails | @As_ContractStatus_CODE | NVARCHAR(50) | 8 | OUT
@As_ContractStatusDesc_TEXT
|  | VARCHAR(100) | 41 | cursor out
JobApplicationTag_TEXT
|  | VARCHAR(100) | 30 | cursor out
Job$SpGetJobApplications | JobInvitationTag_TEXT
|  | VARCHAR(100) | 28 | cursor out
Job$SpGetJobInvitations | JobOfferTag_TEXT
|  | CHAR(2) | 12 | OUT
Job$SpGetJobOffers | @Ac_PayPeriod_CODE
Resume$Sp_Get_ResumeJobPreference |  | NVARCHAR(200) | 12 | IN
| @AS_notableprojects_TEXT | CHAR(1 | 13 | IN
| @Ac_resumevisibility_CODE | NVARCHAR(MAX) | 23 | IN
Resume$Sp_Add_ResumeFull | @jsTechnicalSkills_JSON | NVARCHAR(MAX) | 24 | IN
@jsSoftSkills_JSON
|  | BIT | 9 | IN
@Ab_Delete_INDC
|  | CHAR | 31 | OUT
Resume$Sp_Update_ResumeFreelanceProfile | Ac_Gender_CODE | VARCHAR | 32 | OUT
| As_GenderDesc_TEXT | VARCHAR | 35 | OUT
usp_Get_Case_S1 | As_Address_TEXT | VARCHAR | 50 | OUT
Ac_CaseStatusDesc_TEXT
|  | NVARCHAR(1000) | 22 | IN
| @As_ExternalAPIEndpoint_TEXT | NVARCHAR(100) | 24 | IN
| @As_Tag_text | NVARCHAR(20) | 26 | IN
usp_Form_Add_S1 | @As_VisibilityOption_TEXT | CHAR(3) | 27 | IN
| @Ac_AccessRole_CODE | BIT | 29 | IN
| @Ab_EnableExport_INDC | NVARCHAR(MAX) | 30 | IN
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 31 | IN
@As_CustomJavaScript_TEXT
|  | NVARCHAR(1000) | 35 | OUT
| @As_ExternalAPIEndpoint_TEXT | NVARCHAR(20) | 38 | OUT
| @As_VisibilityOption_TEXT | CHAR(3) | 39 | OUT
usp_Form_Getall_S1 | @Ac_AccessRole_CODE | BIT | 41 | OUT
| @Ab_EnableExport_INDC | NVARCHAR(MAX) | 42 | OUT
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 43 | OUT
| @As_CustomJavaScript_TEXT | NVARCHAR(MAX) | 49 | OUT
@As_TAg_TEXT
|  | INT | 6 | IN
| @Ai_CreatedBy_ID | NVARCHAR(100) | 20 | IN
| @As_tag_text | NVARCHAR(1000) | 26 | IN
usp_Form_Update_S1 | @As_ExternalAPIEndpoint_TEXT | NVARCHAR(20) | 28 | IN
| @As_VisibilityOption_TEXT | CHAR(3) | 29 | IN
| @Ac_AccessRole_CODE | BIT | 31 | IN
| @Ab_EnableExport_INDC | NVARCHAR(MAX) | 32 | IN
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 33 | IN
@As_CustomJavaScript_TEXT
|  | INT | 13 | IN
| @Ai_CreatedBy_ID | NVARCHAR(100) | 27 | IN
| @As_tag_json | NVARCHAR(1000) | 33 | IN
usp_Form_UpdateInfoSettings_S1 | @As_ExternalAPIEndpoint_TEXT | NVARCHAR(20) | 35 | IN
| @As_VisibilityOption_TEXT | CHAR(3) | 36 | IN
| @Ac_AccessRole_CODE | BIT | 38 | IN
| @Ab_EnableExport_INDC | NVARCHAR(MAX) | 39 | IN
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 40 | IN
| @As_CustomJavaScript_TEXT | Char | 6 | IN | Previously it is INT
| Ac_Gender_CODE |  | removed
| An_OldClientTransactionSeqEvent_NUMB |  | removed
usp_Case_Update_S1 | An_NewClientTransactionSeqEvent_NUMB | CHAR | 14 | IN
| Ac_CaseStatus_CODE | Varchar | 1 | IN
| As_ServiceIDs_JSON | INT | 6 | IN
| Ai_SignedonUser_ID | CHAR(1) | 4 | IN
usp_ServiceNotes_Update_S1 | Ac_Status_CODE | CHAR(2) | 3 | IN
usp_Get_service_S1 | Ac_Servicecategory_CODE | INT | 5 | IN
| Ai_From_NUMB | INT | 6 | IN
| Ai_To_NUMB | VARCHAR | 5 | CURSOR OUT
| ServiceCategoryDesc_TEXT | VARCHAR | 7 | CURSOR OUT
| Status_Desc_TEXT | BIT | 8 | CURSOR OUT
| deleteEnable_INDC | BIT | 9 | CURSOR OUT
| IsDeleted_INDC | DATETIME | 10 | CURSOR OUT
| Deleted_DTTM | INT | 16 | CURSOR OUT
| Row_NUMB | INT | 17 | CURSOR OUT
| RowCount_NUMB | CHAR(1) | 3 | IN
| Ac_Priority_CODE | CHAR(1) | 4 | IN
| Ac_Status_CODE | INT | 5 | IN
usp_CaseService_Insert_S2 | Ai_AssignedTo_ID | DATE | 6 | IN
| Ad_Due_DATE | VARCHAR | 7 | IN
| As_Notes_TEXT | DECIMAL | 8 | IN
| An_Amount_NUMB | INT | 11 | OUT
| Ai_CaseService_ID | CHAR(1) | 4 | IN
| Ac_Priority_CODE | CHAR(1) | 5 | IN
| Ac_Status_CODE | INT | 6 | IN
usp_CaseService_Update_S1 | Ai_AssignedTo_ID | DATE | 7 | IN
| Ad_Due_DATE | VARCHAR | 8 | IN
| As_Notes_TEXT | DECIMAL | 9 | IN
| An_Amount_NUMB | NVARCHAR | 2 | IN
| As_SearchText | CHAR(1) | 3 | IN
| Ac_Status_CODE | CHAR(2) | 4 | IN
usp_Case_Service_Bycase_Get_S1 | Ac_ServiceCategory_CODE | CHAR(1) | 5 | IN
| Ac_Priority_CODE | INT | 6 | IN
| Ai_AssignedTo_ID | INT | 7 | IN
| Ai_From_NUMB | INT | 8 | IN
| Ai_To_NUMB | CHAR(1) | 5 | CURSOR OUT
| ServiceCategory_CODE | VARCHAR | 6 | CURSOR OUT
| ServiceCategoryDesc_TEXT | CHAR(1) | 7 | CURSOR OUT
| Priority_CODE | VARCHAR | 8 | CURSOR OUT
| PriorityDesc_TEXT | CHAR(1) | 9 | CURSOR OUT
| Status_CODE | VARCHAR | 10 | CURSOR OUT
| Status_Desc_TEXT | INT | 11 | CURSOR OUT
| AssignedTo_ID | VARCHAR | 12 | CURSOR OUT
| AssignedToName_TEXT | DATE | 13 | CURSOR OUT
| Due_DATE | VARCHAR | 14 | CURSOR OUT
| Notes_TEXT | INT | 15 | CURSOR OUT
| Amount_NUMB | INT | 21 | CURSOR OUT
| Row_NUMB | INT | 22 | CURSOR OUT
RowCount_NUMB
|  | INT | 7 | OUT
| @Ai_perentagecompletion | NVARCHAR(100) | 9 | OUT
@As_ProfileURL_TEXT
Resume$Sp_Get_Resumename |  | BIT | 5 | IN
Resume$Sp_Get_Resumepersonalinfo | @Ab_Certify_INDC | NVARCHAR(100) | 6 | IN
@As_profileURL_TEXT
Resume$Sp_update_Resume_personalinfo
|  | INT | 6 | IN
@Ai_resumecompletionpercentage INT OUTPUT,
|  | INT | 10 | IN
Resume$Sp_Get_Resumehobbies | @Ai_resumepercentcompletion
|  | INT | 8 | OUT
Resume$Sp_Get_ResumeJobPreference | @Ai_resumepercentcompletion
|  | NVARCHAR(100) |  | IN
Resume$Sp_Get_Resumevisibility | @As_ProfileURL_TEXT
|  | NVARCHAR(100) | 9 | OUT
.Resume$Sp_Add_ResumeFull | @As_ProfileURL_TEXT
|  | NVARCHAR(100) | 21 | OUT
Resume$Sp_Get_ResumeFullByID | @As_ProfileURL_TEXT
|  | INT | 2 | IN
Resume$Sp_DownloadResume | @Ai_RowFrom_NUMB | INT | 3 | IN
| @Ai_RowTo_NUMB | varchar | 4 | CURSOR OUT
Applicant$Sp_GetAllApplicants | EmailAddress_TEXT | bigint | 5 | CURSOR OUT
| TransactionSeqEvent_NUMB | INT | 6 | CURSOR OUT
RowCount_NUMB
|  | VARCHAR(500) | 25 | IN
| @As_Location_TEXT | CHAR(2) | 26 | IN
| @Ac_Color_CODE | INT | 27 | OUT
CALENDAR_Add_S1 | @Ai_Calendar_ID
|  | VARCHAR(500) | 25 | IN
(rename) | @As_Location_TEXT | NVARCHAR(250) | 26 | IN
@As_CalendarURL_TEXT
Calendar$Sp_Update_Calendar |  | VARCHAR(500) | 35 | OUT
| @As_Location_TEXT | CHAR(2) | 36 | OUT
| @Ac_Color_CODE | VARCHAR(30) | 37 | OUT
CALENDAR_RetrieveByID_S1 | @Ac_ColorDesc_TEXT
|  | CHAR(2) | 35 | cursor out
| Color_CODE | VARCHAR(30) | 36 | cursor out
| ColorDesc_TEXT | VARCHAR(500) | 37 | cursor out
CALENDAR_RetrieveAll_S1 | LocationAddress_TEXT
|  | INT | 7 | cursor out
| User_ID | INT | 8 | cursor out
workspace_ID
Calendar$SpGetCalendarAvailability |  | INT | 8 | IN
| @Ai_From_NUMB | INT | 9 | IN
| @Ai_To_NUMB | INT | 16 | cursor out
UNIT_RetrieveAll_S1 | RowCount_NUMB | INT | 17 | cursor out
rn
|  | BIGINT | 6 | IN
| @An_OldTransactionSeqEvent_NUMB | BIGINT | 7 | IN
@An_NewTransactionSeqEvent_NUMB
UNIT_UpdateWithMembers_S1 |  | BIGINT | 4 | IN
| @An_OldTransactionSeqEvent_NUMB | BIGINT | 5 | IN
@An_NewTransactionSeqEvent_NUMB
UNIT_UpdateStatus_S1 |  | INT | 12 | OUT
@Ai_MeetingRoom_ID (position and name change)
|  | BIGINT | 11 | IN
MeetingRooms$Sp_Add_MeetingRoom | @An_OldTransactionSeqEvent_NUMB | BIGINT | 12 | IN
@An_NewTransactionSeqEvent_NUMB
MeetingRooms$Sp_Update_MeetingRoom |  | BIGINT | 3 | IN
| @An_OldTransactionSeqEvent_NUMB | BIGINT | 4 | IN
@An_NewTransactionSeqEvent_NUMB
MeetingRooms$Sp_Delete_MeetingRoom |  | BIGINT | 4 | IN
| @An_OldTransactionSeqEvent_NUMB | BIGINT | 5 | IN
| @An_OldTransactionSeqEvent_NUMB | BIGINT | 3 | IN
usp_ApplicantDocument_MoveFolder_S1 | @An_OldTransactionSeqEvent_NUMB | BIGINT | 5 | IN
usp_ApplicantDocument_UpdateMetadata_S1 | @An_OldTransactionSeqEvent_NUMB | BIGINT | 21 | cursor out
usp_ApplicantDocument_UpdateVerificationStatus_S1 | TransactionSeqEvent_NUMB | BIGINT | 23 | cursor out
usp_ApplicantFolder_Update_S1 | TransactionSeqEvent_NUMB | BIGINT | 27 | cursor out
ApplicantDocuments$Sp_Get_VerifiedVersion | TransactionSeqEvent_NUMB | BIGINT | 19 | cursor out
usp_ApplicantDocument_GetAll_S1 | TransactionSeqEvent_NUMB | BIGINT | 21 | cursor out
usp_ApplicantDocument_GetDetails_S1 | TransactionSeqEvent_NUMB | BIGINT | 4 | cursor out
usp_ApplicantDocument_GetVersionHistory_S1 | TransactionSeqEvent_NUMB | BIGINT | 8 | cursor out
usp_ApplicantDocument_GetVersionHistoryByDocument_S1 | TransactionSeqEvent_NUMB | BIGINT | 9 | cursor out
usp_ApplicantFolder_GetAll_S1 | TransactionSeqEvent_NUMB | VARCHAR | 7 | cursor out
usp_ApplicantFolder_GetManage_S1 | MajorActivitySubject_TEXT | VARCHAR
usp_ApplicantFolder_GetTree_S1 | As_DescriptionError_TEXT
usp_Get_ProgramTimeline_ByCase_S1
usp_Case_ProgramService_Add_S1
|  | INT | 3
| @Ai_User_ID | INT | 4
| @Ai_Job_ID | VARCHAR(30) | 5
Calendar$SpGetAppointmentsByUser | @Ac_AppointmentType_CODE | BIT | 27
| ModifyEvent_INDC | BIT | 28
| InviteOthers_INDC | BIT | 29
SeeGuest_INDC
|  | BIT | 22
| @Ab_ModifyEvent_INDC | BIT | 23
| @Ab_InviteOthers_INDC | BIT | 24
Calendar$SpAddAppointment | @Ab_SeeGuest_INDC | BIT | 25
| @Ab_SendEmail_INDC | BIT | 26
@Ab_SendUserPhone_INDC
|  | BIT | 24
| @Ab_ModifyEvent_INDC | BIT | 25
| @Ab_InviteOthers_INDC | BIT | 26
Calendar$SpUpdateAppointment | @Ab_SeeGuest_INDC | BIT | 27
| @Ab_SendEmail_INDC | BIT | 28
| @Ab_SendUserPhone_INDC | INT | 30
@Ai_Appointment_ID
|  | BIT | 29
rename | @Ab_ModifyEvent_INDC | BIT | 30
| @Ab_InviteOthers_INDC | BIT | 31
Calendar$SpGetAppointment | @Ab_SeeGuest_INDC
|  | INT, | 5 | IN
@Ai_user_ID
usp_FormSubmission_Add_S1
|  | INT | 16 | out
| @Ai_user_ID | INT, | 5 | IN
@Ai_user_ID
usp_FormSubmission_RetrieveByID_S1 |  | BIT | 14 | Out
usp_FormSubmission_Update_S1 | @Ab_EnrollmentFlag_INDC | BIT | 15 | Out
| @Ab_PlacementFlag_INDC | BIT | 16 | Out
WIOA_SP_GET_REPORTS_MYPERFORMANCE | @Ab_RetentionFlag_INDC | BIT | 17 | Out
@Ab_CredentialFlag_INDC
|  | BIT | 11 | Out
| @Ab_PlacementFlag_INDC | BIT | 12 | Out
| @Ab_AvgWageFlag_INDC | BIT | 13 | Out
WIOA_SP_GET_REPORTS_PROGRAM_OUTCOMES | @Ab_CredentialFlag_INDC | VARCHAR(20) | 1 | IN
@As_FilterType_TEXT
|  | NVARCHAR(MAX) | 5 | out
@As_Services_TEXT
|  | Bigint | 14 | IN
WIOA_SP_GET_REPORTS_SERVICE_CATEGORY_SUMMARY | @An_OldTransactionSeqEvent_NUMB
|  | Bigint | 6 | IN
usp_Applicant_UpdateContactInformation | @An_NewTransactionSeqEvent_NUMB
|  | Char(1) | 5 | Out
dbo.Users$Sp_UpdatePassword | @Ac_Msg_CODE | NVARCHAR(20) | 7 | Out
| @As_PhoneNumber_TEXT | BIT | 20 | Out
WIOA_SP_GET_REPORTS_SERVICE_DETAILS | @Ab_TwoFactorEnabled_INDC | bit | 21 | Out
Users$Sp_Get_UserInfo | @Ab_IsLocked_INDC | DATETIME2 | 22 | Out
| @Ad_LastPasswordChange_DTTM | INT | 23 | Out
| @Ai_LoginCount_NUMB | DATETIME2 | 24 | Out
| @Ld_LastLogin_DTTM into @Ad_LastLogin_DTTM | int | 25 | Out
| @Ai_Role_ID | CHAR(10) | 26 | Out
COLUMN NAME CHANGE | @Ac_Role_CODE | NVARCHAR(100) | 27 | Out
| @As_RoleDesc_TEXT | INT | 28 | Out
| @Ai_Office_ID | NVARCHAR(100) | 29 | Out
| @As_OfficeName_TEXT | CHAR(10) | 30 | Out
| @Ac_OfficeCounty_CODE | NVARCHAR(100) | 31 | Out
| @As_OfficeCountyName_TEXT | CHAR(10) | 32 | Out
| @Ac_OfficeType_CODE | NVARCHAR(100) | 33 | Out
| @As_OfficeTypeDesc_TEXT | CHAR(1) | 34 | Out
| @Ac_EmploymentStatus_CODE | NVARCHAR(100) | 35 | Out
| @As_EmploymentStatusDesc_TEXT | CHAR(1) | 36 | Out
| @Ac_AccountStatus_CODE | NVARCHAR(50) | 37 | Out
| @As_AccountStatusDesc_TEXT | BIT | 38 | Out
@Ab_ForceReset_INDC
Resume$Sp_Delete_Resume | @Ai_candidate_ID (removed) | INT
Resume$Sp_Add_ResumeFull | @As_WorkExperience_TEXT | NVARCHAR(MAX), | 22 | IN
| @As_Education_TEXT | NVARCHAR(MAX), | 23 | IN
| @As_Certification_TEXT | NVARCHAR(MAX), | 24 | IN
| @As_TechnicalSkills_TEXT | NVARCHAR(MAX), | 25 | IN
| @As_SoftSkills_TEXT | NVARCHAR(MAX), | 26 | IN
| @As_Language_TEXT | NVARCHAR(MAX), | 27 | IN
| @As_Award_TEXT | NVARCHAR(MAX), | 28 | IN
| @As_Reference_TEXT | NVARCHAR(MAX), | 29 | IN
| @As_FreelanceProfile_TEXT | NVARCHAR(MAX), | 30 | IN
| @As_JobPreference_TEXT | NVARCHAR(MAX), | 31 | IN
| @As_ExternalAPIEndpoint_TEXT | NVARCHAR(1000) | 22 | IN
| @As_Tag_text | NVARCHAR(100) | 24 | IN
usp_Form_Add_S1 | @As_VisibilityOption_TEXT | NVARCHAR(20) | 26 | IN
| @Ac_AccessRole_CODE | CHAR(3) | 27 | IN
| @Ab_EnableExport_INDC | BIT | 29 | IN
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 30 | IN
| @As_CustomJavaScript_TEXT | NVARCHAR(MAX) | 31 | IN
| @As_ExternalAPIEndpoint_TEXT | NVARCHAR(1000) | 35 | OUT
| @As_VisibilityOption_TEXT | NVARCHAR(20) | 38 | OUT
usp_Form_Getall_S1 | @Ac_AccessRole_CODE | CHAR(3) | 39 | OUT
| @Ab_EnableExport_INDC | BIT | 41 | OUT
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 42 | OUT
| @As_CustomJavaScript_TEXT | NVARCHAR(MAX) | 43 | OUT
| @As_TAg_TEXT | NVARCHAR(MAX) | 49 | OUT
| @Ai_CreatedBy_ID | INT | 6 | IN
| @As_tag_text | NVARCHAR(100) | 20 | IN
usp_Form_Update_S1 | @As_ExternalAPIEndpoint_TEXT | NVARCHAR(1000) | 26 | IN
| @As_VisibilityOption_TEXT | NVARCHAR(20) | 28 | IN
| @Ac_AccessRole_CODE | CHAR(3) | 29 | IN
| @Ab_EnableExport_INDC | BIT | 31 | IN
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 32 | IN
| @As_CustomJavaScript_TEXT | NVARCHAR(MAX) | 33 | IN
| @Ai_CreatedBy_ID | NVARCHAR(100) | 27 | IN
| @As_tag_json | NVARCHAR(1000) | 33 | IN
usp_Form_UpdateInfoSettings_S1 | @As_ExternalAPIEndpoint_TEXT | NVARCHAR(20) | 35 | IN
| @As_VisibilityOption_TEXT | CHAR(3) | 36 | IN
| @Ac_AccessRole_CODE | BIT | 38 | IN
| @Ab_EnableExport_INDC | NVARCHAR(MAX) | 39 | IN
| @As_CustomCSS_TEXT | NVARCHAR(MAX) | 40 | IN
| @As_CustomJavaScript_TEXT | NVARCHAR(MAX) | 6 | IN
Sp_GetUpcomingAppointmentsByCaseMember | @Ai_From_NUMB | INT | 4 | IN
| @Ai_To_NUMB | INT | 5 | IN
dbo.usp_WIOA_Dashboard_OverdueTasksByCaseworker | @Ai_From_NUMB | INT | 4 | IN
| @Ai_To_NUMB | INT | 5 | IN
dbo.Applicant$Sp_GetLatestNewApplication | @Ai_From_NUMB | INT | 4 | IN
| @Ai_To_NUMB | INT | 5 | IN
usp_Announcement_GetActiveList_S1 | @Ai_From_NUMB | INT | 4 | IN
| @Ai_To_NUMB | INT | 5 | IN
Resume$Sp_Get_Resume_personalinfo
Resume$Sp_Add_ResumeLanguage | @As_Language_TEXT , | VARCHAR(10) | 3 | in
dbo.Resume$Sp_Update_ResumeLanguage | @As_Language_TEXT , | VARCHAR(10) | 3 | in
Applicant$Sp_GetLatestNewApplication | @Ai_From_NUMB | INT | 3 | IN
| @Ai_To_NUMB | INT | 4 | IN
Appointment$Sp_GetUpcomingAppointmentsByCaseMember | @Ai_From_NUMB | INT | 3 | IN
| @Ai_To_NUMB | INT | 4 | IN
usp_WIOA_Dashboard_OverdueTasksByCaseworker | @Ai_From_NUMB | INT | 3 | IN
| @Ai_To_NUMB | INT | 4 | IN
Resume$Sp_GetAll_ResumesByUser
Resume$Sp_GetAll_ResumeLanguageByResume | language_code --> Language_TEXT(cursor out modified)
Resume$Sp_GetAll_ResumesByUser | IsPrimary_INDC (added)
usp_FormSubmission_RetrieveAll_S1 | rowcount_Numb added (cursor out)
As_signedonuser_id (modified as input parameter)
usp_Form_RetrieveAll_S1 | Rowcount_Numb added (cursor out)
dbo.CustomReport$GetReportForView | @As_ClientField_TEXT | VARCHAR(200) | 3 | IN
| @Ai_RowFrom_NUMB | INT | 4 | IN
| @Ai_RowTo_NUMB | INT | 5 | IN
| @As_SearchName_TEXT | VARCHAR(200) | 6 | IN
| @Ai_CustomReport_ID | INT | 7 | OUT
| @Ai_Applicant_ID | INT | 8 | OUT
| @Ai_User_ID | INT | 9 | OUT
| @Ai_Workspace_ID | INT | 10 | OUT
| @As_DataJSON_TEXT | VARCHAR(MAX) | 11 | OUT
| @Ai_RowCount_NUMB | INT | 12 | OUT
Users$Sp_Get_UserInfo | @As_MiddleName_TEXT | NVARCHAR(100) | 6 | out
| @As_EmailAddress_TEXT | NVARCHAR(255) | 11 | out
Users$Sp_Get_UserDetails | @An_TransactionSeqEvent_NUMB | bigint | 17 | out
usp_Resume_SetPrimary_S1 | @Ai_user_ID | INT | 1 | IN
usp_Form_Add_S1 | @As_Submit_TEXT | VARCHAR(10) | 12 | IN
usp_Form_Getall_S1
| @As_RoleName_TEXT | VARCHAR(10) | 39 | OUT
| @As_visibleDESC_TEXT | VARCHAR(10) | 40 | OUT
| @As_Submit_TEXT | NVARCHAR(10) | 28 | OUT
usp_Form_Update_S1 |  |  | 29 | IN
|  |  | 30 | IN
| @As_Submit_TEXT | VARCHAR(10) | 21 | IN
usp_Form_UpdateInfoSettings_S1 | @As_Submit_TEXT | VARCHAR(10) | 28 | IN
usp_FormSubmission_RetrieveAll_S1 | submissions_COUNT | INT | CURSOR OUT
usp_CaseDocument_AddBatch_S1 | @Ai_form_ID | INT | 4 | IN
WIOA_SP_GET_REPORTS_MYPERFORMANCE | @Ac_ProgramCode | CHAR(2) | 4
usp_MyCaseload_List_S1 | CaseAction_ID | INT | 8 | CURSOR OUT
| Action_CODE | CHAR | 9 | CURSOR OUT
| ActionName_TEXT | VARCHAR | 10 | CURSOR OUT
| ActionDesc_TEXT | VARCHAR | 11 | CURSOR OUT
| Action_DTTM | DATETIME | 12 | CURSOR OUT
usp_DetailedPlan_User_Get_S1 | Ai_Case_ID | INT | 5 | IN
Users$Sp_Get_UserList | TransactionSeqEvent_NUMB | BIGINT | 12 | CURSOR OUT
dbo.CustomReport$SPGetCusReports | CreatedBy_ID | INT | 5 | Cursor out
WIOA_SP_GET_REPORTS_SERVICE_DETAILS | @Ai_RowFrom_NUMB | INT | 5 | IN
| @Ai_RowTo_NUMB | INT | 6 | IN
| RowCount_NUMB | INT | 6 | Cursor out
WIOA_SP_GET_REPORTS_CASELOADSUMMARY_TABLE | @Ai_RowFrom_NUMB | INT | 3 | IN
| @Ai_RowTo_NUMB | INT | 4 | IN
| RowCount_NUMB | INT | 6 | Cursor out
usp_CaseMinorActivity_Insert_S1 | As_Notes_TEXT | nvarchar | 5 | in
usp_CaseMinorActivity_Get_S1 | Notes_TEXT | VARCHAR | 10 | Cursor out
Users$Sp_PasswordReset_Confirm | As_EmailAddress_TEXT | VARCHAR | 2 | IN
usp_TwoFactorRecoveryCode_Update_S1 | As_RecoveryCode_TEXT | VARCHAR | 2 | IN
| As_EmailAddress_TEXT | VARCHAR | 3 | IN
| Ai_User_ID | INT | 4 | IN
Users$Sp_Delete_User | An_OldTransactionSeqEvent_NUMB | BIGINT | 5 | IN
| An_NewTransactionSeqEvent_NUMB | BIGINT | 6 | IN
Users$Sp_Get_UserList | MiddleName_TEXT | VARCHAR | 5 | Cursor out
| BirthDate_DATE | DATE | 6 | Cursor out
| SSN_TEXT | CHAR | 7 | Cursor out
| Gender_CODE | CHAR | 8 | Cursor out
| PhoneNumber_TEXT | VARCHAR | 9 | Cursor out
| UserType_CODE | CHAR | 10 | Cursor out
| UserTypeDesc_TEXT | nvarchar | 11 | Cursor out
| LogoURL_TEXT | NVARCHAR | 12 | Cursor out
| ProfileURL_TEXT | VARCHAR | 13 | Cursor out
| TwoFactor_INDC | BIT | 15 | Cursor out
| Role_CODE | char | 17 | Cursor out
| OfficeType_CODE | char | 20 | Cursor out
| OfficeTypeDesc_TEXT | nvarchar | 22 | Cursor out
| EmployerStatus_CODE | CHAR | 23 | Cursor out
| EmployerStatusDesc_TEXT | nvarchar | 24 | Cursor out
| Status_Desc | nvarchar | 26 | Cursor out
| InvitationSent_INDC | BIT | 28 | Cursor out
| ForceReset_INDC | BIT | 29 | Cursor out
| SecurityStateTransaction_NUMB | BIGINT | 31 | Cursor out
| OfficeAssignmentTransaction_NUMB | BIGINT | 32 | Cursor out
IssPlan_AddFull_S1 | Ai_Form_ID | INT | 2 | IN
Users$Sp_Get_UserInfo | @As_ProfileURL_TEXT | NVARCHAR | 12 | OUT
Users$Sp_Get_UserDetails | @As_ProfileURL_TEXT | NVARCHAR | 8 | OUT
usp_DashboardQuickNav_GetList_S1 | Ac_Screen_CODE | CHAR | 2 | IN
| Ai_SignedOnUser_ID | INT | 3 | IN
| Module_TEXT | VARCHAR | 1 | Cursor out
| Section_CODE | CHAR | 2 | Cursor out
| Section_TEXT | VARCHAR | 3 | Cursor out
| Count_TEXT | VARCHAR | 4 | Cursor out
Users$Sp_Update_Password | As_CurrentPassword_TEXT | NVARCHAR | 2 | IN
| As_NewPassword_TEXT | NVARCHAR | 3 | IN
| As_ConfirmNewPassword_TEXT | NVARCHAR | 4 | IN
usp_Get_Notifications_S1 | As_FilterType_CODE | CHAR | 3 | IN
usp_Duplication_Check_S1 | CaseReference_ID | VARCHAR | 3 | Cursor out
usp_Received_Referral_Get_S1 | Ai_Case_ID | INT | 5 | IN
usp_User_NotificationPreference_Get_S1 | QuietHoursEnabled_INDC | BIT | 11 | Cursor out
| QuietHoursStart_TIME | TIME | 12 | Cursor out
| QuietHoursEnd_TIME | TIME | 13 | Cursor out
usp_User_NotificationPreference_Update_S1 | As_QuietHours_JSON | NVARCHAR | 3 | IN
usp_UserProgress_Milestones_Add_S1 | As_Program_CODE renamed to (@As_Program_TEXT) | NVARCHAR(MAX) | 2 | IN
usp_UserProgress_Milestones_Get_S1 | Program_CODE | removed
| ProgramName_TEXT | removed
| Program_JSON | JSON | 6 | Cursor out
usp_UserProgress_GetParticipants_S1 | Program_CODE | removed
| ProgramName_TEXT | removed
| Program_JSON | JSON | 8 | Cursor out
usp_Duplication_Check_S1 | Ai_SignedOnUser_ID | INT | 9 | IN
| AssesmentCompleted_INDC | BIT | 12 | Cursor out
| Edit_INDC | BIT | 13 | Cursor out
usp_GoalActionItem_Add_S1 | @Ai_Service_ID | INT | 9 | IN
usp_Document_GetAll_S3 | FolderName_TEXT | VARCHAR |  | Cursor out
usp_Add_CaseNote_s1 | @As_NotesName_TEXT | VARCHAR | 4 | IN
usp_Get_CaseNote_s3 | NotesName_TEXT | VARCHAR | 4 | Cursor out
usp_Update_CaseNote_s1 | New Procedure
TrainingEnrollment_Add_S1 | New Procedure
TrainingEnrollment_Update_S1 | New Procedure
TrainingEnrollment_Delete_S1 | New Procedure
TrainingEnrollment_Get_S1 | New Procedure
Employment$Sp_Get_UserEmployment | SalaryFrequency_CODE | CHAR | 6 | Cursor out
| SalaryFrequencyDesc_TEXT | VARCHAR | 7 | Cursor out
UserEmployment_Delete_S1 | New Procedure
Employment$Sp_Add_UserEmployment | @Ac_SalaryFrequency_CODE | CHAR | 5 | IN
Employment$Sp_Update_UserEmployment | @Ac_SalaryFrequency_CODE | CHAR | 6 | IN
usp_CaseMinorActivity_Insert_S1 | @Ai_CaseMinorActivity_ID | INT | 20 | OUT
Columns are changed to Nullable
usp_CaseMinorActivity_Delete_S1 | New Procedure
usp_UserFollowUp_GetCompleted_S1 | New Procedure
usp_UserFollowUp_List_S1 | New Procedure
usp_UserFollowUp_Delete_S1 | New Procedure
usp_UserFollowUp_Complete_S1 | New Procedure
usp_UserFollowUp_Add_S1 | New Procedure
usp_Duplication_Check_S1 | @Ai_From_NUMB | INT | 9 | IN
| @Ai_To_NUMB | INT | 10 | IN
| Row_NUMB | INT | 14 | Cursor out
| RowCount_NUMB | INT | 15 | Cursor out
usp_IssPlan_Goals_Get_S1 | OverallProgress_NUMB | INT | 24 | Cursor out
usp_UserProgress_GetParticipants_S1 | UserProgress_ID | Removed
| IsActive_INDC | Removed
| @Ai_Case_ID | INT | 2 | IN
usp_Sent_Referral_Get_S1 | Created_DTTM | DATE | 24 | Cursor out
| CreatedByName_TEXT | VARCHAR | 23 | Cursor out
| UpdatedBy_ID | INT | 25 | Cursor out
| Updated_DTTM | DATE | 26 | Cursor out
usp_ReferralOutcome_Update_S1 | @As_Notes_TEXT | VARCHAR | 4 | IN
usp_MessageHistory_Fetch_S1 | Subject_TEXT | VARCHAR | 3 | Cursor out
usp_MyCaseload_Fetch_S1 | Edit_INDC |  |  | Cursor out
| Ac_TabCode_TEXT | VARCHAR | 10 | IN
| NAME_TEXT | Name paramter renamed
Applicant$Sp_GetAllApplicants | @As_SearchName_TEXT | NVARCHAR | 2 | IN
usp_ApplicantDocument_GetLatestVersions_S1 | New Procedure
usp_ApplicantDocument_GetDeleteDescription_S1 | New Procedure
usp_ApplicantFolder_GetTree_S1 | HasChildren | int | 4 | Cursor out
usp_ApplicantFolder_Add_S1 | @Ai_ParentFolder_ID -- input required
usp_ApplicantFolder_Update_S1 | New Procedure
ApplicantFolder$Sp_Delete_ApplicantFolder | New Procedure
Applicant_Get_With_Documents_S1 | @As_SearchName_TEXT | NVARCHAR | 2 | IN
ApplicantFolder$Sp_Get_ApplicantFolder | New Procedure
usp_ApplicantFolder_GetFolderList_S1 | New Procedure
ApplicantFolder$Sp_Get_DeleteConfirmation | New Procedure
Users$Sp_Get_UserDetails | As_PendingEmailInfo_TEXT | NVARCHAR | 29 | out
User$Sp_Create_User | As_Gender_CODE - nullable column
Office$Sp_Get_OfficeList | @As_SearchName_TEXT | NVARCHAR | 7 | in
Users$Sp_UpdateAccountStatus | New Procedure
Users$Sp_UpdateTwoFactorAuth | New Procedure
User$Sp_Update_UserProfile | Ab_ForceReset_INDC - nullable column
User$Sp_Update_UserProfile | As_Email_TEXT | NVARCHAR | 7 | in
Users$Sp_Get_UserList | PendingEmailInfo_TEXT | NVARCHAR | 28 | cursor out
User$Sp_ApproveEmailChange | New Procedure
User$Sp_GetEmailChangeAudit | New Procedure
Role$Sp_Get_RoleAccessList | New Procedure
Role$Sp_Update_MultipleRolePermissions | New Procedure
Announcement_GetDetails | New Procedure
Office$Sp_Update_Office | @As_OrganizationName_TEXT - nullable column
Org$SpSaveCandidate | Ai_Resume_ID - nullable column
usp_GetAllCandidatesByOrganization | UserSave_INDC |  | 13 | cursor out
| UserInvite_INDC |  | 14 | cursor out
| Ai_Organization_ID | int | 2 | in
| Ac_Education_CODE | char | 13 | in

## Sheet2
CW - API | C - API
GET ~/api/login/get/info | usp_DashboardQuickNav_GetList_S1
GET ~/api/login/authenticate-email | Job$SpGetJobApplications
PUT ~/api/login/logout
PUT ~/api/login/password/reset/confirm | Job$SpGetJobDetails
POST ~/api/login/password/reset/request | Job$SpGetJobApplications
GET~api/dashboard/dashboard/summary | Job$SpGetJobContracts
POST~/api/dashboard/overdue-tasks | Job$SpGetJobContractDetails
POST~/api/dashboard/appointments/upcoming | Job$SpGetJobContracts
Get~/api/dashboard/applicant/latest | usp_Applicant_GetDetails_S1
GET~api/dashboard/dashboard/snapshot | usp_Applicant_GetDetails_S1
GET ~ /api/arkansas/announcement/active-list | usp_Applicant_UpdateBase_S1
POST~/api/application/user/add | usp_Applicant_UpdateContactInformation
POST~ /api/application/applicant/insertbase | usp_Applicant_GetDetails_S1
POST~/api/application/applicant/barriers | usp_Applicant_GetDetails_S1
POST ~/api/application/applicant/{applicantId}/public-assistance | usp_Applicant_UpdateBase_S1
POST~/api/application/applicant/evaluate-eligibility | usp_ApplicantEligibleProgram_GetAll_S8
POST~/api/application/applicant/eligibleprograms | usp_ApplicantDocument_GetAll_S1
POST~ /api/application/applicant/addresses | usp_ApplicantDocument_Delete_S1
POST~ /api/application/documents/add | usp_ApplicantDocument_AddBatch_S1
POST~ /api/application/final-submit | Calendar$SpGetAppointment
POST~ /api/application/applicant/insert | Calendar$SpGetAppointmentsByUser
GET~/api/application/review/application-list | usp_User_ConversationSummary_GetList_S2
GET~/api/application/applicant/details | usp_MessageHistory_Fetch_S1
GET~/api/application/applicant/eligibleprograms | usp_Conversation_CreateAndInsertMessage_S1
GET ~/api/application/documents/getAllData | usp_Message_ReadStatus_Update_S1
PUT~/api/application/document/status | usp_Get_Notifications_S1
GET~/api/application/user/message-history | usp_Update_Notification_ReadStatus_S1
post~/api/application/conversation/create-insert-message | usp_Insert_NotificationRecipientActionLog_S1
PUT~/api/application/message/read-status/update | usp_Delete_Notification_S1
GET~/api/application/template/getall | Resume$Sp_GetAll_ResumesByUser
PUT~/api/application/applicant/updatebase
PUT~/api/application/applicant/eligibleprograms/update
PUT~/api/application/applicant/{applicantId}/public-assistance | Resume$Sp_Get_ResumeFullbyid
PUT~/api/application/applicant-barrier/update | Resume$Sp_Clone_ResumeByID
POST~/api/application/preliminary-note/add-update | Resume$Sp_Delete_Resume
GET~ /api/application/preliminary-note/get | Resume$Sp_Add_ResumeFull
PUT~/api/application/applicant/updatestatus | dbo.usp_Resume_SetPrimary_S1
POST ~ /api/application/case/create | Resume$Sp_DownloadResume
GET~/api/caseload/my-caseload/list | Resume$Sp_Add_Resumenameonly
GET ~/api/caseload/get/case | Resume$Sp_Get_Resumename
GET~/api/caseload/programtimeline/bycase | Resume$Sp_Update_Resumename
POST~ /api/caseload/add-submission | Resume$Sp_Update_Resumepersonalinfo
POST~/api/caseload/retrieve-submission | Resume$Sp_Get_Resumepersonalinfo
PUT~/api/caseload/update-submission | Resume$Sp_Update_Resumepersonalinfo
POST~/api/caseload/caseprogramservice/add | Resume$Sp_Add_ResumeWorkExperience
PUT~/api/caseload/caseprogramservice/status | Resume$Sp_Update_ResumeWorkExperience
PUT~/api/caseload/caseprogramservice/update | Resume$Sp_GetAll_ResumeWorkExperienceByResume
GET~/api/managecase/case/program-services | Resume$Sp_Add_ResumeEducation
Post ~/api/arkansas/iss-plan/full | Resume$Sp_GetAll_ResumeEducationByResume
Get ~/api/caseload/issplan/retrieve-by-id | Resume$Sp_Update_ResumeEducation
Put ~ /api/caseload/issplan/update | Resume$Sp_Add_ResumeCertification
PUT~/api/caseload/case-note/update | Resume$Sp_GetAll_ResumeCertificationByResume
GET~/api/caseload/case/note | Resume$Sp_Update_ResumeCertification
POST ~/api/caseload/case-note/add | Resume$Sp_Update_ResumeSkill
GET ~/api/managecase/duplication/check | Resume$Sp_GetAll_ResumeSkillByResume
GET~/api/caseload/get/case | Resume$Sp_Update_ResumeSkill
PUT~/api/managecase/case/update | Resume$Sp_Add_ResumeLanguage
PUT~/api/managecase/user/address/update | Resume$Sp_GetAll_ResumeLanguageByResume
GET~/api/managecase/organization/program/list | Resume$Sp_Update_ResumeLanguage
GET~/api/managecase/organization/program/services/list | Resume$Sp_Update_Resumehobbies
DELETE~/api/managecase/case/program/service/delete | Resume$Sp_Get_Resumehobbies
GET~/api/caseload/list | Resume$Sp_Update_Resumehobbies
GET~/api/managecase/case/primaryneeds | Resume$Sp_Add_ResumeFreelanceProfile
POST~/api/managecase/insert/case-service | Resume$Sp_Update_ResumeFreelanceProfile
PUT~/api/managecase/caseservice | Resume$Sp_GetAll_ResumeFreelanceProfileByResume
GET~/api/managecase/case/services | Resume$Sp_Add_ResumeAward
DELETE~/api/managecase/case/service | Resume$Sp_GetAll_ResumeAwardByResume
GET~/api/managecase/service/list | Resume$Sp_Update_ResumeAward
PUT~/api/managecase/service/notes | Resume$Sp_Add_ResumeJobPreference
POST~/api/managecase/insert/service | Resume$Sp_Get_ResumeJobPreference
PUT~/api/managecase/update/service | Resume$Sp_Update_ResumeJobPreference
DLEETE~/api/managecase/delete/service | Resume$Sp_Update_ResumeVisibility
POST~/api/managecase/referral/add | Resume$Sp_Get_Resumevisibility
GET~ /api/arkansas/referral/sent | Resume$Sp_Update_ResumeVisibility
PUT~/api/managecase/referral/update | Resume$Sp_Add_ResumeReference
PUT~/api/arkansas/referral/status | Resume$Sp_GetAll_ResumeReferenceByResume
POST~/api/managecase/referral-note | Resume$Sp_Update_ResumeReference
PUT~/api/managecase/referral-note | Job$SpSearchJobs
GET ~ /api/arkansas/referral/followup-history | Job$SpSaveUserJob
DELETE~/api/managecase/referral-note | Job$SpSaveUserJob
GET~/api/arkansas/referral/sent | Job$SpGetJobDetails
GET~/api/job/referral/received/list | Job$SpApplyJob
PUT~/api/managecase/update/referral/response | Organization$SpGetOrganizationDetails
PUT~/api/arkansas/referral/outcome/update | Job$SpGetSimilarJobs
GET ~ /api/managecase/detailed-plan/user Execption | Job$SpSaveJob
GET ~ /api/caseload/issplan/retrieve-by-id | Job$SpSaveUserJob
POST ~/api/managecase/issplan/goals | Job$SpApplyJob
POST ~ /api/managecase/goal | dbo.usp_Employer_GetList_S1
PUT ~ /api/arkansas/iss-goal | Organization$SpGetOrganizationDetails
DELETE ~ /api/arkansas/iss-goal | Organization$SpGetOrganizationDetails
PUT ~ /api/managecase/update/goal/action-item
DELETE ~ api/managecase/delete/goal/action-item | dbo.Review$GetAllByUserAndOrganization
POST ~ api/managecase/goal-action-item/add | Job$SpGetJobInvitations
GET~/api/managecase/fetch/goal/action-item | Job$SpGetJobInvitationDetails
Put ~/api/managecase/goal-action-item/update-status | Job$SpGetJobDetails ,Organization$SpGetOrganizationDetails
GET ~ api/managecase/user-progress/participants | Job$SpApplyJob
GET ~ api/managecase/user-progress/milestones | Job$SpSaveUserJob
GET ~ api/managecase/progress-outcome/get | usp_MessageHistory_Fetch_S1
POST ~ api/managecase/user-progress/add-with-milestones | Job$SpUpdateJobInvitationStatus
DELETE ~ api/managecase/user-progress/delete-by-case | Job$SpGetJobApplications
GET ~ api/managecase/milestone-notes/list | Job$SpGetJobApplications
PUT ~ api/managecase/milestones/update-status | Job$SpGetJobApplications
POST ~ api/managecase/progress-outcome/add | Job$SpGetJobApplications
PUT ~ api/managecase/progress-outcome/update | Job$SpUpdateJobApplicationStatus
POST ~ /api/managecase/insert/case-minor-activity | Job$SpGetSimilarJobs
PUT ~/api/managecase/caseminoractivity/updatestatus | Organization$SpGetOrganizationDetails
GET~/api/managecase/case/minor-activities | Calendar$SpGetAppointment
PUT ~ /api/managecase/update/case-major-activity-status | [Job$SpGetJobOfferDetails]
GET ~ /api/managecase/case/major-activities | Job$SpGetJobContractDetails
POST~/api/managecase/case/majoractivity | Job$SpUpdateJobOfferStatus
POST~/api/managecase/case/primaryneeds | Job$SpUpdateJobOfferStatus
PUT~/api/managecase/case/primaryneeds | dbo.Job$SpGetJobContracts
POST~ /api/managecase/referral/add | Job$SpGetJobContractDetails
GET~ /api/managecase/allReferral/details | Job$SpUpdateJobContractStatus
GET~/api/managecase/partner-agency/list | Job$SpUpdateJobContractStatus
DELETE~ /api/managecase/referral/delete
GET~/api/managecase/referral/details | Job$SpGetContractPaymentInfo
GET~/api/managecase/case/list | Job$SpGetUserContractDocuments
PUT~/api/managecase/goal | usp_EndContractAndSubmitReview
GET~/api/managecase/case/goals-report | usp_MessageHistory_Fetch_S1
PUT/api/managecase/goal/update
DELETE/api/managecase/goal/delete
POST/api/managecase/goal-action-item/add
Update~/api/managecase/update/goal/action-item
DELETE ~/api/managecase/delete/goal/action-item | Sp_StartProjectTracking,Sp_StopProjectTracking
GET~ /api/managecase/referral/active
GET /api/managecase/case/get-case-percent | GetClientWorkDiary
GET /api/managecase/program/get-outcomes | GetWorkDiaryWeeklySummary
GET/api/managecase/goal/detail
GET~ /api/managecase/activities | GetWorkDiaryWeeklySummary
POST~/api/customcase/custom-case-service/add
PUT~/api/customcase/custom-case-service/update
DELETE~/api/customcase/custom-case-service/delete
GET~/api/customcase/custom-case-service/get-by-id
GET~/api/arkansas/calendar/appointments | GetTimesheetEntriesByDate
Get~/api/appointments/calendar/list | AddTimesheetEntry
POST~ /api/appointments/calendar/add | updatertimesheetentry
Put~/api/appointments/update | GetWorkHistoryByPayPeriod
Get~/api/appointments/calendar
DELETE ~/api/appointments/delete | GetTimesheetSummaryByProject
PUT ~/api/appointments/update-status | GetTimesheetSummaryByProject
PUT~/api/appointments/calendar/update-availability | usp_Get_Notifications_S1
GET~/api/appointments/calendar/availability | usp_User_ConversationSummary_GetList_S2
GET~/api/appointments/calendar/share-link/temp | usp_MessageHistory_Fetch_S1
POST~/api/appointments/calendar/share-link/add | usp_Get_Notifications_S1
PUT~/api/appointments/calendar/share-link/expire
GET ~ /api/appointments/calendar/share-link/workspace
GET ~ /api/appointments/calendar/unavailable-slots
POST~/api/appointments/user/default-working-hours
PUT~/api/appointments/working-hours/save | dbo.Review$GetAllByUserAndOrganization
GET~ /api/appointments/user/working-hours | dbo.Users$Sp_UpdatePassword
POST ~/api/appointments/insert-with-members
PUT ~ /api/appointments/unit/update-with-members
GET ~ /api/appointments/unit/list
GET ~ /api/appointments/unit/detail
PUT ~ /api/appointments/unit/status
POST ~ /api/appointments/add/meeting-room
POST ~ /api/appointments/update/meeting-room
DELETE ~ /api/appointments/delete/meeting-room | AddTimesheetEntry
GET ~ /api/appointments/get/meeting-rooms | updateTimesheetEntry
GET ~ /api/appointments/get/meeting-room-info | Timesheet$Sp_Get_DailyTimesheetEntry
POST ~ /api/appointments/add/appointment | Timesheet$Sp_Get_ConsolidatedTimesheetDetails
PUT~ /api/appointments/calendar/appointment | timesheet$GetTimesheetSummaryDetails
DELETE ~ /api/appointments/delete/appointment | GetWorkHistoryByPayPeriod
GET~ /api/appointments/calendar/appointment | GetTimesheetSummaryByProject
GET~/api/appointments/calendar/availability-slots | GetTimesheetEntriesByDate
POST ~ /api/appointments/calendar/share-appointment | dbo.timesheet$gettimesheetentry_details
PUT ~ /api/appointments/calendar/update-rsvp-status | Contract$Sp_Get_RecentTransactions
POST /api/documents/applicant-document/add-batch | Timesheet$Sp_AddOrUpdate_Entry
GET ~/api/documents/applicants/all | Timesheet$Sp_Get_ActiveNow
GET/api/documents/list | Timesheet$Sp_Get_EntriesByDateRange
GET~/api/documents/applicant/document/details | Timesheet$Sp_Get_EntryDetails
PUT/api/documents/document/update-metadata | Timesheet$Sp_Get_HoursByType
POST/api/documents/applicant/document/delete | Timesheet$Sp_Get_PendingList
PUT/api/documents/applicantdocument/updateverificationstatus | Timesheet$Sp_Get_Summary
POST /api/documents/applicant-document/add-new-version | Timesheet$Sp_Get_SummaryView
GET/api/documents/version-history | Timesheet$Sp_Get_WorkDiary
GET~/api/documents/applicant-document/verified-version | Timesheet$Sp_SubmitForReview
DELETE/api/documents/document/delete/version | Timesheet$Sp_Update_Status_S1
PUT/api/documents/move-document-folder | WorkDiary$Sp_GetActivityTimeline
GET /api/documents/applicant/{applicantId}/folders/manage | WorkDiary$Sp_Get_Summary
GET /api/documents/applicant/{applicantId}/folders/tree | WorkDiary$Sp_Get_SummaryMetrics
GET /api/documents/applicant/{applicantId}/folders | WorkDiary$Sp_Get_UserContractProjects
GET /api/documents/applicant/{applicantId}/document/version-history | WorkDiary$Sp_StartTracking
POST /api/documents/applicant/folder/add | WorkDiary$Sp_StopTracking
POST~/api/forms/add | WorkDiary$Sp_Upsert_UserSessionSettings
GET~ /api/forms/details
GET~ /api/forms/allform/list
PUT /api/forms/update
PUT /api/forms/update-info-settings
POST /api/forms/form-submission/add
GET /api/forms/form-submission/list
GET /api/forms/form-submission/retrieve
PUT /api/forms/form-submission/update
PUT /api/forms/update-status
GET ~ api/forms/dashboard/forms/by-form-type
GET ~ /api/forms/form/history
GET ~ api/forms/form/download
GET ~ api/forms/plan/form/download"
GET ~ /api/forms/client/form-selection"
POST ~ /api/forms/add/formNote"
POST ~ /api/job/save
PUT ~ /api/job/update/job-status
GET~ /api/job/search
POST~ /api/job/user/save
GET~/api/job/details
POST~/api/job/apply
GET~/api/job/similar-jobs
GET ~ /api/job/organization/details
POST~/api/job/add/invitation
PUT~ /api/job/invitation/status
GET~/api/job/invitations
GET/api/job/invitation-details
GET/api/job/application/list
GET/api/job/application/details
GET/api/job/offer
POST/api/job/offer/add
PUT/api/job/offer/update
Get/api/job/offer/status
Get/api/job/joboffers
Put/api/job/update-job-application-status
GetMapping/api/job/organization/details
POST ~/api/job/job-contract/add
GET~/api/job/contract/detail
GET~/api/job/contracts
PUT~/api/job/contract/update
PUT~/api/job/job-contract/update-status
GET~/api/job/contract/activity/list
GET~/api/job/employer/list
GET~/api/arkansas/organization/details
POST~ /api/resume/add-full
PUT /api/resume/update-full
Get~/api/resume/full-by-id
POST~/api/resume/add/resume
PUT~/api/resume/update/resume
GET~/api/resume/get/by-resume-id
GET~/api/resume/get/all/by-user
POST~/api/resume/add/work-experience
GET~/api/resume/get/work-experience/by-id
GET~/api/resume/get/work-experience/by-resume
PUT~/api/resume/update/resume/education
GET~/api/resume/get/education/by-id
GET /api/resume/education/list
POST~ /api/resume/resume/certification/add
GET /api/resume/certification
GET /api/resume/certification/list
PUT /api/resume/skill/update
GET~/api/resume/fetch/skill
GET~/api/resume/skill/list
PUT~/api/resume/language/update
GET~/api/resume/get/language
GET~/api/resume/language/list
POST~/api/resume/award/add
PUT~/api/resume/award/update
GET~/api/resume/gte/award
GET~/api/resume/award/list
POST~/api/resume/reference/add
PUT~/api/resume/reference/update
GET~/api/resume/get/reference
GET~/api/resume/get/references
POST~api/resume/add/freelance
PUT~api/resume/update/freelance
GET~api/resume/get/freelance
GET~api/resume/get/freelance/list
POST~api/resume/add/job-preference
PUT~api/resume/update/job-preference
GET~api/resume/get/job-preference
GET~api/resume/get/job-preference/list
GET /api/arkansas/program/get-performance
POST~ /api/arkansas/wioa/monthly-trends
POST~ /api/arkansas/wioa/caseload-summary-chart
POST~ /api/arkansas/wioa/caseload-summary-table
GET /api/arkansas/program/get-outcomes
GET /api/arkansas/program/get-comparison
GET ~ /api/arkansas/wioa/report/service-category-summary
GET ~ /api/arkansas/wioa/report/service-details
POST - /api/arkansas/office/insert
GET -/api/arkansas/organization/list
POST~/api/arkansas/announcement
PUT - /api/arkansas/announcement/update
DELETE -/api/arkansas/announcement/delete
GET~/api/arkansas/announcement/list
GET ~ /api/arkansas/reference-data
POST ~ /api/arkansas/get/user-list
POST~ /api/login/add/two-factor-device
PUT~/api/login/update/two-factor-device-status
GET~/api/login/get/two-factor-device
PUT~/api/login/update/two-factor-device
POST~/api/login/add/two-factor-recovery-code
POST~/api/login/add/two-factor-verification-log
GET~/api/login/get/two-factor-recovery-code
PUT~/api/login/update/two-factor-recovery-code
GET~/api/login/get/two-factor-devices
PUT ~ /api/arkansas/user/update/personal-info
PUT ~ /api/arkansas/user/update/password
PUT ~ /api/arkansas/user/update/twofactor-device
GET ~ /api/login/twofactor/recovery-codes
PUT ~ /api/login/user/update/profile-picture
POST ~ /api/login/user/settings
GET ~ /api/login/user/settings
POST ~ /api/login/office/add
PUT ~ /api/login/office/update
DELETE ~ /api/login/office/delete
GET ~ /api/arkansas/office/list
GET ~ /api/login/user/list
POST ~ /api/login/create/user
PUT ~ /api/login/profile
PUT ~ /api/login/bulk/account-status
PUT ~ /api/login/bulk/role
POST ~ /api/login/with-recipients
GET ~ /api/login/fetch/recipients
GET ~ /api/login/user/details
GET ~ /api/login/audit-log/timeline
DELETE ~ /api/login/delete/user
GET ~ /api/login/user-count
GET~ /api/login/users/by-role
GET~ /api/login/role/list
GET~ /api/login/role/details
PUT~ /api/login/bulk/office-update
PUT ~ /api/login/user/update-role
PUT ~ /api/login/user/update-lock-status
POST ~ /api/login/user/send-invitation-email
GET~ /api/customreport/custom-report/list
POST~ /api/customreport/create
GET~ /api/customreport/check-name-availability
GET~ /api/customreport/custom-report/view
POST~ /api/customreport/custom-report/export
POST~ /api/customreport/custom-report/record-view
PUT~ /api/customreport/custom-report/update
DELETE~ /api/customreport/delete